## ABC-2015-02-00_
AURORA DISTRICT ENGINEERING OFFICE
FORM ABC-2015-02-00
CONSTRUCTION OF ROAD
BRGY. L. PIMENTEL, SAN LUIS, AURORA
SUMMARY OF APPROVED BUDGET FOR THE CONTRACT
[10 empty] | Contract Duration : |  | 65
ITEM NO. | DESCRIPTION |  |  | ESTIMATED DIRECT COST |  | TOTAL MARK-UP |  |  | VAT | TOTAL INDIRECT COST |  | TOTAL COST
[6 empty] | % | VALUE
PART A | FACILITIES FOR THE ENGINEER |  | AS EVALUATED
|  |  | AS SUBMITTED | 48948.07 |  | 20% | 9789.61 |  | 2936.88 | 12726.49 |  | 61674.56
PART B | OTHER GENERAL REQUIREMENTS |  | AS EVALUATED
|  |  | AS SUBMITTED | 201538.18 |  | 6.154% | 12402.75 |  | 10697.04 | 23099.79 |  | 224637.97
PART C | EARTHWORK |  | AS EVALUATED
|  |  | AS SUBMITTED | 775217.54 |  | 20% | 155043.5 |  | 46513.06 | 201556.56 |  | 976774.1
PART D | SUBBASE AND BASE COURSE |  | AS EVALUATED
|  |  | AS SUBMITTED | 1035926.63 |  | 20% | 207185.33 |  | 62155.6 | 269340.93 |  | 1305267.56
PART E | SURFACE COURSES |  | AS EVALUATED
|  |  | AS SUBMITTED | 4672524.15 |  | 20% | 934504.83 |  | 280351.45 | 1214856.28 |  | 5887380.43
PART F | DRAINAGE AND SLOPE PROTECTION STRUCTURES |  | AS EVALUATED
|  |  | AS SUBMITTED | 1066877.28 |  | 20% | 213375.46 |  | 64012.64 | 277388.1 |  | 1344265.38
TOTAL |  |  | AS EVALUATED
|  |  | AS SUBMITTED | 7801031.85 |  |  | 1532301.48 |  | 466666.67 | 1998968.15 |  | 9800000 | TRUE
Note: Prices/Rates were based on CMPD 4TH Quarter CY 2022 for Materials, Memorandum dated December 29, 2022 for Labor cost and Memorandum dated May 18, 2022 for Equipment rental including Fuel & Oil/Lubricant cost as of January 4, 2023 for DPWH Regional/District Engineering Offices | [12 empty] | TRUE
Preparation and Submission: |  |  |  |  | Evaluation: |  |  | Approval:
TRUE
Prepared by: |  | Checked/Submitted by: |  |  | Reviewed as to Unit Cost: |  |  | Recommending Approval: |  |  | Approved: |  | TRUE
TRUE
WINLOVE A. ESTEVES |  | MARK ANGELO E. SURIL |  |  | NICOMEDES G. NOHAY |  |  | BENELITO D. PASCUA |  |  | RODERICK A. ANDAL
Engineer II |  | Engineer II |  |  | Engineer III |  |  | Engineer III |  |  | District Engineer
Planning and Design Section |  | Planning and Design Section |  |  | Planning and Design Section |  |  | Concurrent OIC Assistant District Engineer

## ABC-2015-02A-00
AURORA DISTRICT ENGINEERING OFFICE
ATTACHMENT "A"
D.O. No. 197, Series of 2016
CONSTRUCTION OF ROAD
BRGY. L. PIMENTEL, SAN LUIS, AURORA
APPROVED BUDGET FOR THE CONTRACT
Stations: | LOCATION 1 | 0 | TO | 741
| LOCATION 2 | 0 | TO | 222
Net Length: | 1.926 | Lane km
[14 empty] | Contract Duration : |  | 65
ITEM NO. | DESCRIPTION |  |  |  | QUANTITY | UNIT | ESTIMATED DIRECT COST | MARK-UPS IN PERCENT |  | TOTAL MARK-UP |  | VAT | TOTAL INDIRECT COST | TOTAL COST |  | UNIT COST | DIRECT UNIT COST
[10 empty] | % | VALUE
-1 | -2 |  |  |  | -3 | -4 | -5 | OCM | PROFIT | -8 | -9 | -10 | -11 | -12 |  | -13
[8 empty] | -6 | -7 |  | (5) x (8) | 5%[(5)+(9)] | (9) + (10) | (5) + (11) |  | (12)/(3)
PART A | FACILITIES FOR THE ENGINEER
A.1.1 (3) | Construction of Field Office for the Engineer |  |  |  | 1 | ls | 48948.07 | 12% | 8% | 20% | 9789.61 | 2936.88 | 12726.49 | 61674.56 |  | 61674.56 | 48948.07 | 0
TOTAL OF PART A | [6 empty] | 48948.07 |  |  |  | 9789.61 | 2936.88 | 12726.49 | 61674.56
PART B | OTHER GENERAL REQUIREMENTS
B.5 | Project Billboard/ Signboard (DPWH) |  |  |  | 2 | ea | 6832.04 | 12% | 8% | 20% | 1366.41 | 409.92 | 1776.33 | 8608.37 |  | 4304.19 | 3416.02 | 0
B.5 | Project Billboard/ Signboard (COA) |  |  |  | 1 | ea | 6832.04 | 12% | 8% | 20% | 1366.41 | 409.92 | 1776.33 | 8608.37 |  | 8608.37 | 6832.04 | 0
B.7 (2) | Occupational Safety and Health Program |  |  |  | 1 | ls | 109314.5 | 0% | 8% | 8% | 8745.16 | 5902.98 | 14648.14 | 123962.64 |  | 123962.64 | 109314.5 | 0
B.8(2) | Road Works Safety and Traffic Management |  |  |  | 1 | ls | 11559.6 | 0% | 8% | 8% | 924.77 | 624.22 | 1548.99 | 13108.59 |  | 13108.59 | 11559.6 | 0
B.9 | Mobilization/ Demobilization |  |  |  | 1 | ls | 67000 | 0% | 0% | 0% | 0 | 3350 | 3350 | 70350 |  | 70350 | 67000 | 0
TOTAL OF PART B | [6 empty] | 201538.18 |  |  | 20% | 12402.75 | 10697.04 | 23099.79 | 224637.97
PART C | EARTHWORK
100(3)a1 | Individual Removal of Trees (150-300 mm dia., Small) |  |  |  | 0 | ea | 0 | 12% | 8% | 20% | 0 | 0 | 0 | 0 |  | #DIV/0! | 1747.39 | 0
102(2) | Surplus Common Excavation |  |  |  | 800.05 | cum | 184315.52 | 12% | 8% | 20% | 36863.1 | 11058.93 | 47922.03 | 232237.55 |  | 290.28 | 230.38 | 0
104(2)a | Embankment from Borrow (Common Soil) |  |  |  | 848.88 | cum | 468581.76 | 12% | 8% | 20% | 93716.35 | 28114.91 | 121831.26 | 590413.02 |  | 695.52 | 552 | 0
105(1)a | Subgrade Preparation (Common Material) |  |  |  | 5778 | sqm | 122320.26 | 12% | 8% | 20% | 24464.05 | 7339.22 | 31803.27 | 154123.53 |  | 26.67 | 21.17 | 0
TOTAL OF PART C | [6 empty] | 775217.54 |  |  |  | 155043.5 | 46513.06 | 201556.56 | 976774.1
PART D | SUBBASE AND BASE COURSE
200(1) | Aggregate Subbase Course |  |  |  | 1551.95 | cum | 1035926.63 | 12% | 8% | 20% | 207185.33 | 62155.6 | 269340.93 | 1305267.56 |  | 841.05 | 667.5 | 0
TOTAL OF PART D | [6 empty] | 1035926.63 |  |  |  | 207185.33 | 62155.6 | 269340.93 | 1305267.56
PART E | SURFACE COURSES
311(1)b1 | Portland Cement Concrete Pavement (Unreinforced, 0.20m thick, 14 days) |  |  |  | 4815 | sqm | 4672524.15 | 12% | 8% | 20% | 934504.83 | 280351.45 | 1214856.28 | 5887380.43 |  | 1222.72 | 970.41 | 0
TOTAL OF PART E | [6 empty] | 4672524.15 |  |  |  | 934504.83 | 280351.45 | 1214856.28 | 5887380.43
PART F | DRAINAGE AND SLOPE PROTECTION STRUCTURES
506(1) | Stone Masonry(Slope Protection) |  |  |  | 336 | cum | 1066877.28 | 12% | 8% | 20% | 213375.46 | 64012.64 | 277388.1 | 1344265.38 |  | 4000.79 | 3175.23 | 0
TOTAL OF PART F | [6 empty] | 1066877.28 |  |  |  | 213375.46 | 64012.64 | 277388.1 | 1344265.38
GRAND TOTAL | [6 empty] | 7801031.85 |  |  |  | 1532301.48 | 466666.67 | 1998968.15 | 9800000 |  |  | TRUE
Note: Prices/Rates were based on CMPD 4TH Quarter CY 2022 for Materials, Memorandum dated December 29, 2022 for Labor cost and Memorandum dated May 18, 2022 for Equipment rental including Fuel & Oil/Lubricant cost as of January 4, 2023 for DPWH Regional/District Engineering Offices | [16 empty] | TRUE
Preparation and Submission: |  |  |  |  | Evaluation: | [11 empty] | TRUE
TRUE
Prepared by: |  |  | Checked/Submitted by: |  | Reviewed as to Unit Cost: | [11 empty] | TRUE
WINLOVE A. ESTEVES |  |  | MARK ANGELO E. SURIL |  | NICOMEDES G. NOHAY
Engineer II |  |  | Engineer II |  | Engineer III
Planning and Design Section |  |  | Planning and Design Section |  | Planning and Design Section

## ABC-2015-02A-00__(1)
AURORA DISTRICT ENGINEERING OFFICE
ATTACHMENT "A"
D.O. No. 197, Series of 2016
CONSTRUCTION OF ROAD
BRGY. L. PIMENTEL, SAN LUIS, AURORA
APPROVED BUDGET FOR THE CONTRACT
Stations: | LOCATION 1 | 0 | TO | 741
| LOCATION 2 | 0 | TO | 222
Net Length: | 1.926 | Lane km
[15 empty] | Contract Duration : |  | 65
ITEM NO. | DESCRIPTION |  |  |  | QUANTITY | UNIT | ESTIMATED DIRECT COST | MARK-UPS IN PERCENT |  | TOTAL MARK-UP |  | VAT | TOTAL INDIRECT COST |  | TOTAL COST |  | UNIT COST | DIRECT UNIT COST
[10 empty] | % | VALUE | [8 empty] | NOTE:
-1 | -2 |  |  |  | -3 | -4 | -5 | OCM | PROFIT | -8 | -9 | -10 | -11 |  | -12 |  | -13 |  |  |  | tingnan kung equal yung mga decimals ng VAT TOT IND at TC sa POW
[8 empty] | -6 | -7 |  | (5) x (8) | 5%[(5)+(9)] | (9) + (10) |  | (5) + (11) |  | (12)/(3) |  |  |  | check mo yung mga naka link at sum kung may de naiisama kapag de nageequal
PART A | FACILITIES FOR THE ENGINEER
A.1.1 (3) | Construction of Field Office for the Engineer |  |  |  | 1 | ls | 48948.07 | 12% | 8% | 20% | 9789.61 | 2936.88 | 12726.49 |  | 61674.56 |  | 61674.56 | 48948.07 | 0
TOTAL OF PART A | [6 empty] | 48948.07 |  |  |  | 9789.61 | 2936.88 | 12726.49 |  | 61674.56
PART B | OTHER GENERAL REQUIREMENTS
B.5 | Project Billboard/ Signboard (DPWH) |  |  |  | 2 | ea | 6832.04 | 12% | 8% | 20% | 1366.41 | 409.92 | 1776.33 |  | 8608.37 |  | 4304.19 | 3416.02 | 0
B.5 | Project Billboard/ Signboard (COA) |  |  |  | 1 | ea | 6832.04 | 12% | 8% | 20% | 1366.41 | 409.92 | 1776.33 |  | 8608.37 |  | 8608.37 | 6832.04 | 0
B.7 (2) | Occupational Safety and Health Program |  |  |  | 1 | ls | 109314.5 | 0% | 8% | 8% | 8745.16 | 5902.98 | 14648.14 |  | 123962.64 |  | 123962.64 | 109314.5 | 0
B.8(2) | Road Works Safety and Traffic Management |  |  |  | 1 | ls | 11559.6 | 0% | 8% | 8% | 924.77 | 624.22 | 1548.99 |  | 13108.59 |  | 13108.59 | 11559.6 | 0
B.9 | Mobilization/ Demobilization |  |  |  | 1 | ls | 67000 | 0% | 0% | 0% | 0 | 3350 | 3350 |  | 70350 |  | 70350 | 67000 | 0
TOTAL OF PART B | [6 empty] | 201538.18 |  |  | 20% | 12402.75 | 10697.04 | 23099.79 |  | 224637.97
PART C | EARTHWORK
100(3)a1 | Individual Removal of Trees (150-300 mm dia., Small) |  |  |  | 0 | ea | 0 | 12% | 8% | 20% | 0 | 0 | 0 |  | 0 |  | #DIV/0! | 1747.39 | 0
102(2) | Surplus Common Excavation |  |  |  | 800.05 | cum | 184315.52 | 12% | 8% | 20% | 36863.1 | 11058.93 | 47922.03 |  | 232237.55 |  | 290.28 | 230.38 | 0
104(2)a | Embankment from Borrow (Common Soil) |  |  |  | 848.88 | cum | 468581.76 | 12% | 8% | 20% | 93716.35 | 28114.91 | 121831.26 |  | 590413.02 |  | 695.52 | 552 | 0
105(1)a | Subgrade Preparation (Common Material) |  |  |  | 5778 | sqm | 122320.26 | 12% | 8% | 20% | 24464.05 | 7339.22 | 31803.27 |  | 154123.53 |  | 26.67 | 21.17 | 0
TOTAL OF PART C | [6 empty] | 775217.54 |  |  |  | 155043.5 | 46513.06 | 201556.56 |  | 976774.1
PART D | SUBBASE AND BASE COURSE
200(1) | Aggregate Subbase Course |  |  |  | 1551.95 | cum | 1035926.63 | 12% | 8% | 20% | 207185.33 | 62155.6 | 269340.93 |  | 1305267.56 |  | 841.05 | 667.5 | 0
TOTAL OF PART D | [6 empty] | 1035926.63 |  |  |  | 207185.33 | 62155.6 | 269340.93 |  | 1305267.56
PART E | SURFACE COURSES
311(1)b1 | Portland Cement Concrete Pavement (Unreinforced, 0.20m thick, 14 days) |  |  |  | 4815 | sqm | 4672524.15 | 12% | 8% | 20% | 934504.83 | 280351.45 | 1214856.28 |  | 5887380.43 |  | 1222.72 | 970.41 | 0
TOTAL OF PART E | [6 empty] | 4672524.15 |  |  |  | 934504.83 | 280351.45 | 1214856.28 |  | 5887380.43
PART F | DRAINAGE AND SLOPE PROTECTION STRUCTURES
506(1) | Stone Masonry(Slope Protection) |  |  |  | 336 | cum | 1066877.28 | 12% | 8% | 20% | 213375.46 | 64012.64 | 277388.1 |  | 1344265.38 |  | 4000.79 | 3175.23 | 0
TOTAL OF PART F | [6 empty] | 1066877.28 |  |  |  | 213375.46 | 64012.64 | 277388.1 |  | 1344265.38
GRAND TOTAL | [6 empty] | 7801031.85 |  |  |  | 1532301.48 | 466666.67 | 1998968.15 |  | 9800000 |  |  | TRUE
Note: Prices/Rates were based on CMPD 4TH Quarter CY 2022 for Materials, Memorandum dated December 29, 2022 for Labor cost and Memorandum dated May 18, 2022 for Equipment rental including Fuel & Oil/Lubricant cost as of January 4, 2023 for DPWH Regional/District Engineering Offices | [17 empty] | TRUE
Preparation and Submission: |  |  |  |  | Evaluation: |  |  |  | Approval: | [8 empty] | TRUE
TRUE
Prepared by: |  |  | Checked/Submitted by: |  | Reviewed as to Unit Cost: |  |  |  | Recommending Approval: |  |  |  |  | Approved: |  |  |  | TRUE
WINLOVE A. ESTEVES |  |  | MARK ANGELO E. SURIL |  | NICOMEDES G. NOHAY |  |  |  | BENELITO D. PASCUA |  |  |  |  | RODERICK A. ANDAL
Engineer II |  |  | Engineer II |  | Engineer III |  |  |  | Engineer III |  |  |  |  | District Engineer
Planning and Design Section |  |  | Planning and Design Section |  | Planning and Design Section |  |  |  | Concurrent OIC Assistant District Engineer

## POW-2015-01-00_
AURORA DISTRICT ENGINEERING OFFICE
FORM POW-2015-01-00
PROGRAM OF WORK/BUDGET COST
Project |  |  | : | CONSTRUCTION OF ROAD | [12 empty] | Net Length | : | (a) Road | 1.926 |  | Lane km
[18 empty] | : | (b) Bridge
[18 empty] | : | (c) Others
Project ID |  |  | :
Location |  |  | : | BRGY. L. PIMENTEL, SAN LUIS, AURORA | [12 empty] | Target Start Date | :
Station Limits |  |  | : | LOCATION 1 | 0 | TO | 741 | [9 empty] | Total Project Duration | : |  |  |  | 65 | CD
|  |  |  | LOCATION 2 | 0 | TO | 222
Appropriation |  |  | : | 10000000 | [12 empty] | No. of Pre-determined | :
Source of Fund |  |  | : | [13 empty] | Unworkable Days
DESCRIPTION OF WORKS TO BE DONE | [8 empty] | QUANTITY |  | UNIT |  | AS SUBMITTED | [5 empty] | AS EVALUATED
[13 empty] | % TOTAL |  | TOTAL DIRECT COST |  |  |  | % TOTAL |  | TOTAL DIRECT COST
Part | A: | FACILITIES FOR THE ENGINEER
B: |  | OTHER GENERAL REQUIREMENTS | [6 empty] | (PLS. SEE FORM POW-2015-01C-00)
C: |  | EARTHWORK
| D: | SUBBASE AND BASE COURSE
| E: | SURFACE COURSES
| F: | DRAINAGE AND SLOPE PROTECTION STRUCTURES
Total
EQUIPMENT: | [7 empty] | BREAKDOWN OF EXPENDITURES: | [17 empty] | 200000
DESCRIPTION | [5 empty] | REQUIRED | [5 empty] | AS SUBMITTED |  | AS EVALUATED | [6 empty] | AS SUBMITTED |  |  | AS EVALUATED
[8 empty] | 1. Labor |  |  |  | 325640.3784 |  |  |  |  | A. Total Direct Cost |  |  |  | 7801031.85
[8 empty] | 2. Materials |  |  |  | 5613700.325 |  |  |  |  | B. OCM and Profit |  |  |  | 1532301.48
[8 empty] | 3. Rental of Equipment |  |  |  | 1861691.1416 |  |  |  |  | C. Value Added Tax (5%) |  |  |  | 466666.67
[8 empty] | 4. Provisional Sum / Daywork | [8 empty] | D. Total Construction Cost |  |  |  | 9800000
(PLS. SEE FORM POW-2015-01B-00) | [7 empty] | 5. OCM and Profit |  |  |  | 1532301.48 |  |  |  |  | E. Eng'g & Administrative Overhead, |  |  | 2% | 200000 |  |  |  | 200000 |  | 9800000
[8 empty] | 6. Value Added Tax (5%) |  |  |  | 466666.67 |  |  |  |  | F. RROW Acquisition
[8 empty] | 7. EAO, |  | 2% |  | 200000 |  |  |  |  | G. Physical Reserved (Contingency)
8. RROW Acquisition
9. Physical Reserved (Contingency)
[8 empty] | 10.TOTAL ESTIMATED COST |  |  |  | 9999999.995 |  |  |  |  | H. TOTAL ESTIMATED COST |  |  |  | 10000000 |  |  |  | 10000000
Note: Prices/Rates were based on CMPD 4TH Quarter CY 2022 for Materials, Memorandum dated December 29, 2022 for Labor cost and Memorandum dated May 18, 2022 for Equipment rental including Fuel & Oil/Lubricant cost as of January 4, 2023 for DPWH Regional/District Engineering Offices | [24 empty] | 0
Preparation and Submission: | [10 empty] | Evaluation: |  |  |  |  | Approval:
Prepared by: | [6 empty] | Checked/Submitted by: |  |  |  | Reviewed as to Unit Cost: |  |  |  |  | Recommending Approval: |  |  |  | Approved: | [6 empty] | FALSE
4.174%
WINLOVE A. ESTEVES | [6 empty] | MARK ANGELO E. SURIL |  |  |  | NICOMEDES G. NOHAY |  |  |  |  | BENELITO D. PASCUA |  |  |  | RODERICK A. ANDAL
Engineer II | [6 empty] | Engineer II |  |  |  | Engineer III |  |  |  |  | Engineer III |  |  |  | District Engineer
Planning and Design Section | [6 empty] | Planning and Design Section |  |  |  | Planning and Design Section |  |  |  |  | Concurrent OIC Assistant District Engineer
[25 empty] | #DIV/0! | cost per m
[25 empty] | #DIV/0! | m
0

## POW-2015-01A-00_
CONSTRUCTION OF ROAD
BRGY. L. PIMENTEL, SAN LUIS, AURORA
FORM POW-2015-01A-00
ITEMIZED BREAKDOWN
ITEM NO. | DESCRIPTION | QUANTITY |  | UNIT | DIRECT COST |  |  |  | TOTAL UNIT COST (DIRECT+INDIRECT) |  | % DIRECT COST | TOTAL COST
[5 empty] | TOTAL |  | UNIT COST
|  | AS SUBMITTED | AS EVALUATED |  | AS SUBMITTED | AS EVALUATED | AS SUBMITTED | AS EVALUATED | AS SUBMITTED | AS EVALUATED | AS EVALUATED
PART A | FACILITIES FOR THE ENGINEER
A.1.1 (3) | Construction of Field Office for the Engineer | 1 |  | ls | 48948.07 |  | 48948.07 |  | 61674.56 |  | 0.62746 |  | FALSE
| TOTAL OF PART A |  |  |  | 48948.07 | [5 empty] | 0.62746
PART B | OTHER GENERAL REQUIREMENTS
B.5 | Project Billboard/ Signboard (DPWH) | 2 |  | ea | 6832.04 |  | 3416.02 |  | 4304.185 |  | 0.087579 |  | FALSE
B.5 | Project Billboard/ Signboard (COA) | 1 |  | ea | 6832.04 |  | 6832.04 |  | 8608.37 |  | 0.087579 |  | TRUE
B.7 (2) | Occupational Safety and Health Program | 1 |  | ls | 109314.5 |  | 109314.5 |  | 123962.64 |  | 1.4013 |  | FALSE
B.8(2) | Road Works Safety and Traffic Management | 1 |  | ls | 11559.6 |  | 11559.6 |  | 13108.59 |  | 0.14818 |  | TRUE
B.9 | Mobilization/ Demobilization | 1 |  | ls | 67000 |  | 67000 |  | 70350 |  | 0.85886 |  | TRUE
| TOTAL OF PART B |  |  |  | 201538.18 | [5 empty] | 2.5835
PART C | EARTHWORK
100(3)a1 | Individual Removal of Trees (150-300 mm dia., Small) | 0 |  | ea | 0 |  | #DIV/0! |  | #DIV/0! |  | 0 |  | #DIV/0!
102(2) | Surplus Common Excavation | 800.05 |  | cum | 184315.52 |  | 230.38 |  | 290.2788 |  | 2.3627 |  | FALSE
104(2)a | Embankment from Borrow (Common Soil) | 848.88 |  | cum | 468581.76 |  | 552 |  | 695.52 |  | 6.0067 |  | FALSE
105(1)a | Subgrade Preparation (Common Material) | 5778 |  | sqm | 122320.26 |  | 21.17 |  | 26.6742 |  | 1.568 |  | FALSE
| TOTAL OF PART C |  |  |  | 775217.54 | [5 empty] | 9.9374
PART D | SUBBASE AND BASE COURSE
200(1) | Aggregate Subbase Course | 1551.95 |  | cum | 1035926.63 |  | 667.5 |  | 841.05 |  | 13.2794 |  | FALSE
| TOTAL OF PART D |  |  |  | 1035926.63 | [5 empty] | 13.2794
PART E | SURFACE COURSES
311(1)b1 | Portland Cement Concrete Pavement (Unreinforced, 0.20m thick, 14 days) | 4815 |  | sqm | 4672524.15 |  | 970.41 |  | 1222.7166 |  | 59.8962 |  | FALSE
| TOTAL OF PART E |  |  |  | 4672524.15 | [5 empty] | 59.8962
PART F | DRAINAGE AND SLOPE PROTECTION STRUCTURES
506(1) | Stone Masonry(Slope Protection) | 336 |  | cum | 1066877.28 |  | 3175.23 |  | 4000.7898 |  | 13.6761 |  | FALSE
| TOTAL OF PART F |  |  |  | 1066877.28 | [5 empty] | 13.6761
| GRAND TOTAL |  |  |  | 7801031.85 | [5 empty] | 100
TRUE

## POW-2015-01B-00_
[8 empty] | Column1 | Column2
CONSTRUCTION OF ROAD
BRGY. L. PIMENTEL, SAN LUIS, AURORA
FORM POW-2015-01B-00
MINIMUM EQUIPMENT REQUIREMENT
No. | Equipment Description | Capacity | Number of Equipment | No. | Equipment Description | Capacity | Number of Equipment
1 | Low Bed Trailer |  | 1 | 31
2 | Backhoe (0.80 m³,138 hp) | 0.80 m³ | 1 | 32
3 | Dump Truck (12 yd³, 290 hp) | 12 yd³ | 1 | 33
4 | Chain Saw |  | 1 | 34
5 | Bulldozer, DX175 (167 hp) |  | 1 | 35
6 | Payloader, LX80-2C (1.50m³, 110 hp) | 1.50 m3/1.95 yd3 | 1 | 36
7 | Payloader, LX80-2C (1.50m³, 110 hp) - at disposal area | 1.50 m3/1.95 yd4 | 1 | 37
8 | Motorized Road Grader, G710A (140 hp) |  | 1 | 38
9 | Vibratory Roller, SD100DC (10mt, 125 hp) | 10 mt | 1 | 39
10 | Water Truck/Pump (16000 L, 360 hp) | 16000 L | 1 | 40
11 | Transit Mixer (175 hp) |  | 2 | 41
12 | Concrete Vibrator |  | 2 | 42
13 | Concrete Batch Plant |  | 1 | 43
14 | Concrete Screeder (5.50 hp) |  | 1 | 44
15 | Concrete Saw, 14" Blade ø (7.5 hp) |  | 1 | 45
16 | Bar Cutter, Single Phase |  | 1 | 46
17 | Joint Sealer |  | 1 | 47
18 | Bar Bender, Three Phase |  | 1 | 48
19 | Cargo/Service Truck (9-10mt, 270 hp) | 9-10mt | 1 | 49
20 | One Bagger Mixer (4-6 ft³/min) | 4-6 ft³/min | 1 | 50
21 | Backhoe, Wheel Mounted (0.28 m³, 50 hp) | 0.28 m³ | 1 | 51
22 |  |  |  | 52
23 |  |  |  | 53
24 |  |  |  | 54
25 |  |  |  | 55
26 |  |  |  | 56
27 |  |  |  | 57
28 |  |  |  | 58
29 |  |  |  | 59
30 |  |  |  | 60
| SUB-TOTAL |  | 23 |  | SUB-TOTAL |  | 0
[5 empty] | TOTAL |  | 23
[11 empty] | UNIT | HRS
[8 empty] | 100(3)a1 | Backhoe, SOLAR 220 LC-3 (0.80 m³,138 hp) | 1 | 1 | 0.25
[8 empty] | 100(3)a1 | Dump Truck (12 yd³, 290 hp) | 1 | 1 | 0.17 | Backhoe, SOLAR 220 LC-3 (0.80 m³,138 hp) | 1
[8 empty] | 100(3)a1 | Chain Saw | 1 | 1 | 0.17 | Dump Truck (12 yd³, 290 hp) | 1
[8 empty] | 100(3)a1 |  |  |  |  | Chain Saw | 1
[13 empty] | Bulldozer, DX175 (167 hp) | 1
[13 empty] | Payloader, LX80-2C (1.50m³, 110 hp) | 1
[13 empty] | Payloader, LX80-2C (1.50m³, 110 hp) - at disposal area | 1
[13 empty] | Motorized Road Grader, G710A (140 hp) | 1
[13 empty] | Vibratory Roller, SD100DC (10mt, 125 hp) | 1
[13 empty] | Water Truck/Pump (16000 L, 360 hp) | 1
[13 empty] | Transit Mixer (175 hp) | 2
[13 empty] | Concrete Vibrator | 2
[13 empty] | Concrete Batch Plant | 1
[8 empty] | 102(2) | Bulldozer, DX175 (167 hp) | 1 | 1 | 1 | Concrete Screeder (5.50 hp) | 1
[8 empty] | 102(2) | Payloader, LX80-2C (1.50m³, 110 hp) | 1 | 1 | 1 | Concrete Saw, 14" Blade ø (7.5 hp) | 1
[8 empty] | 102(2) | Payloader, LX80-2C (1.50m³, 110 hp) - at disposal area | 1 | 1 | 0.3 | Bar Cutter, Single Phase | 1
[8 empty] | 102(2) | Backhoe, SOLAR 220 LC-3 (0.80 m³,138 hp) |  | 1 | 1 | Joint Sealer | 1
[13 empty] | Bar Bender, Three Phase | 1
[13 empty] | Cargo/Service Truck (9-10mt, 270 hp) | 1
[13 empty] | One Bagger Mixer (4-6 ft³/min) | 1
[13 empty] | Backhoe, Wheel Mounted (0.28 m³, 50 hp) | 1
[8 empty] | 104(1)a | Bulldozer, DX175 (167 hp) |  | 1 | 0.83
[8 empty] | 104(1)a | Payloader, LX80-2C (1.50m³, 110 hp) |  | 1 | 0.83
[8 empty] | 104(1)a | Dump Truck (12 yd³, 290 hp) |  | 2 | 0.83
104(1)a
22
[9 empty] | Motorized Road Grader, G710A (140 hp) | 1 | 1 | 1
[8 empty] | 104(1)a | Vibratory Roller, SD100DC (10mt, 125 hp) | 1 | 1 | 1
[8 empty] | 104(1)a | Water Truck/Pump (16000 L, 360 hp) | 1 | 1 | 0.25
104(1)a
[8 empty] | 104(2)a | Motorized Road Grader, G710A (140 hp) |  | 1 | 1
[8 empty] | 104(2)a | Vibratory Roller, SD100DC (10mt, 125 hp) |  | 1 | 1
[8 empty] | 104(2)a | Water Truck/Pump (16000 L, 360 hp) |  | 1 | 0.25
104(2)a
[8 empty] | 105(1)a | Motorized Road Grader, G710A (140 hp) |  | 1 | 1
[8 empty] | 105(1)a | Vibratory Roller, SD100DC (10mt, 125 hp) |  | 1 | 1
[8 empty] | 105(1)a | Water Truck/Pump (16000 L, 360 hp) |  | 1 | 0.25
105(1)a
[8 empty] | 200(1) | Motorized Road Grader, G710A (140 hp) |  | 1 | 1
[8 empty] | 200(1) | Vibratory Roller, SD100DC (10mt, 125 hp) |  | 1 | 1
[8 empty] | 200(1) | Water Truck/Pump (16000 L, 360 hp) |  | 1 | 0.25
200(1)
[8 empty] | 311(1)b1 | Transit Mixer (175 hp) | 2 | 4 | 1
[8 empty] | 311(1)b1 | Concrete Vibrator | 2 | 2 | 1
[8 empty] | 311(1)b1 | Concrete Batch Plant | 1 | 1 | 1
[8 empty] | 311(1)b1 | Payloader, LX80-2C (1.50m³, 110 hp) |  | 1 | 1
[8 empty] | 311(1)b1 | Concrete Screeder (5.50 hp) | 1 | 1 | 1
[8 empty] | 311(1)b1 | Water Truck/Pump (16000 L, 360 hp) |  | 1 | 1
[8 empty] | 311(1)b1 | Concrete Saw, 14" Blade ø (7.5 hp) | 1 | 1 | 1
[8 empty] | 311(1)b1 | Bar Cutter, Single Phase | 1 | 1 | 0.1
[8 empty] | 311(1)b1 | Joint Sealer | 1 | 1 | 0.1
311(1)b1
[8 empty] | 404(1)a | Bar Cutter, Single Phase |  | 1 | 0.5
[8 empty] | 404(1)a | Bar Bender, Three Phase | 1 | 1 | 0.5
[8 empty] | 404(1)a | Cargo/Service Truck (9-10mt, 270 hp) | 1 | 1 | 0.15
404(1)a
[8 empty] | 405(1)a3 | One Bagger Mixer (4-6 ft³/min) | 1 | 1 | 1
[8 empty] | 405(1)a3 | Concrete Vibrator |  | 1 | 1
[8 empty] | 405(1)a3 | Water Truck/Pump (16000 L, 360 hp) |  | 1 | 0.1
405(1)a3
21

## POW-2015-01C-00_
CONSTRUCTION OF ROAD
BRGY. L. PIMENTEL, SAN LUIS, AURORA
FORM POW-2015-01C-00
DETAILED BREAKDOWN OF COMPONENT COST FOR EACH ITEM | [19 empty] | ROADWAY | = | 8169422.09
ITEM NO. | DESCRIPTION |  | % | QTY. | UNIT | DIRECT COST | [6 empty] | TOTAL MARK-UP |  | 5% VAT | TOTAL COST | ADJUSTED UNIT COST |  |  | DRAINAGE | =
[6 empty] | MATERIAL UNIT COST | MATERIAL | LABOR UNIT COST | LABOR | EQUIPMENT UNIT COST | EQUIPMENT | TOTAL | % | VALUE | [5 empty] | STONE MASONRY | = | 1344265.38
PART A | FACILITIES FOR THE ENGINEER | [20 empty] | 9513687.47
A.1.1 (3) | Construction of Field Office for the Engineer | AS EVALUATED |  |  | ls | [13 empty] | 48948.07 |  |  | -286312.53
|  | AS SUBMITTED | 0.62746 | 1 |  | 45446.47 | 45446.47 | 3501.6 | 3501.6 | 0 | 0 | 48948.07 | 20% | 9789.61 | 2936.88 | 61674.56 | 61674.56 |  | #REF! |  |  | FALSE
| TOTAL OF PART A | AS EVALUATED | [16 empty] | 0
|  | AS SUBMITTED | 0.62746 |  |  |  | 45446.47 |  | 3501.6 |  | 0 | 48948.07 |  | 9789.61 | 2936.88 | 61674.56 |  |  | 0
PART B | OTHER GENERAL REQUIREMENTS | [17 empty] | 0
B.5 | Project Billboard/ Signboard (DPWH) | AS EVALUATED |  |  | ea | [13 empty] | 3416.02
|  | AS SUBMITTED | 0.087579 | 2 |  | 2934.55 | 5869.1 | 437.7 | 875.4 | 43.77 | 87.54 | 6832.04 | 20% | 1366.41 | 409.92 | 8608.37 | 4304.185 |  | 0
B.5 | Project Billboard/ Signboard (COA) | AS EVALUATED |  |  | ea | [13 empty] | 6832.04
|  | AS SUBMITTED | 0.087579 | 1 |  | 5869.1 | 5869.1 | 875.4 | 875.4 | 87.54 | 87.54 | 6832.04 | 20% | 1366.41 | 409.92 | 8608.37 | 8608.37 |  | 0
B.7 (2) | Occupational Safety and Health Program | AS EVALUATED |  |  | ls | [13 empty] | 109314.5
|  | AS SUBMITTED | 1.4013 | 1 |  | 29750.9 | 29750.9 | 71597.2 | 71597.2 | 7966.4 | 7966.4 | 109314.5 | 8% | 8745.16 | 5902.98 | 123962.64 | 123962.64 |  | #REF!
B.8(2) | Road Works Safety and Traffic Management | AS EVALUATED |  |  | ls | [13 empty] | 11559.6
|  | AS SUBMITTED | 0.14818 | 1 |  | 11559.6 | 11559.6 | 0 | 0 | 0 | 0 | 11559.6 | 8% | 924.77 | 624.22 | 13108.59 | 13108.59 |  | #REF!
B.9 | Mobilization/ Demobilization | AS EVALUATED |  |  | ls | [13 empty] | 67000
|  | AS SUBMITTED | 0.85886 | 1 |  | 0 | 0 | 0 | 0 | 67000 | 67000 | 67000 | 0% | 0 | 3350 | 70350 | 70350 |  | 0
| TOTAL OF PART B | AS EVALUATED | [16 empty] | 0
|  | AS SUBMITTED | 2.5835 |  |  |  | 53048.7 |  | 73348 |  | 75141.48 | 201538.18 |  | 12402.75 | 10697.04 | 224637.97 |  | 4787681.015 | #REF!
PART C | EARTHWORK | [17 empty] | #REF!
100(3)a1 | Individual Removal of Trees (150-300 mm dia., Small) | AS EVALUATED |  |  | ea | [13 empty] | 1747.39
|  | AS SUBMITTED | 0 | 0 |  | 480 | 0 | 103.69 | 0 | 1163.7 | 0 | 0 | 20% | 0 | 0 | 0 | #DIV/0! |  | #REF!
102(2) | Surplus Common Excavation | AS EVALUATED |  |  | cum | [13 empty] | 230.38
|  | AS SUBMITTED | 2.3627 | 800.05 |  | 0 | 0 | 2.93 | 2344.15 | 227.45 | 181971.37 | 184315.52 | 20% | 36863.1 | 11058.93 | 232237.55 | 290.2788 |  | #REF!
104(2)a | Embankment from Borrow (Common Soil) | AS EVALUATED |  |  | cum | [13 empty] | 552
|  | AS SUBMITTED | 6.0067 | 848.88 |  | 425 | 360774 | 4.68 | 3972.7584 | 122.32 | 103835.0016 | 468581.76 | 20% | 93716.35 | 28114.91 | 590413.02 | 695.52 |  | #REF!
105(1)a | Subgrade Preparation (Common Material) | AS EVALUATED |  |  | sqm | [13 empty] | 21.17
|  | AS SUBMITTED | 1.568 | 5778 |  | 0 | 0 | 0.78 | 4506.84 | 20.39 | 117813.42 | 122320.26 | 20% | 24464.05 | 7339.22 | 154123.53 | 26.6742 |  | #REF!
| TOTAL OF PART C | AS EVALUATED | [16 empty] | 0
|  | AS SUBMITTED | 9.9374 |  |  |  | 360774 |  | 10823.7484 |  | 403619.7916 | 775217.54 |  | 155043.5 | 46513.06 | 976774.1 |  |  | #REF!
PART D | SUBBASE AND BASE COURSE | [17 empty] | 0
200(1) | Aggregate Subbase Course | AS EVALUATED |  |  | cum | [13 empty] | 667.5
|  | AS SUBMITTED | 13.2794 | 1551.95 |  | 540.5 | 838828.975 | 4.68 | 7263.13 | 122.32 | 189834.52 | 1035926.63 | 20% | 207185.33 | 62155.6 | 1305267.56 | 841.05 |  | #REF!
| TOTAL OF PART D | AS EVALUATED | [16 empty] | 0
|  | AS SUBMITTED | 13.2794 |  |  |  | 838828.975 |  | 7263.13 |  | 189834.52 | 1035926.63 |  | 207185.33 | 62155.6 | 1305267.56 |  |  | #REF!
PART E | SURFACE COURSES | [17 empty] | 0
311(1)b1 | Portland Cement Concrete Pavement (Unreinforced, 0.20m thick, 14 days) | AS EVALUATED |  |  | sqm | [13 empty] | 970.41
|  | AS SUBMITTED | 59.8962 | 4815 |  | 732.78 | 3528335.7 | 14.56 | 70106.4 | 223.07 | 1074082.05 | 4672524.15 | 20% | 934504.83 | 280351.45 | 5887380.43 | 1222.7166 |  | #REF!
| TOTAL OF PART E | AS EVALUATED | [16 empty] | 223.07
|  | AS SUBMITTED | 59.8962 |  |  |  | 3528335.7 |  | 70106.4 | 223.07 | 1074082.05 | 4672524.15 |  | 934504.83 | 280351.45 | 5887380.43 |  |  | 0
PART F | DRAINAGE AND SLOPE PROTECTION STRUCTURES | [17 empty] | 0
506(1) | Stone Masonry(Slope Protection) | AS EVALUATED |  |  | cum | [13 empty] | 3175.23
|  | AS SUBMITTED | 13.6761 | 336 |  | 2343.055 | 787266.48 | 477.9688 | 160597.5 | 354.2062 | 119013.3 | 1066877.28 | 20% | 213375.46 | 64012.64 | 1344265.38 | 4000.7898 |  | #REF!
| TOTAL OF PART F | AS EVALUATED | [16 empty] | 354.2062
|  | AS SUBMITTED | 13.6761 |  |  |  | 787266.48 |  | 160597.5 | 354.2062 | 119013.3 | 1066877.28 |  | 213375.46 | 64012.64 | 1344265.38 |  |  | 0
| GRAND TOTAL | AS EVALUATED | [16 empty] | 0
|  | AS SUBMITTED | 100 |  |  |  | 5613700.325 |  | 325640.3784 |  | 1861691.1416 | 7801031.85 |  | 1532301.48 | 466666.67 | 9800000 |  |  | 0
9999999.995

## BACKUP
Project : | CONSTRUCTION OF ROAD
Location : | BRGY. L. PIMENTEL, SAN LUIS, AURORA |  |  |  | Length | Lane | Net Length
Station Limits: : | LOCATION 1 | 0 | TO | 741 | 741 | 2 | 1482
| LOCATION 2 | 0 | TO | 222 | 222 | 2 | 444
[5 empty] | 963 |  | 1926
Total Length : | 0.963 | km
Net Length : | 1.926 | Lane km
1 | 2 | 3 | 4 | 5 | 6
BACKUP COMPUTATION
Item | Individual Removal of Trees (150-300 mm dia., Small) | [8 empty] | NOTE:
100(3)a1 | Total Quantity | = | 0 | ea | [5 empty] | gagamitin lang ang item 104(2)a (embankment borrow) kapag mas malaki yung excavation (104(1)a) sa embankment
Item | Surplus Common Excavation | [8 empty] | B_7 at B_9 lang ang ginagalaw halos sa dupa. at di pwedeng magexceed ng 1% ang b_9
102(2) | Total Volume | = | 800.05 | cum
| Cut Volume | = | 800.05 | cum | [5 empty] | kapag inedit yung 7 at 9 need palitan lahat ng abc at pow
| Deduction | = | 848.88 | cum | *from 104(1)a
napapalitan ang gasolina
Item | Embankment from Borrow (Common Soil)
104(2)a | Total Volume | = | 848.88 | cum | [5 empty] | icheck yung HEADER NG DUPA at mga title syempre
Item | Subgrade Preparation (Common Material) | [8 empty] | tingnan mga naka link. may nakanote din sa gilid ng mga ABC
105(1)a | Total Area | = | 5778 | sqm
check mo yung mga nakahide pati dito sa backup
Item | Aggregate Subbase Course
200(1) | Total Volume | = | 1551.95 | cum
Item | Portland Cement Concrete Pavement (Unreinforced, 0.20m thick, 14 days)
311(1)b1 | Total Area | = | 4815 | sqm
| Area 1 | = | 4815 | sqm | *for Roadway
Item | Stone Masonry(Slope Protection)
506(1) | Total Volume | = | 336 | cum
WINLOVE A. ESTEVES |  |  | MARK ANGELO E. SURIL
Engineer II |  |  | Engineer II
Planning and Design Section |  |  | Planning and Design Section
QUANTITY SHEET
STATION | DISTANCE | ITEM | 102(2) | ITEM | 104(2)a | ITEM | #REF! | ITEM | 105(1)a | ITEM | 200(1) | ITEM | 311(1)b1 | REMARKS
|  | Area (sqm) | Volume (cum) | Area (sqm) | Volume (cum) | Area (sqm) | Volume (cum) | Width (m) | Area (sqm) | Area (sqm) | Volume (cum) | Width (m) | Area (sqm)
LOCATION 1
0 |  | 3.44 |  | 0 |  |  |  | 6 |  | 1.65 |  | 5
20 | 20 | 0.63 | 40.7 | 0 | 0 |  |  | 6 | 120 | 1.65 | 33 | 5 | 100 |  | 0
40 | 20 | 1.17 | 18 | 0 | 0 |  |  | 6 | 120 | 1.65 | 33 | 5 | 100 |  | 0
60 | 20 | 1.23 | 24 | 0 | 0 |  |  | 6 | 120 | 1.65 | 33 | 5 | 100 |  | 0
80 | 20 | 0.6 | 18.3 | 0 | 0 |  |  | 6 | 120 | 1.65 | 33 | 5 | 100 |  | 0
100 | 20 | 0.27 | 8.7 | 0 | 0 |  |  | 6 | 120 | 1.65 | 33 | 5 | 100 |  | 0
120 | 20 | 0.37 | 6.4 | 0 | 0 |  |  | 6 | 120 | 1.65 | 33 | 5 | 100 |  | 0
140 | 20 | 0.21 | 5.8 | 0 | 0 |  |  | 6 | 120 | 1.65 | 33 | 5 | 100 |  | 0
160 | 20 | 0 | 2.1 | 0.76 | 7.6 |  |  | 6 | 120 | 1.65 | 33 | 5 | 100 |  | 0
180 | 20 | 0 | 0 | 0.56 | 13.2 |  |  | 6 | 120 | 1.65 | 33 | 5 | 100 |  | 0
200 | 20 | 0.08 | 0.8 | 0.03 | 5.9 |  |  | 6 | 120 | 1.65 | 33 | 5 | 100 |  | 0
220 | 20 | 1.42 | 15 | 0 | 0.3 |  |  | 6 | 120 | 1.65 | 33 | 5 | 100 |  | 0
240 | 20 | 0.27 | 16.9 | 0.28 | 2.8 |  |  | 6 | 120 | 1.65 | 33 | 5 | 100 |  | 0
260 | 20 | 0.16 | 4.3 | 0.19 | 4.7 |  |  | 6 | 120 | 1.65 | 33 | 5 | 100 |  | 0
280 | 20 | 0 | 1.6 | 0.61 | 8 |  |  | 6 | 120 | 1.65 | 33 | 5 | 100 |  | 0
300 | 20 | 0.44 | 4.4 | 0 | 6.1 |  |  | 6 | 120 | 1.65 | 33 | 5 | 100 |  | 0
320 | 20 | 0.19 | 6.3 | 0 | 0 |  |  | 6 | 120 | 1.65 | 33 | 5 | 100 |  | 0 | 3
340 | 20 | 0 | 1.9 | 0.71 | 7.1 |  |  | 6 | 120 | 1.65 | 33 | 5 | 100 |  | 0
360 | 20 | 0 | 0 | 1.6 | 23.1 |  |  | 6 | 120 | 1.65 | 33 | 5 | 100 |  | 0
380 | 20 | 0 | 0 | 1.35 | 29.5 |  |  | 6 | 120 | 1.65 | 33 | 5 | 100 |  | 0
400 | 20 | 0 | 0 | 0.75 | 21 |  |  | 6 | 120 | 1.65 | 33 | 5 | 100 |  | 0
420 | 20 | 0.52 | 5.2 | 0 | 7.5 |  |  | 6 | 120 | 1.65 | 33 | 5 | 100 |  | 0
440 | 20 | 1.74 | 22.6 | 0 | 0 |  |  | 6 | 120 | 1.65 | 33 | 5 | 100 |  | 0
460 | 20 | 3.96 | 57 | 0 | 0 |  |  | 6 | 120 | 1.65 | 33 | 5 | 100 |  | 0
480 | 20 | 5.72 | 96.8 | 0 | 0 |  |  | 6 | 120 | 1.65 | 33 | 5 | 100 |  | 0
500 | 20 | 5.45 | 111.7 | 0 | 0 |  |  | 6 | 120 | 1.65 | 33 | 5 | 100 |  | 0
520 | 20 | 5.68 | 111.3 | 0 | 0 |  |  | 6 | 120 | 1.65 | 33 | 5 | 100 |  | 0
540 | 20 | 2.68 | 83.6 | 0 | 0 |  |  | 6 | 120 | 1.65 | 33 | 5 | 100 |  | 0
560 | 20 | 1.57 | 42.5 | 0 | 0 |  |  | 6 | 120 | 1.65 | 33 | 5 | 100 |  | 0
580 | 20 | 0 | 15.7 | 0.41 | 4.1 |  |  | 6 | 120 | 1.65 | 33 | 5 | 100 |  | 0
600 | 20 | 0.02 | 0.2 | 0.34 | 7.5 |  |  | 6 | 120 | 1.65 | 33 | 5 | 100 |  | 0
620 | 20 | 0 | 0.2 | 0.37 | 7.1 |  |  | 6 | 120 | 1.65 | 33 | 5 | 100 |  | 0
640 | 20 | 0.45 | 4.5 | 0 | 3.7 |  |  | 6 | 120 | 1.65 | 33 | 5 | 100 |  | 0
660 | 20 | 0.1 | 5.5 | 0.08 | 0.8 |  |  | 6 | 120 | 1.65 | 33 | 5 | 100 |  | 0
680 | 20 | 0 | 1 | 0.6 | 6.8 |  |  | 6 | 120 | 1.65 | 33 | 5 | 100 |  | 0
700 | 20 | 0 | 0 | 0.34 | 9.4 |  |  | 6 | 120 | 1.65 | 33 | 5 | 100 |  | 0
720 | 20 | 0.48 | 4.8 | 0 | 3.4 |  |  | 6 | 120 | 1.65 | 33 | 5 | 100 |  | 0
740 | 20 | 0.6 | 10.8 | 0.48 | 4.8 |  |  | 6 | 120 | 1.65 | 33 | 5 | 100 |  | 0
741 | 1 | 0.6 | 0.6 | 0.48 | 0.48 |  |  | 6 | 6 | 1.65 | 1.65 | 5 | 5 |  | 0
LOCATION 2 | [9 empty] | 1.65 |  |  |  |  | 0
0 |  | 3.42 |  | 0 |  |  |  | 6 |  | 1.65 |  | 5 |  |  | 0
20 | 20 | 0 | 34.2 | 6.84 | 68.4 |  |  | 6 | 120 | 1.36 | 30.1 | 5 | 100 |  | 0
40 | 20 | 0 | 0 | 6.85 | 136.9 |  |  | 6 | 120 | 1.36 | 27.2 | 5 | 100 |  | 0
60 | 20 | 0 | 0 | 5.32 | 121.7 |  |  | 6 | 120 | 1.36 | 27.2 | 5 | 100 |  | 0
80 | 20 | 0 | 0 | 3.88 | 92 |  |  | 6 | 120 | 1.36 | 27.2 | 5 | 100 |  | 0
100 | 20 | 0 | 0 | 1.99 | 58.7 |  |  | 6 | 120 | 1.51 | 28.7 | 5 | 100 |  | 0
120 | 20 | 0 | 0 | 0.91 | 29 |  |  | 6 | 120 | 1.65 | 31.6 | 5 | 100 |  | 0
140 | 20 | 0 | 0 | 1.4 | 23.1 |  |  | 6 | 120 | 1.65 | 33 | 5 | 100 |  | 0
160 | 20 | 0 | 0 | 2.34 | 37.4 |  |  | 6 | 120 | 1.38 | 30.3 | 5 | 100 |  | 0
180 | 20 | 0 | 0 | 2.83 | 51.7 |  |  | 6 | 120 | 1.37 | 27.5 | 5 | 100 |  | 0
200 | 20 | 0 | 0 | 0.84 | 36.7 |  |  | 6 | 120 | 1.65 | 30.2 | 5 | 100 |  | 0
220 | 20 | 1.47 | 14.7 | 0 | 8.4 |  |  | 6 | 120 | 1.65 | 33 | 5 | 100 |  | 0
222 | 2 | 0.48 | 1.95 | 0 | 0 |  |  | 6 | 12 | 1.65 | 3.3 | 5 | 10 |  | 0
260 | 0 | 0 | 0 | 0.37 | 0 |  |  | 6 | 0 | 1.65 | 0 | 5 | 0 |  | 0
280 | 0 | 1.23 | 0 | 0 | 0 |  |  | 6 | 0 | 1.65 | 0 | 5 | 0 |  | 0
300 | 0 | 1.96 | 0 | 0 | 0 |  |  | 6 | 0 | 1.65 | 0 | 5 | 0 |  | 0
320 | 0 | 0 | 0 | 3.42 | 0 |  |  | 6 | 0 | 1.65 | 0 | 5 | 0 |  | 0
340 | 0 | 0 | 0 | 1.71 | 0 |  |  | 6 | 0 | 1.65 | 0 | 5 | 0 |  | 0
351.35 | 0 | 1.28 | 0 | 0 | 0 |  |  | 6 | 0 | 1.65 | 0 | 5 | 0 |  | 0
0
TOTAL | 963 |  | 800.05 |  | 848.88 |  |  |  | 5778 |  | 1551.95 |  | 4815 |  | 0 |  | 0
Prepared by: |  |  |  | Checked/Submitted by:
WINLOVE A. ESTEVES |  |  |  | MARK ANGELO E. SURIL
Engineer II |  |  |  | Engineer II
Planning and Design Section |  |  |  | Planning and Design Section
0
311(1)b1 | Portland Cement Concrete Pavement (Unreinforced, 0.20m thick, 14 days)
STATION LIMIT |  |  | LENGTH (m) | WIDTH (m) | THICKNESS (m) | AREA (sqm) | REMARKS
LOCATION 1
0 | to | 741 | 741 | 5 | 0.2 | 3705
LOCATION 2
0 | to | 222 | 222 | 5 | 0.2 | 1110
SUBTOTAL |  |  | 963 |  |  | 4815
ITEM | 506(1) | Stone Masonry(Slope Protection)
STATION |  |  | Length | Top | Base | Height | Area | Volume | REMARKS
|  |  | (m) | (m) | (m) | (m) | (sqm) | (cum)
LOCATION 2
10 | to | 30 | 20 | 0.5 | 1.15 | 2.3 | 1.8975 | 37.95 | LEFT SIDE
30 | to | 50 | 20 | 0.5 | 1.1 | 2.2 | 1.76 | 35.2 | LEFT SIDE
50 | to | 70 | 20 | 0.5 | 1 | 2 | 1.5 | 30 | LEFT SIDE
70 | to | 90 | 20 | 0.5 | 0.75 | 1.5 | 0.9375 | 18.75 | LEFT SIDE
90 | to | 110 | 20 | 0.5 | 0.7 | 1.4 | 0.84 | 16.8 | LEFT SIDE
150 | to | 170 | 20 | 0.5 | 0.75 | 1.5 | 0.9375 | 18.75 | LEFT SIDE
170 | to | 190 | 20 | 0.5 | 0.8 | 1.6 | 1.04 | 20.8 | LEFT SIDE
310 | to | 330 | 20 | 0.5 | 0.85 | 1.7 | 1.1475 | 22.95 | LEFT SIDE
10 | to | 50 | 40 | 0.5 | 1.15 | 2.3 | 1.8975 | 75.9 | RIGHT SIDE
50 | to | 70 | 20 | 0.5 | 0.95 | 1.9 | 1.3775 | 27.55 | RIGHT SIDE
70 | to | 90 | 20 | 0.5 | 0.75 | 1.5 | 0.9375 | 18.75 | RIGHT SIDE
150 | to | 170 | 20 | 0.5 | 0.7 | 1.4 | 0.84 | 16.8 | RIGHT SIDE
170 | to | 190 | 20 | 0.5 | 0.75 | 1.5 | 0.9375 | 18.75 | RIGHT SIDE
310 | to | 330 | 20 | 0.5 | 0.8 | 1.6 | 1.04 | 20.8 | RIGHT SIDE
TOTAL | [7 empty] | 336

## SOQ
Project Title : | CONSTRUCTION OF ROAD
Location / Section: | BRGY. L. PIMENTEL, SAN LUIS, AURORA
Station Limits : | LOCATION 1 | 0 | TO | 741
| LOCATION 2 | 0 | TO | 222
Total Length : | 0.963 | km
Net Length : | 1.926 | Lane km
|  |  |  | TOTAL CALENDAR DAYS | = | 65 | CD
S U M M A R Y O F Q U A N T I T I E S
ITEM NO. | DESCRIPTION |  |  |  | UNIT | QUANTITY | REMARKS
PART A | FACILITIES FOR THE ENGINEER
A.1.1 (3) | Construction of Field Office for the Engineer |  |  |  | ls | 1 | Construction of 3.0x3.0m Field Office with CR
PART B | OTHER GENERAL REQUIREMENTS
B.5 | Project Billboard/ Signboard (DPWH) |  |  |  | ea | 2 | To be installed and maintained
B.5 | Project Billboard/ Signboard (COA) |  |  |  | ea | 1 | To be installed and maintained
B.7 (2) | Occupational Safety and Health Program |  |  |  | ls | 1 | To be provided and maintained (Considering Safety Measures for COVID-19)
B.8(2) | Road Works Safety and Traffic Management |  |  |  | ls | 1 | To be provided and maintained
B.9 | Mobilization/ Demobilization |  |  |  | ls | 1 | For Equipments
PART C | EARTHWORK
100(3)a1 | Individual Removal of Trees (150-300 mm dia., Small) |  |  |  | ea | 0 | Removal of Coconut Tree
102(2) | Surplus Common Excavation |  |  |  | cum | 800.05 | To be disposed
104(2)a | Embankment from Borrow (Common Soil) |  |  |  | cum | 848.88 | Embankment for Roadway
105(1)a | Subgrade Preparation (Common Material) |  |  |  | sqm | 5778 | For Roadbed
PART D | SUBBASE AND BASE COURSE
200(1) | Aggregate Subbase Course |  |  |  | cum | 1551.95 | Compacted Volume, 200mm thk
PART E | SURFACE COURSES
311(1)b1 | Portland Cement Concrete Pavement (Unreinforced, 0.20m thick, 14 days) |  |  |  | sqm | 4815 | For Roadway (width = 5m), 200mm thk
PART F | DRAINAGE AND SLOPE PROTECTION STRUCTURES
506(1) | Stone Masonry(Slope Protection) |  |  |  | cum | 336 | For Roadway Slope Protection
PREPARED BY:
WINLOVE A. ESTEVES | [5 empty] | MARK ANGELO E. SURIL
Engineer II | [5 empty] | Engineer II
`

## cd
TOTAL DURATION OF PROJECT | [7 empty] | TOTAL DURATION OF PROJECT
(DO 44 S. 2012 & DO 71 S. 2013) | [7 empty] | (DO 44 S. 2012)
Project: | CONSTRUCTION OF ROAD | [6 empty] | Project: | :
Location: | BRGY. L. PIMENTEL, SAN LUIS, AURORA | [6 empty] | Location: | :
A. | ROADWAY | [6 empty] | A. | Roadways
| AMOUNT | [7 empty] | AMOUNT
Php | 5000000 | = | 27 | CD |  |  |  | Php | 5000000 | = | 28 | CD
Php | 8169422.09 | = | 39 | CD | (BY INTERPOLATION) |  |  | Php | #REF! | = | #REF! | CD | (BY INTERPOLATION)
Php | 20000000 | = | 80 | CD |  |  |  | Php |  | =
B. | DRAINAGE | [6 empty] | A. | Roadways
| AMOUNT | [7 empty] | AMOUNT
Php | 0 | = | 0 | CD |  |  |  | Php | 5000000 | = | 28 | CD
Php |  | = | 0 | CD | (BY INTERPOLATION) |  |  | Php | #REF! | = | #REF! | CD | (BY INTERPOLATION)
Php | 5000000 | = | 63 | CD |  |  |  | Php |  | =
C. | STONE MASONRY | [6 empty] | A. | Roadways
| AMOUNT | [7 empty] | AMOUNT
Php | 0 | = | 0 | CD |  |  |  | Php | 5000000 | = | 28 | CD
Php | 1344265.38 | = | 16 | CD | (BY INTERPOLATION) |  |  | Php | #REF! | = | #REF! | CD | (BY INTERPOLATION)
Php | 5000000 | = | 59 | CD |  |  |  | Php |  | =
| A + B + C | = | 55 | CD |  |  |  | C. | Drainage / Slope Protection
|  | OR | 1.84 | MONTHS |  |  |  |  | AMOUNT |  | Stone Masonry
[8 empty] | Php | 5000000 | = | 107 | CD
PREDETERMINED UNWORKABLE DAYS |  | = | 5 |  | X | 1.84 |  | Php | 5940697.4 | = | 128 | CD | (BY INTERPOLATION)
|  | = | 10 | CD |  |  |  | Php |  | =
TOTAL DURATION =( A+B+C )+ PREDETERMINED UNWORKABLE DAYS | [7 empty] | C. | Drainage / Slope Protection
[9 empty] | AMOUNT |  | Stone Masonry
| TOTAL CALENDAR DAYS | = | 65 | CD |  |  |  | Php | 5000000 | = | 107 | CD
|  |  | 2.2 | mo |  |  |  | Php | 5940697.4 | = | 128 | CD | (BY INTERPOLATION)
|  |  | 2.1667 |  |  |  | #REF! | Php |  | =
[7 empty] | Err:520 |  | MOB/DEMOB | = | 10 | CD (UP TO 5M.)
Prepared by: |  |  |  | Checked/Submitted by:
[9 empty] | A + B + C + MOB./DEMOB. | = | #REF! | CD
[10 empty] | OR | #REF! | MONTHS
WINLOVE A. ESTEVES |  |  |  | MARK ANGELO E. SURIL |  |  |  | PREDETERMINED UNWORKABLE DAYS |  | = | 5 |  | X | #REF!
Engineer II |  |  |  | Engineer II | [5 empty] | = | #REF! | CD
Planning and Design Section |  |  |  | Planning and Design Section
TOTAL DURATION =( A + B + C + MOB/DEMOB )+ PREDETERMINED UNWORKABLE DAYS
[9 empty] | TOTAL DURATION | = | #REF! | CD
[11 empty] | #REF! | #REF!
0

## FO
Construction of Field Office for the Engineer
BACKUP COMPUTATION
Concrete |  |  |  |  | MATERIALS
Footing | = | 0.288 |  |  | Cement | = | 20.7 | bags
Column | = | 0.256 |  |  | Sand | = | 1.3 | cum
Slab | = | 0.9 |  |  | Gravel | = | 1.44 | cum
|  | 1.444 | cum |  | 100 mm thk CHB | = | 187 | pcs
Cement | = | 13.1404 | bags |  | 1/4" Marine Plywood | = | 11 | pcs
Sand | = | 0.722 | cum |  | Reinforcing Steel Bar, Grade 40 | = | 112.45 | kg
Gravel | = | 1.444 | cum |  | Corrugated Roofing | = | 21 | sqm
[5 empty] | Coco Lumber | = | 291 | bdft
CHB wall |  |  |  |  | Plain G.I. Ridge Roll | = | 4.2 | m
Area | = | 14.4 | sqm
100 mm thk CHB | = | 187.2 | pcs
Cement | = | 7.56 | bags
Sand | = | 0.576 | cum
Plywood Wall
Area | = | 20.4 | sqm
1/4" Marine Plywood | = | 7.0833 | pcs
RSB
Footing
10mm | = | 19.2 | m
Column
12mm | = | 28.8 | m
10mm | = | 28.8 | m
Slab
10mm | = | 36 | m
CHB Wall
10mm | = | 56.8 | m
10mm | = | 86.8736 | kg
12mm | = | 25.5744 | kg
Reinforcing Steel Bar, Grade 40 | = | 112.448 | kg
Roof
Corrugated Roofing | = | 21 | sqm
Lumber
4" x 4" coco lumber | = | 22.3097 | ft | post
2" x 2" coco lumber | = | 118.1102 | ft | ceiling joist
2" x 2" coco lumber | = | 23.622 | ft | hanger
2" x 4" coco lumber | = | 39.3701 | ft | bot chord
2" x 5" coco lumber | = | 2.6247 | ft | king post
2" x 5" coco lumber | = | 13.1234 | ft | collar plate
2" x 5" coco lumber | = | 32.8084 | ft | top chord
2" x 3" coco lumber | = | 110.2362 | ft | purlins
2" x 5" coco lumber | = | 9.8425 | ft
2" x 2" coco lumber | = | 251.9685 | ft | wall
2" x 2" coco lumber | = | 131.2336 | bdft
2" x 3" coco lumber | = | 55.1181 | bdft
2" x 4" coco lumber | = | 26.2467 | bdft
2" x 5" coco lumber | = | 48.6658 | bdft
4" x 4" coco lumber | = | 29.7463 | bdft
Coco Lumber | = | 291.0105 | bdft
1/4" Marine Plywood | = | 3.125 | pcs
Plain G.I. Ridge Roll | = | 4.2 | m

## A_1_1_(3)
FORM-POW-2015-01D-00
Item No. / Description |  |  | : | A.1.1 (3) | Construction of Field Office for the Engineer
Unit of Measurement |  |  | : | ls
Output per hour - As Submitted |  |  | : | 1
Output per hour - As Evaluated |  |  | :
A.1 | Designation |  |  | No. of Person/s | No. of Hour/s | Hourly Rate | Amount (PhP)
Labor
| a. | Construction Foreman |  | 1 | 8 | 110.65 | 885.2
| b. | Skilled Laborer |  | 1 | 8 | 80.05 | 640.4
| c. | Unskilled Laborer |  | 4 | 8 | 61.75 | 1976
| Sub - Total for A.1 - As Submitted | [5 empty] | 3501.6 | 3501.6
A.2 | Labor
| Sub - Total for A.2 - As Evaluated | [5 empty] | 0
B.1 | Name and Capacity |  |  | No. of Unit/s | No. of Month/s | Monthly Rate | Amount (Php)
Equipment
| Sub - Total for B.1 - As Submitted | [5 empty] | 0 | 0
B.2 | Equipment
| Sub - Total for B.2 - As Evaluated | [5 empty] | 0
C.1 | Total (A.1 + B.1) - As Submitted | [5 empty] | 3501.6
C.2 | Total (A.2+ B.2) - As Evaluated
D.1 | Output per hour - As Submitted | [5 empty] | 1
D.2 | Output per hour - As Evaluated
E.1 | Direct Unit Cost (C.1 ÷ D.1) - As Submitted | [5 empty] | 3501.6
E.2 | Direct Unit Cost (C.1 ÷ D.1) - As Evaluated
F.1 | Name and Specification |  |  | Unit | Quantity | Unit Cost | Amount (PhP)
Materials
| a. | Cement |  | bags | 20.7 | 260 | 5382
| b. | Sand |  | cum | 1.3 | 400 | 520
| c. | Gravel |  | cum | 1.44 | 570 | 820.8
| d. | 100 mm thk CHB |  | pcs | 187 | 18 | 3366
| e. | 1/4" Marine Plywood |  | pcs | 11 | 420 | 4620
| f. | Reinforcing Steel Bar, Grade 40 |  | kg | 112.45 | 41 | 4610.45
| g. | Corrugated Roofing |  | sqm | 21 | 375 | 7875
| h. | Coco Lumber |  | bdft | 291 | 21 | 6111
| i. | Plain G.I. Ridge Roll |  | m | 4.2 | 110 | 462
| j. | G.I. Tie Wire #16 (2% of RSB) |  | kg | 2.25 | 85 | 191.25
| k. | Assorted CWN (1kg./100 bd.ft. of Lumber) |  | kg | 2.91 | 77.5 | 225.525
| l. | Water Closet |  | set | 1 | 8980 | 8980
| m. | Faucet |  | set | 1 | 180 | 180
| n. | Plastic Blue Drum (Septic tank) |  | pcs | 2 | 800 | 1600
Hauling Cost
| a. | Cement |  | bags | 20.7 | 2 | 41.4
| f. | Reinforcing Steel Bar, Grade 40 |  | kg | 112.45 | 4.1 | 461.045
| Sub - Total for F.1 - As Submitted | [5 empty] | 45446.47 | 45446.47 |  | 22723.235 | 68169.705
F.2 | Materials | [8 empty] | 0.33333
| Sub - Total for F.2 - As Evaluated | [5 empty] | 0
G.1 | Direct Unit Cost (E.1 + F.1) - As Submitted | [5 empty] | 48948.07 | 48948.07 | 0
G.2 | Direct Unit Cost (E.2 + F.2) - As Evaluated
H.1 | Overhead, Contingencies & Miscellaneous (OCM) - As Submitted |  |  |  |  | 12% | 5873.7684
H.2 | Overhead, Contingencies & Miscellaneous (OCM) - As Evaluated
I.1 | Contractor's Profit (CP) - As Submitted |  |  |  |  | 8% | 3915.8456
I.2 | Contractor's Profit (CP) - As Evaluated
J.1 | Value Added Tax (VAT) - As Submitted |  |  |  |  | 5% | 2936.88
J.2 | Value Added Tax (VAT) - As Evaluated
K.1 | Total Unit Cost - As Submitted |  |  |  |  | (G.1+H.1+I.1+J.1) | 61674.564
K.2 | Total Unit Cost - As Evaluated
Note: Prices/Rates were based on CMPD 4TH Quarter CY 2022 for Materials, Memorandum dated December 29, 2022 for Labor cost and Memorandum dated May 18, 2022 for Equipment rental including Fuel & Oil/Lubricant cost as of January 4, 2023 for DPWH Regional/District Engineering Offices
Prepared by: | [5 empty] | Checked by:
WINLOVE A. ESTEVES | [5 empty] | MARK ANGELO E. SURIL
Engineer II | [5 empty] | Engineer II
DPWH-ADEO | [5 empty] | DPWH-ADEO

## B_5(dp)
FORM-POW-2015-01D-00
Item No. / Description |  |  | : | B.5 | Project Billboard/ Signboard (DPWH)
Unit of Measurement |  |  | : | ea
Output per hour - As Submitted |  |  | : | 1
Output per hour - As Evaluated |  |  | :
A.1 | Designation |  |  | No. of Person/s | No. of Hour/s | Hourly Rate | Amount (PhP)
Labor
| a. | Construction Foreman |  | 1 | 1 | 110.65 | 110.65
| b. | Skilled Laborer |  | 1 | 1 | 80.05 | 80.05
| c. | Unskilled Laborer |  | 4 | 1 | 61.75 | 247
| Sub - Total for A.1 - As Submitted | [5 empty] | 437.7 | 437.7
A.2 | Labor
| Sub - Total for A.2 - As Evaluated | [5 empty] | 0
B.1 | Name and Capacity |  |  | No. of Unit/s | No. of Hour/s | Hourly Rate | Amount (Php)
Equipment
| Minor Tools (10% of Labor) | [5 empty] | 43.77 | 10%
| Sub - Total for B.1 - As Submitted | [5 empty] | 43.77 | 43.77
B.2 | Equipment
| Sub - Total for B.2 - As Evaluated | [5 empty] | 0
C.1 | Total (A.1 + B.1) - As Submitted | [5 empty] | 481.47
C.2 | Total (A.2+ B.2) - As Evaluated
D.1 | Output per hour - As Submitted | [5 empty] | 1
D.2 | Output per hour - As Evaluated
E.1 | Direct Unit Cost (C.1 ÷ D.1) - As Submitted | [5 empty] | 481.47
E.2 | Direct Unit Cost (C.1 ÷ D.1) - As Evaluated
F.1 | Name and Specification |  |  | Unit | Quantity | Unit Cost | Amount (PhP)
Materials
| a. Tarpaulin |  |  | sqft | 32 | 50 | 1600
| b. Coco Lumber ( Braces &Frames) |  |  | bdft | 42 | 21 | 882
| c. Marine Plywood (1/4"x4'x8') |  |  | pc | 1 | 420 | 420
| d. CWN Assorted |  |  | kg | 0.42 | 77.5 | 32.55
| Sub - Total for F.1 - As Submitted | [5 empty] | 2934.55 | 2934.55
F.2 | Materials
| Sub - Total for F.2 - As Evaluated | [5 empty] | 0
G.1 | Direct Unit Cost (E.1 + F.1) - As Submitted | [5 empty] | 3416.02 | 3416.02 | 0
G.2 | Direct Unit Cost (E.2 + F.2) - As Evaluated
H.1 | Overhead, Contingencies & Miscellaneous (OCM) - As Submitted |  |  |  |  | 12% | 409.9224
H.2 | Overhead, Contingencies & Miscellaneous (OCM) - As Evaluated
I.1 | Contractor's Profit (CP) - As Submitted |  |  |  |  | 8% | 273.2816
I.2 | Contractor's Profit (CP) - As Evaluated
J.1 | Value Added Tax (VAT) - As Submitted |  |  |  |  | 5% | 204.9612
J.2 | Value Added Tax (VAT) - As Evaluated
K.1 | Total Unit Cost - As Submitted |  |  |  |  | (G.1+H.1+I.1+J.1) | 4304.19
K.2 | Total Unit Cost - As Evaluated
Note: Prices/Rates were based on CMPD 4TH Quarter CY 2022 for Materials, Memorandum dated December 29, 2022 for Labor cost and Memorandum dated May 18, 2022 for Equipment rental including Fuel & Oil/Lubricant cost as of January 4, 2023 for DPWH Regional/District Engineering Offices
Prepared by: | [5 empty] | Checked by:
WINLOVE A. ESTEVES | [5 empty] | MARK ANGELO E. SURIL
Engineer II | [5 empty] | Engineer II
DPWH-ADEO | [5 empty] | DPWH-ADEO

## B_5_(coa)
FORM-POW-2015-01D-00
Item No. / Description |  |  | : | B.5 | Project Billboard/ Signboard (COA)
Unit of Measurement |  |  | : | ea
Output per hour - As Submitted |  |  | : | 1
Output per hour - As Evaluated |  |  | :
A.1 | Designation |  |  | No. of Person/s | No. of Hour/s | Hourly Rate | Amount (PhP)
Labor
| a. | Construction Foreman |  | 1 | 2 | 110.65 | 221.3
| b. | Skilled Laborer |  | 1 | 2 | 80.05 | 160.1
| c. | Unskilled Laborer |  | 4 | 2 | 61.75 | 494
| Sub - Total for A.1 - As Submitted | [5 empty] | 875.4 | 875.4
A.2 | Labor
| Sub - Total for A.2 - As Evaluated | [5 empty] | 0
B.1 | Name and Capacity |  |  | No. of Unit/s | No. of Hour/s | Hourly Rate | Amount (Php)
Equipment
| Minor Tools (10% of Labor) | [5 empty] | 87.54 | 10%
| Sub - Total for B.1 - As Submitted | [5 empty] | 87.54 | 87.54
B.2 | Equipment
| Sub - Total for B.2 - As Evaluated | [5 empty] | 0
C.1 | Total (A.1 + B.1) - As Submitted | [5 empty] | 962.94
C.2 | Total (A.2+ B.2) - As Evaluated
D.1 | Output per hour - As Submitted | [5 empty] | 1
D.2 | Output per hour - As Evaluated
E.1 | Direct Unit Cost (C.1 ÷ D.1) - As Submitted | [5 empty] | 962.94
E.2 | Direct Unit Cost (C.1 ÷ D.1) - As Evaluated
F.1 | Name and Specification |  |  | Unit | Quantity | Unit Cost | Amount (PhP)
Materials
| a. Tarpaulin |  |  | sqft | 64 | 50 | 3200
| b. Coco Lumber ( Braces &Frames) |  |  | bdft | 84 | 21 | 1764
| c. Marine Plywood (1/4"x4'x8') |  |  | pc | 2 | 420 | 840
| d. CWN Assorted |  |  | kg | 0.84 | 77.5 | 65.1
| Sub - Total for F.1 - As Submitted | [5 empty] | 5869.1 | 5869.1
F.2 | Materials
| Sub - Total for F.2 - As Evaluated | [5 empty] | 0
G.1 | Direct Unit Cost (E.1 + F.1) - As Submitted | [5 empty] | 6832.04 | 6832.04 | 0
G.2 | Direct Unit Cost (E.2 + F.2) - As Evaluated
H.1 | Overhead, Contingencies & Miscellaneous (OCM) - As Submitted |  |  |  |  | 12% | 819.8448
H.2 | Overhead, Contingencies & Miscellaneous (OCM) - As Evaluated
I.1 | Contractor's Profit (CP) - As Submitted |  |  |  |  | 8% | 546.5632
I.2 | Contractor's Profit (CP) - As Evaluated
J.1 | Value Added Tax (VAT) - As Submitted |  |  |  |  | 5% | 409.92
J.2 | Value Added Tax (VAT) - As Evaluated
K.1 | Total Unit Cost - As Submitted |  |  |  |  | (G.1+H.1+I.1+J.1) | 8608.37
K.2 | Total Unit Cost - As Evaluated
Note: Prices/Rates were based on CMPD 4TH Quarter CY 2022 for Materials, Memorandum dated December 29, 2022 for Labor cost and Memorandum dated May 18, 2022 for Equipment rental including Fuel & Oil/Lubricant cost as of January 4, 2023 for DPWH Regional/District Engineering Offices
Prepared by: | [5 empty] | Checked by:
WINLOVE A. ESTEVES | [5 empty] | MARK ANGELO E. SURIL
Engineer II | [5 empty] | Engineer II
DPWH-ADEO | [5 empty] | DPWH-ADEO

## Man-days
DETAILED CALCULATIONS ON COST OF PERSONAL PROTECTIVE EQUIPMENT (ROAD-10)
Item No. | Description | Quantity | Output per Hour | Workers | No. of Personnel | Days | Man-days | Safety Helmet | Safety Shoes | Safety Vest | Working Gloves | Rain Coats | Face Mask | Ear Muff | Body Harness | Lanyard | Rubber Boots | Eye Goggles | Face Shield
100(3)a1 | Individual Removal of Trees (150-300 mm dia., Small) | 0 | 1 | Foreman | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
|  |  |  | Skilled Laborer | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
|  |  |  | Unskilled Laborer | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
102(2) | Surplus Common Excavation | 800.05 | 80 | Foreman | 1 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 0.375 | 1.25 |  |  |  |  | 1.25
|  |  |  | Skilled Laborer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
|  |  |  | Unskilled Laborer | 2 | 1.25 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 0.75 | 2.5 |  |  |  |  | 2.5
104(2)a | Embankment from Borrow (Common Soil) | 848.88 | 50 | Foreman | 2 | 2.12 | 4.24 | 4.24 | 4.24 | 4.24 | 4.24 | 1.272 | 4.24 |  |  |  |  | 4.24
|  |  |  | Skilled Laborer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
|  |  |  | Unskilled Laborer | 4 | 2.12 | 8.48 | 8.48 | 8.48 | 8.48 | 8.48 | 2.544 | 8.48 |  |  |  |  | 8.48
105(1)a | Subgrade Preparation (Common Material) | 5778 | 300 | Foreman | 1 | 2.41 | 2.41 | 2.41 | 2.41 | 2.41 | 2.41 | 0.723 | 2.41 |  |  |  |  | 2.41
|  |  |  | Skilled Laborer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
|  |  |  | Unskilled Laborer | 2 | 2.41 | 4.82 | 4.82 | 4.82 | 4.82 | 4.82 | 1.446 | 4.82 |  |  |  |  | 4.82
200(1) | Aggregate Subbase Course | 1551.95 | 50 | Foreman | 1 | 3.88 | 3.88 | 3.88 | 3.88 | 3.88 | 3.88 | 1.164 | 3.88 |  |  |  |  | 3.88
|  |  |  | Skilled Laborer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
|  |  |  | Unskilled Laborer | 2 | 3.88 | 7.76 | 7.76 | 7.76 | 7.76 | 7.76 | 2.328 | 7.76 |  |  |  |  | 7.76
311(1)b1 | Portland Cement Concrete Pavement (Unreinforced, 0.20m thick, 14 days) | 4815 | 80.5 | Foreman | 1 | 7.48 | 7.48 | 7.48 |  | 7.48 | 7.48 | 2.244 | 7.48 |  |  |  | 7.48 | 7.48
|  |  |  | Skilled Laborer | 4 | 7.48 | 29.92 | 29.92 |  | 29.92 | 29.92 | 8.976 | 29.92 |  |  |  | 29.92 | 29.92
|  |  |  | Unskilled Laborer | 12 | 7.48 | 89.76 | 89.76 |  | 89.76 | 89.76 | 26.928 | 89.76 |  |  |  | 89.76 | 89.76
506(1) | Stone Masonry(Slope Protection) | 336 | 1.6 | Foreman | 1 | 26.25 | 26.25 | 26.25 |  | 26.25 | 26.25 | 7.875 | 26.25 |  |  |  | 26.25 | 26.25
|  |  |  | Skilled Laborer | 2 | 26.25 | 52.5 | 52.5 |  | 52.5 | 52.5 | 15.75 | 52.5 |  |  |  | 52.5 | 52.5
|  |  |  | Unskilled Laborer | 8 | 26.25 | 210 | 210 |  | 210 | 210 | 63 | 210 |  |  |  | 210 | 210
[23 empty] | 20719.15 | 1657.532
|  |  |  | A. Total, Personnel/ Man-days | 47 |  | 281.3629 | 281.3629 | 35.34 | 281.3629 | 281.3629 | 135.375 | 281.3629 | 0 | 0 | 0 | 246.0229 | 281.3629 | 0 |  |  |  | 3459.21 | 172.9605
|  |  |  | B. Service Life, Days |  |  |  | 730 | 365 | 180 | 3 | 730 | 0.5 | 730 | 730 | 730 | 365 | 60 | 60
|  |  |  | C. Purchase Cost, Ph |  |  |  | 250 | 1500 | 400 | 23 | 245 | 5 | 602.6 | 1263.85 | 1083.3 | 506 | 300 | 500
|  |  |  | D. Unit Cost/Man-Day (C/B) |  |  |  | 0.34247 | 4.1096 | 2.2222 | 7.6667 | 0.33562 | 10 |  |  |  | 1.3863 | 5 |  |  |  | CD | 65
|  |  |  | E. Direct Cost for PPE's (D x A (Man-days)) |  |  |  | 96.3572 | 145.2329 | 625.2508 | 2157.1154 | 45.4341 | 2813.6288 | 0 | 0 | 0 | 341.0619 | 1406.8144 | 0 | 7630.8954 |  | weeks | hrs | days
|  |  |  | F. Safety Officer/Practitioner (Part Time) @ 15,000/Month (as Per D.O. 56,S2005, consider at least 4 hours per week) | [15 empty] | 2500 |  | 9.2857 | 37.1429 | 4.6429 | 5 | 2500
|  |  |  | G. Health Personnel (Full Time) @ 8,400/Month ( as per D.O. 56, S2005) | [15 empty] | 18200 |  |  |  | 280
|  |  |  | H. Total Direct Cost (E+F+G) | [15 empty] | 28330.8954 |  |  |  | 500
|  |  |  | I. OCM(% of H) | [15 empty] | 0
|  |  |  | J. Profit (% of H) | [15 empty] | 2266.4716 | 8%
|  |  |  | K. Vat (5% of H+I+J) | [15 empty] | 1529.8683 | 5%
|  |  |  | L. Total Cost (H+I+J+K) | [15 empty] | 32127.2353
Err:508
Planning and Design Section

## B_7(2)
FORM-POW-2015-01D-00
Item No. / Description |  |  | : | B.7 (2) | Occupational Safety and Health Program
Unit of Measurement |  |  | : | ls
Output - As Submitted |  |  | : | 1
Output - As Evaluated |  |  | :
A.1 | Designation |  |  | No. of Person/s | No. of Day/s | Daily Rate | Amount (PhP) | 65 | TOTAL CD
Labor
| a. | Safety Officer (Part Time) |  | 1 | 16 | 885.2 | 14163.2
| b. | Health Personnel (Full Time First Aider) |  | 1 | 65 | 640.4 | 41626
| c. | Sanitation Aide (Part Time) |  | 2 | 16 | 494 | 15808
| Sub - Total for A.1 - As Submitted | [5 empty] | 71597.2 | 71597.2
A.2 | Labor
| Sub - Total for A.2 - As Evaluated | [5 empty] | 0
B.1 | Name and Capacity |  |  | No. of Unit/s | No. of Hour/s | Hourly Rate | Amount (Php)
Equipment
| a. | Portable Mist-Based Sanitation Tent |  | 1 | 520 | 9.79 | 5090.8
| b. | Thermal Scanner (w/ rechargeable battery) |  | 2 | 520 | 1.03 | 1071.2
| c. | Power Sprayer w/ complete accessories |  | 1 | 520 | 3.47 | 1804.4
| Sub - Total for B.1 - As Submitted | [5 empty] | 7966.4 | 7966.4
B.2 | Equipment
| Sub - Total for B.2 - As Evaluated | [5 empty] | 0
C.1 | Total (A.1 + B.1) - As Submitted | [5 empty] | 79563.6
C.2 | Total (A.2+ B.2) - As Evaluated
D.1 | Output - As Submitted | [5 empty] | 1
D.2 | Output - As Evaluated
E.1 | Direct Unit Cost (C.1 ÷ D.1) - As Submitted | [5 empty] | 79563.6
E.2 | Direct Unit Cost (C.1 ÷ D.1) - As Evaluated
F.1 | Name and Specification |  |  | Unit | Quantity | Unit Cost | Amount (PhP)
Materials
Personal Protective Equipment (PPE)
| a. Safety Helmet |  |  | 0 | 281.3629 | 0.34247 | 96.3572
| b. Safety Shoes |  |  | man-days | 35.34 | 4.1096 | 145.2329
| c. Safety Vest |  |  | man-days | 281.3629 | 2.2222 | 625.2508 |  | 1344265.38
| d. Working Gloves |  |  | man-days | 281.3629 | 7.6667 | 2157.1154
| e. Face Mask (Surgical/Cloth) |  |  | man-days | 281.3629 | 10 | 2813.6288 |  |  | 0
| f. Rubber Boots |  |  | man-days | 246.0229 | 1.3863 | 341.0619
| g. Eye Goggles |  |  | man-days | 281.3629 | 5 | 1406.8144 |  | 169.8871
| h. Face Shield |  |  | man-days | 0 | 0 | 0
| i. Rain Coats (30% of the Duration) |  |  | man-days | 135.375 | 0.33562 | 45.4341 |  | 7630.8954
TRUE
| COVID 19 Rapid Antibody Test |  |  | each | 7 | 1000 | 7000
Antiseptics and Disinfectant (25% of Total Duration)
| k. Sanitizing Solution |  |  | lit | 16 | 100 | 1600
| l. Ethyl Alcohol |  |  | lit | 16 | 185 | 2960
| m. Disinfectant Spray (400-550 grams) |  |  | can | 16 | 510 | 8160
| n. Liquid Hand Soap |  |  | lit | 16 | 150 | 2400
| Sub - Total for F.1 - As Submitted | [5 empty] | 29750.8954 | 29750.9 |  | 0
F.2 | Materials
| Sub - Total for F.2 - As Evaluated | [5 empty] | 0
G.1 | Direct Unit Cost (E.1 + F.1) - As Submitted | [5 empty] | 109314.5 | 109314.5 | 0 |  | 325640.3784 | 7801031.85
G.2 | Direct Unit Cost (E.2 + F.2) - As Evaluated | [9 empty] | 5613700.325 | 1532301.48
H.1 | Overhead, Contingencies & Miscellaneous (OCM) - As Submitted |  |  |  |  | 0% | 0 |  |  |  | 1861691.1416 | 466666.67
H.2 | Overhead, Contingencies & Miscellaneous (OCM) - As Evaluated | [9 empty] | 0 | 9800000
I.1 | Contractor's Profit (CP) - As Submitted |  |  |  |  | 8% | 8745.16 |  |  |  | 1532301.48 | 200000
I.2 | Contractor's Profit (CP) - As Evaluated | [9 empty] | 466666.67
J.1 | Value Added Tax (VAT) - As Submitted |  |  |  |  | 5% | 5902.98 |  |  |  | 200000
J.2 | Value Added Tax (VAT) - As Evaluated
K.1 | Total Unit Cost - As Submitted |  |  |  |  | (G.1+H.1+I.1+J.1) | 123962.64 | 7801031.85 | 0
K.2 | Total Unit Cost - As Evaluated | [6 empty] | 1.9% | gravel to concrete
Note: Prices/Rates were based on CMPD 4TH Quarter CY 2022 for Materials, Memorandum dated December 29, 2022 for Labor cost and Memorandum dated May 18, 2022 for Equipment rental including Fuel & Oil/Lubricant cost as of January 4, 2023 for DPWH Regional/District Engineering Offices | [7 empty] | 148219.6052
Prepared by: | [5 empty] | Checked by: |  | -24256.9652
1.589%
WINLOVE A. ESTEVES | [5 empty] | MARK ANGELO E. SURIL
Engineer II | [5 empty] | Engineer II
DPWH-ADEO | [5 empty] | DPWH-ADEO

## B_8(2)
Item No. / Description |  | : | B.8(2) | Road Works Safety and Traffic Management
Unit of Measurement |  | : | ls
Output - As Submitted |  | : | 1
Output - As Evaluated |  | :
A.1 | Designation |  | No. of Person/s | No. of Day/s | Daily Rate | Amount (PhP)
Labor
| Sub - Total for A.1 - As Submitted |  |  |  |  | 0 | 0
A.2 | Labor
| Sub - Total for A.2 - As Evaluated |  |  |  |  | 0
B.1 | Name and Capacity |  | No. of Unit/s | No. of Hour/s | Hourly Rate | Amount (Php)
Equipment
| Sub - Total for B.1 - As Submitted |  |  |  |  | 0 | 0
B.2 | Equipment
| Sub - Total for B.2 - As Evaluated |  |  |  |  | 0
C.1 | Total (A.1 + B.1) - As Submitted |  |  |  |  | 0
C.2 | Total (A.2+ B.2) - As Evaluated
D.1 | Output - As Submitted |  |  |  |  | 1
D.2 | Output - As Evaluated
E.1 | Direct Unit Cost (C.1 ÷ D.1) - As Submitted |  |  |  |  | 0
E.2 | Direct Unit Cost (C.1 ÷ D.1) - As Evaluated
F.1 | Name and Specification |  | Unit | Quantity | Unit Cost | Amount (PhP)
[7 empty] | 65 | TOTAL DURATION
| Materials | [5 empty] | 39 | PCCP ONLY
| a. Roadwork Ahead (T1-1) |  | ea | 4 | 711.75 | 2847 | 10.95 | 711.75 | quantity in traffic is 1/no of mos.
| b. End Roadwork (T2-16) |  | ea | 4 | 711.75 | 2847 | 10.95 | 711.75
| c. Slippery (T3-3) |  | ea | 8 | 366.6 | 2932.8 | 5.64 | 366.6
| d. Loose Stones (T3-9) |  | ea | 8 | 366.6 | 2932.8 | 5.64 | 366.6
Note: Modifications may be made if deemed necessary.
| Sub - Total for F.1 - As Submitted |  |  |  |  | 11559.6 | 11559.6
F.2 | Materials
| Sub - Total for F.2 - As Evaluated |  |  |  |  | 0
G.1 | Direct Unit Cost (E.1 + F.1) - As Submitted |  |  |  |  | 11559.6 | 11559.6 | 0
G.2 | Direct Unit Cost (E.2 + F.2) - As Evaluated
H.1 | Overhead, Contingencies & Miscellaneous (OCM) - As Submitted |  |  |  | 0% | 0
H.2 | Overhead, Contingencies & Miscellaneous (OCM) - As Evaluated
I.1 | Contractor's Profit (CP) - As Submitted |  |  |  | 8% | 924.77
I.2 | Contractor's Profit (CP) - As Evaluated
J.1 | Value Added Tax (VAT) - As Submitted |  |  |  | 5% | 624.22
J.2 | Value Added Tax (VAT) - As Evaluated
K.1 | Total Unit Cost - As Submitted |  |  |  | (G.1+H.1+I.1+J.1) | 13108.59
K.2 | Total Unit Cost - As Evaluated
Note: Prices/Rates were based on CMPD 4TH Quarter CY 2022 for Materials, Memorandum dated December 29, 2022 for Labor cost and Memorandum dated May 18, 2022 for Equipment rental including Fuel & Oil/Lubricant cost as of January 4, 2023 for DPWH Regional/District Engineering Offices
Prepared by: |  |  |  |  | Checked by:
WINLOVE A. ESTEVES |  |  |  |  | MARK ANGELO E. SURIL
Engineer II |  |  |  |  | Engineer II
DPWH-ADEO |  |  |  |  | DPWH-ADEO

## B_9
FORM-POW-2015-01D-00
Item No. / Description |  |  | : | B.9 | Mobilization/ Demobilization
Unit of Measurement |  |  | : | ls
Output - As Submitted |  |  | : | 1
Output - As Evaluated |  |  | :
A.1 | Designation |  |  | No. of Person/s | No. of Day/s | Daily Rate | Amount (PhP)
Labor
| Sub - Total for A.1 - As Submitted | [5 empty] | 0
A.2 | Labor
| Sub - Total for A.2 - As Evaluated | [5 empty] | 0
B.1 | Name and Capacity |  |  | No. of Unit/s | No. of Day/s | Daily Rate | Amount (Php)
Equipment
Low Bed Trailer
| a. | Backhoe, SOLAR 220 LC-3 (0.80 m³,138 hp) |  | 1 | 0.67 | 20000 | 13400 | 5.36
| b. | Bulldozer, DX175 (167 hp) |  | 1 | 0.67 | 20000 | 13400 |  |  | 0.9257%
| c. | Payloader, LX80-2C (1.50m³, 110 hp) |  | 1 | 0.67 | 20000 | 13400 | 321.6
| d. | Motorized Road Grader, G710A (140 hp) |  | 1 | 0.67 | 20000 | 13400 | 80.4
| e. | Vibratory Roller, SD100DC (10mt, 125 hp) |  | 1 | 0.67 | 20000 | 13400 | 1.34
Note: Low bed trailer daily rate = Php 20,000
| Sub - Total for B.1 - As Submitted | [5 empty] | 67000 | 67000
B.2 | Equipment
Sub - Total for B.2 - As Evaluated
C.1 | Total (A.1 + B.1) - As Submitted | [5 empty] | 67000
C.2 | Total (A.2+ B.2) - As Evaluated
D.1 | Output - As Submitted | [5 empty] | 1
D.2 | Output - As Evaluated
E.1 | Direct Unit Cost (C.1 ÷ D.1) - As Submitted | [5 empty] | 67000
E.2 | Direct Unit Cost (C.1 ÷ D.1) - As Evaluated
F.1 | Name and Specification |  |  | Unit | Quantity | Unit Cost | Amount (PhP)
Materials
Column1
| Sub - Total for F.1 - As Submitted | [5 empty] | 0
F.2 | Materials
| Sub - Total for F.2 - As Evaluated | [5 empty] | 0
G.1 | Direct Unit Cost (E.1 + F.1) - As Submitted | [5 empty] | 67000 | 67000 | 0
G.2 | Direct Unit Cost (E.2 + F.2) - As Evaluated
H.1 | Overhead, Contingencies & Miscellaneous (OCM) - As Submitted |  |  |  |  | 0% | 0
H.2 | Overhead, Contingencies & Miscellaneous (OCM) - As Evaluated
I.1 | Contractor's Profit (CP) - As Submitted |  |  |  |  | 0% | 0
I.2 | Contractor's Profit (CP) - As Evaluated
J.1 | Value Added Tax (VAT) - As Submitted |  |  |  |  | 5% | 3350
J.2 | Value Added Tax (VAT) - As Evaluated
K.1 | Total Unit Cost - As Submitted |  |  |  |  | (G.1+H.1+I.1+J.1) | 70350 | 7599493.67
K.2 | Total Unit Cost - As Evaluated | [6 empty] | 75994.9367 | 0.9257%
Note: Prices/Rates were based on CMPD 4TH Quarter CY 2022 for Materials, Memorandum dated December 29, 2022 for Labor cost and Memorandum dated May 18, 2022 for Equipment rental including Fuel & Oil/Lubricant cost as of January 4, 2023 for DPWH Regional/District Engineering Offices | [7 empty] | 5644.9367
Mobilization and demobilization shall not exceed 1% of the Estimated Direct Cost (EDC) of the civil works items. (D.O. No. 197, Series of 2016)
Prepared by: | [5 empty] | Checked by:
WINLOVE A. ESTEVES | [5 empty] | MARK ANGELO E. SURIL
Engineer II | [5 empty] | Engineer II
Planning and Design Section | [5 empty] | Planning and Design Section
DPWH-ADEO | [5 empty] | DPWH-ADEO
[9 empty] | EquipmentSource | : | DEO
[9 empty] | Rental Cost | : | 20,000/day | 2500 | per Hour
[9 empty] | Distance (from DEO to site) | : | 18.2 | km
[9 empty] | Free Hauling Distance | : | 5 | km
[9 empty] | Hauling Distance | : | 13.2 | km
[9 empty] | TERRAIN CONDITION | DISTANCE (km) |  | RATE (km/h) | LOADING TIME (min) | LOADING TIME (hr) | TRAVEL TIME (LOADED) (hr) | UNLOAD AND MANEUVER (min) | UNLOAD AND MANEUVER (hr) | RATE (km/h) | TRAVEL TIME (EMPTY) (hr) | CYCLE TIME | ALLOWANCE FOR DELAY (10% of Cycle Time) | TOTAL CYCLE TIME (hr)
[9 empty] | TERRAIN CONDITION | DISTANCE (km) |  | RATE (km/h) | LOADING TIME (min) | LOADING TIME (hr) | TRAVEL TIME (LOADED) (hr) | UNLOAD AND MANEUVER (min) | UNLOAD AND MANEUVER (hr) | RATE (km/h) | TRAVEL TIME (EMPTY) (hr) | CYCLE TIME | ALLOWANCE FOR DELAY (10% of Cycle Time) | TOTAL CYCLE TIME (hr)
FLAT
[9 empty] | Paved | 18.2 |  | 35 | 3 | 0.05 | 0.57 | 2 | 0.033333 | 55 | 0.36424 | 0.93424 | 0.093424 | 1.0277 | 0.057
[9 empty] | Unpaved |  |  | 30 |  | 0 | 0 |  | 0 | 45 | 0 | 0 | 0 | 0
ROLLING
[9 empty] | Paved | 0 |  | 30 |  | 0 | 0 |  | 0 | 40 | 0 | 0 | 0 | 0 | 0
[9 empty] | Unpaved |  |  | 25 |  | 0 | 0 |  | 0 | 35 | 0 | 0 | 0 | 0
MOUNTAINOUS
[9 empty] | Paved | 0 |  | 20 |  | 0 | 0 |  | 0 | 30 | 0 | 0 | 0 | 0 | 0
[9 empty] | Unpaved |  |  | 15 |  | 0 | 0 |  | 0 | 25 | 0 | 0 | 0 | 0
[9 empty] | T O T A L | 18.2 |  |  |  |  | 0.57 |  |  |  | 0.36424 |  | 0.093424 | 1.0277 | TRUE
Note: Mobilization and demobilization shall not exceed 1% of the Estimated Direct Cost (EDC) of the civil works items. (D.O. No. 197, Series of 2016)
[9 empty] | Loading Using Low Bed | TRUE |  |  |  |  | 0.627 | [6 empty] | 0.12846 | days
[15 empty] | 0.078375 | Day
61.66

## 100(3)a1
FORM-POW-2015-01D-00
Item No. / Description |  |  | : | 100(3)a1 | Individual Removal of Trees (150-300 mm dia., Small)
Unit of Measurement |  |  | : | ea
Output per hour - As Submitted |  |  | : | 1
Output per hour - As Evaluated |  |  | :
A.1 | Designation |  |  | No. of Person/s | No. of Hour/s | Hourly Rate | Amount (PhP)
Labor
| a. | Construction Foreman |  | 1 | 0.33 | 110.65 | 36.5145
| b. | Skilled Laborer |  | 1 | 0.33 | 80.05 | 26.4165
| c. | Unskilled Laborer |  | 2 | 0.33 | 61.75 | 40.755
| Sub - Total for A.1 - As Submitted | [5 empty] | 103.686 | 103.69 | 103.686 | 0.004
A.2 | Labor
| Sub - Total for A.2 - As Evaluated | [5 empty] | 0
B.1 | Name and Capacity |  |  | No. of Unit/s | No. of Hour/s | Hourly Rate | Amount (Php)
Equipment
| a. | Backhoe, SOLAR 220 LC-3 (0.80 m³,138 hp) |  | 1 | 0.25 | 2588.75 | 647.1875
| b. | Dump Truck (12 yd³, 290 hp) |  | 1 | 0.17 | 2932.45 | 498.5165
| c. | Chain Saw |  | 1 | 0.17 | 75.36 | 12.8112
| Minor Tools (5% of Labor Cost) | [5 empty] | 5.1843 | 5%
| Sub - Total for B.1 - As Submitted | [5 empty] | 1163.6995 | 1163.7 | 1163.6995 | 0.0005
B.2 | Equipment
| Sub - Total for B.2 - As Evaluated | [5 empty] | 0
C.1 | Total (A.1 + B.1) - As Submitted | [5 empty] | 1267.3855
C.2 | Total (A.2+ B.2) - As Evaluated
D.1 | Output per hour - As Submitted | [5 empty] | 1
D.2 | Output per hour - As Evaluated
E.1 | Direct Unit Cost (C.1 ÷ D.1) - As Submitted | [5 empty] | 1267.3855
E.2 | Direct Unit Cost (C.1 ÷ D.1) - As Evaluated
F.1 | Name and Specification |  |  | Unit | Quantity | Unit Cost | Amount (PhP)
Materials
| a. Rope, 1" Ø - 5 uses |  |  | m | 20 | 120 | 480
| Sub - Total for F.1 - As Submitted | [5 empty] | 480 | 480 | 480 | 0
F.2 | Materials
| Sub - Total for F.2 - As Evaluated | [5 empty] | 0
G.1 | Direct Unit Cost (E.1 + F.1) - As Submitted | [5 empty] | 1747.39 | 1747.39 | 0
G.2 | Direct Unit Cost (E.2 + F.2) - As Evaluated
H.1 | Overhead, Contingencies & Miscellaneous (OCM) - As Submitted |  |  |  |  | 12% | 209.6868
H.2 | Overhead, Contingencies & Miscellaneous (OCM) - As Evaluated
I.1 | Contractor's Profit (CP) - As Submitted |  |  |  |  | 8% | 139.7912
I.2 | Contractor's Profit (CP) - As Evaluated
J.1 | Value Added Tax (VAT) - As Submitted |  |  |  |  | 5% | 104.8434
J.2 | Value Added Tax (VAT) - As Evaluated
K.1 | Total Unit Cost - As Submitted |  |  |  |  | (G.1+H.1+I.1+J.1) | 2201.71
K.2 | Total Unit Cost - As Evaluated
Note: Prices/Rates were based on CMPD 4TH Quarter CY 2022 for Materials, Memorandum dated December 29, 2022 for Labor cost and Memorandum dated May 18, 2022 for Equipment rental including Fuel & Oil/Lubricant cost as of January 4, 2023 for DPWH Regional/District Engineering Offices
Prepared by: | [5 empty] | Checked by:
WINLOVE A. ESTEVES | [5 empty] | MARK ANGELO E. SURIL
Engineer II | [5 empty] | Engineer II
DPWH-ADEO | [5 empty] | DPWH-ADEO

## 102(2)
FORM-POW-2015-01D-00
Item No. / Description |  |  | : | 102(2) | Surplus Common Excavation
Unit of Measurement |  |  | : | cum
Output per hour - As Submitted |  |  | : | 80
Output per hour - As Evaluated |  |  | :
A.1 | Designation |  |  | No. of Person/s | No. of Hour/s | Hourly Rate | Amount (PhP)
Labor
| a. | Construction Foreman |  | 1 | 1 | 110.65 | 110.65
| b. | Unskilled Laborer |  | 2 | 1 | 61.75 | 123.5
| Sub - Total for A.1 - As Submitted | [5 empty] | 234.15 | 2.93
A.2 | Labor
| Sub - Total for A.2 - As Evaluated | [5 empty] | 0
B.1 | Name and Capacity |  |  | No. of Unit/s | No. of Hour/s | Hourly Rate | Amount (Php)
Equipment
| a. | Bulldozer, DX175 (167 hp) |  | 1 | 1 | 4060.69 | 4060.69
| b. | Payloader, LX80-2C (1.50m³, 110 hp) |  | 1 | 1 | 2114.8 | 2114.8
| c. | Payloader, LX80-2C (1.50m³, 110 hp) - at disposal area |  | 1 | 0.3 | 2114.8 | 634.44
| d. | Dump Truck (12 yd³, 290 hp) |  | 3 | 1 | 2932.45 | 8797.35
| e. | Backhoe, SOLAR 220 LC-3 (0.80 m³,138 hp) |  | 1 | 1 | 2588.75 | 2588.75
| Sub - Total for B.1 - As Submitted | [5 empty] | 18196.03 | 227.45
B.2 | Equipment
| Sub - Total for B.2 - As Evaluated | [5 empty] | 0
C.1 | Total (A.1 + B.1) - As Submitted | [5 empty] | 18430.18
C.2 | Total (A.2+ B.2) - As Evaluated
D.1 | Output per hour - As Submitted | [5 empty] | 80
D.2 | Output per hour - As Evaluated
E.1 | Direct Unit Cost (C.1 ÷ D.1) - As Submitted | [5 empty] | 230.3773
E.2 | Direct Unit Cost (C.1 ÷ D.1) - As Evaluated
F.1 | Name and Specification |  |  | Unit | Quantity | Unit Cost | Amount (PhP)
Materials
| Sub - Total for F.1 - As Submitted | [5 empty] | 0
F.2 | Materials
| Sub - Total for F.2 - As Evaluated | [5 empty] | 0
G.1 | Direct Unit Cost (E.1 + F.1) - As Submitted | [5 empty] | 230.38 | 230.38 | 0
G.2 | Direct Unit Cost (E.2 + F.2) - As Evaluated
H.1 | Overhead, Contingencies & Miscellaneous (OCM) - As Submitted |  |  |  |  | 12% | 27.65
H.2 | Overhead, Contingencies & Miscellaneous (OCM) - As Evaluated
I.1 | Contractor's Profit (CP) - As Submitted |  |  |  |  | 8% | 18.43
I.2 | Contractor's Profit (CP) - As Evaluated
J.1 | Value Added Tax (VAT) - As Submitted |  |  |  |  | 5% | 13.82
J.2 | Value Added Tax (VAT) - As Evaluated
K.1 | Total Unit Cost - As Submitted |  |  |  |  | (G.1+H.1+I.1+J.1) | 290.28
K.2 | Total Unit Cost - As Evaluated
Note: Prices/Rates were based on CMPD 4TH Quarter CY 2022 for Materials, Memorandum dated December 29, 2022 for Labor cost and Memorandum dated May 18, 2022 for Equipment rental including Fuel & Oil/Lubricant cost as of January 4, 2023 for DPWH Regional/District Engineering Offices
Prepared by: | [5 empty] | Checked by:
WINLOVE A. ESTEVES | [5 empty] | MARK ANGELO E. SURIL
Engineer II | [5 empty] | Engineer II
DPWH-ADEO | [5 empty] | DPWH-ADEO

## 104(1)a
FORM-POW-2015-01D-00
Item No./Description |  |  | : | 104(1)a | Embankment from Roadway Excavation (Common Soil)
Unit of Measurement |  |  | : | cum
Output per hour - As Submitted |  |  | : | 50
Output per hour - As Evaluated |  |  | :
A.1 | Designation |  |  | No. of Person/s | No. of Hour/s | Hourly Rate | Amount (PhP)
Labor
For Excavation Work:
| a. | Construction Foreman |  | 1 | 0.83 | 110.65 | 91.8395
| b. | Unskilled Laborer |  | 2 | 0.83 | 61.75 | 102.505
Spreading and Compaction:
| a. | Construction Foreman |  | 1 | 1 | 110.65 | 110.65
| b. | Unskilled Laborer |  | 2 | 1 | 61.75 | 123.5
| Sub - Total for A.1 - As Submitted | [5 empty] | 428.4945 | 8.57
A.2 | Labor
| Sub - Total for A.2 - As Evaluated | [5 empty] | 0
B.1 | Name and Capacity |  |  | No. of Unit/s | No. of Hour/s | Hourly Rate | Amount (Php)
Equipment
For Excavation Work:
| a. | Bulldozer, DX175 (167 hp) |  | 1 | 0.83 | 4060.69 | 3370.3727
| b. | Payloader, LX80-2C (1.50m³, 110 hp) |  | 1 | 0.83 | 2114.8 | 1755.284
| c. | Dump Truck (12 yd³, 290 hp) |  | 2 | 0.83 | 2932.45 | 4867.867
Spreading and Compaction:
| a. | Motorized Road Grader, G710A (140 hp) |  | 1 | 1 | 2664.75 | 2664.75
| b. | Vibratory Roller, SD100DC (10mt, 125 hp) |  | 1 | 1 | 2396.78 | 2396.78
| c. | Water Truck/Pump (16000 L, 360 hp) |  | 1 | 0.25 | 4217.31 | 1054.3275
| Sub - Total for B.1 - As Submitted | [5 empty] | 16109.3812 | 322.19
B.2 | Equipment
| Sub - Total for B.2 - As Evaluated | [5 empty] | 0
C.1 | Total (A.1 + B.1) - As Submitted | [5 empty] | 16537.8757
C.2 | Total (A.2+ B.2) - As Evaluated
D.1 | Output per hour - As Submitted | [5 empty] | 50
D.2 | Output per hour - As Evaluated
E.1 | Direct Unit Cost (C.1 ÷ D.1) - As Submitted | [5 empty] | 330.7575
E.2 | Direct Unit Cost (C.1 ÷ D.1) - As Evaluated
F.1 | Name and Specification |  |  | Unit | Quantity | Unit Cost | Amount (PhP)
Materials
| Sub - Total for F.1 - As Submitted | [5 empty] | 0 | 0
F.2 | Materials
| Sub - Total for F.2 - As Evaluated | [5 empty] | 0
G.1 | Direct Unit Cost (E.1 + F.1) - As Submitted | [5 empty] | 330.76 | 330.76 | 0
G.2 | Direct Unit Cost (E.2 + F.2) - As Evaluated
H.1 | Overhead, Contingencies & Miscellaneous (OCM) - As Submitted |  |  |  |  | 12% | 39.691
H.2 | Overhead, Contingencies & Miscellaneous (OCM) - As Evaluated
I.1 | Contractor's Profit (CP) - As Submitted |  |  |  |  | 8% | 26.46
I.2 | Contractor's Profit (CP) - As Evaluated
J.1 | Value Added Tax (VAT) - As Submitted |  |  |  |  | 5% | 19.85
J.2 | Value Added Tax (VAT) - As Evaluated
K.1 | Total Unit Cost - As Submitted |  |  |  |  | (G.1+H.1+I.1+J.1) | 416.76
K.2 | Total Unit Cost - As Evaluated
Note: Prices/Rates were based on CMPD 4TH Quarter CY 2022 for Materials, Memorandum dated December 29, 2022 for Labor cost and Memorandum dated May 18, 2022 for Equipment rental including Fuel & Oil/Lubricant cost as of January 4, 2023 for DPWH Regional/District Engineering Offices
Prepared by: | [5 empty] | Checked by:
WINLOVE A. ESTEVES | [5 empty] | MARK ANGELO E. SURIL
Engineer II | [5 empty] | Engineer II
DPWH-ADEO | [5 empty] | DPWH-ADEO

## 104(2)a
FORM-POW-2015-01D-00
Item No./Description |  |  | : | 104(2)a | Embankment from Borrow (Common Soil)
Unit of Measurement |  |  | : | cum
Output per hour - As Submitted |  |  | : | 50
Output per hour - As Evaluated |  |  | :
A.1 | Designation |  |  | No. of Person/s | No. of Hour/s | Hourly Rate | Amount (PhP)
Labor
| a. | Construction Foreman |  | 1 | 1 | 110.65 | 110.65
| b. | Unskilled Laborer |  | 2 | 1 | 61.75 | 123.5
| Sub - Total for A.1 - As Submitted | [5 empty] | 234.15 | 4.68
A.2 | Labor
| Sub - Total for A.2 - As Evaluated | [5 empty] | 0
B.1 | Name and Capacity |  |  | No. of Unit/s | No. of Hour/s | Hourly Rate | Amount (Php)
Equipment
| a. | Motorized Road Grader, G710A (140 hp) |  | 1 | 1 | 2664.75 | 2664.75
| b. | Vibratory Roller, SD100DC (10mt, 125 hp) |  | 1 | 1 | 2396.78 | 2396.78
| c. | Water Truck/Pump (16000 L, 360 hp) |  | 1 | 0.25 | 4217.31 | 1054.3275
| Sub - Total for B.1 - As Submitted | [5 empty] | 6115.8575 | 122.32
B.2 | Equipment
| Sub - Total for B.2 - As Evaluated | [5 empty] | 0
C.1 | Total (A.1 + B.1) - As Submitted | [5 empty] | 6350.0075
C.2 | Total (A.2+ B.2) - As Evaluated
D.1 | Output per hour - As Submitted | [5 empty] | 50
D.2 | Output per hour - As Evaluated
E.1 | Direct Unit Cost (C.1 ÷ D.1) - As Submitted | [5 empty] | 127.0002
E.2 | Direct Unit Cost (C.1 ÷ D.1) - As Evaluated
F.1 | Name and Specification |  |  | Unit | Quantity | Unit Cost | Amount (PhP)
Materials
| a. Common Borrow (w/ 25% Shrinkage Factor) |  |  | cum | 1.25 | 340 | 425
| Sub - Total for F.1 - As Submitted | [5 empty] | 425 | 425
F.2 | Materials
| Sub - Total for F.2 - As Evaluated | [5 empty] | 0
G.1 | Direct Unit Cost (E.1 + F.1) - As Submitted | [5 empty] | 552 | 552 | 0
G.2 | Direct Unit Cost (E.2 + F.2) - As Evaluated
H.1 | Overhead, Contingencies & Miscellaneous (OCM) - As Submitted |  |  |  |  | 12% | 66.24
H.2 | Overhead, Contingencies & Miscellaneous (OCM) - As Evaluated
I.1 | Contractor's Profit (CP) - As Submitted |  |  |  |  | 8% | 44.16
I.2 | Contractor's Profit (CP) - As Evaluated
J.1 | Value Added Tax (VAT) - As Submitted |  |  |  |  | 5% | 33.12
J.2 | Value Added Tax (VAT) - As Evaluated
K.1 | Total Unit Cost - As Submitted |  |  |  |  | (G.1+H.1+I.1+J.1) | 695.52
K.2 | Total Unit Cost - As Evaluated
Note: Prices/Rates were based on CMPD 4TH Quarter CY 2022 for Materials, Memorandum dated December 29, 2022 for Labor cost and Memorandum dated May 18, 2022 for Equipment rental including Fuel & Oil/Lubricant cost as of January 4, 2023 for DPWH Regional/District Engineering Offices
Prepared by: | [5 empty] | Checked by:
WINLOVE A. ESTEVES | [5 empty] | MARK ANGELO E. SURIL
Engineer II | [5 empty] | Engineer II
DPWH-ADEO | [5 empty] | DPWH-ADEO

## 105(1)a
FORM-POW-2015-01D-00
Item No. / Description |  |  | : | 105(1)a | Subgrade Preparation (Common Material)
Unit of Measurement |  |  | : | sqm
Output per hour - As Submitted |  |  | : | 300
Output per hour - As Evaluated |  |  | :
A.1 | Designation |  |  | No. of Person/s | No. of Hour/s | Hourly Rate | Amount (PhP)
Labor
| a. | Construction Foreman |  | 1 | 1 | 110.65 | 110.65
| b. | Unskilled Laborer |  | 2 | 1 | 61.75 | 123.5
| Sub - Total for A.1 - As Submitted | [5 empty] | 234.15 | 0.78 | 0.7805 | -0.0005
A.2 | Labor
| Sub - Total for A.2 - As Evaluated | [5 empty] | 0
B.1 | Name and Capacity |  |  | No. of Unit/s | No. of Hour/s | Hourly Rate | Amount (Php)
Equipment
| a. | Motorized Road Grader, G710A (140 hp) |  | 1 | 1 | 2664.75 | 2664.75
| b. | Vibratory Roller, SD100DC (10mt, 125 hp) |  | 1 | 1 | 2396.78 | 2396.78
| c. | Water Truck/Pump (16000 L, 360 hp) |  | 1 | 0.25 | 4217.31 | 1054.3275
| Sub - Total for B.1 - As Submitted | [5 empty] | 6115.8575 | 20.39 | 20.3862 | 0.0038083
B.2 | Equipment
| Sub - Total for B.2 - As Evaluated | [5 empty] | 0
C.1 | Total (A.1 + B.1) - As Submitted | [5 empty] | 6350.0075
C.2 | Total (A.2+ B.2) - As Evaluated
D.1 | Output per hour - As Submitted | [5 empty] | 300
D.2 | Output per hour - As Evaluated
E.1 | Direct Unit Cost (C.1 ÷ D.1) - As Submitted | [5 empty] | 21.1667
E.2 | Direct Unit Cost (C.1 ÷ D.1) - As Evaluated
F.1 | Name and Specification |  |  | Unit | Quantity | Unit Cost | Amount (PhP)
Materials
| Sub - Total for F.1 - As Submitted | [5 empty] | 0 | 0 | 0
F.2 | Materials
| Sub - Total for F.2 - As Evaluated | [5 empty] | 0
G.1 | Direct Unit Cost (E.1 + F.1) - As Submitted | [5 empty] | 21.17 | 21.17 | 0
G.2 | Direct Unit Cost (E.2 + F.2) - As Evaluated
H.1 | Overhead, Contingencies & Miscellaneous (OCM) - As Submitted |  |  |  |  | 12% | 2.5404
H.2 | Overhead, Contingencies & Miscellaneous (OCM) - As Evaluated
I.1 | Contractor's Profit (CP) - As Submitted |  |  |  |  | 8% | 1.6936
I.2 | Contractor's Profit (CP) - As Evaluated
J.1 | Value Added Tax (VAT) - As Submitted |  |  |  |  | 5% | 1.2702
J.2 | Value Added Tax (VAT) - As Evaluated
K.1 | Total Unit Cost - As Submitted |  |  |  |  | (G.1+H.1+I.1+J.1) | 26.67
K.2 | Total Unit Cost - As Evaluated
Note: Prices/Rates were based on CMPD 4TH Quarter CY 2022 for Materials, Memorandum dated December 29, 2022 for Labor cost and Memorandum dated May 18, 2022 for Equipment rental including Fuel & Oil/Lubricant cost as of January 4, 2023 for DPWH Regional/District Engineering Offices
Prepared by: | [5 empty] | Checked by:
WINLOVE A. ESTEVES | [5 empty] | MARK ANGELO E. SURIL
Engineer II | [5 empty] | Engineer II
DPWH-ADEO | [5 empty] | DPWH-ADEO

## 200(1)
FORM-POW-2015-01D-00
Item No. / Description |  |  | : | 200(1) | Aggregate Subbase Course
Unit of Measurement |  |  | : | cum
Output per hour - As Submitted |  |  | : | 50
Output per hour - As Evaluated |  |  | :
A.1 | Designation |  |  | No. of Person/s | No. of Hour/s | Hourly Rate | Amount (PhP)
Labor
| a. | Construction Foreman |  | 1 | 1 | 110.65 | 110.65
| b. | Unskilled Laborer |  | 2 | 1 | 61.75 | 123.5
| Sub - Total for A.1 - As Submitted | [5 empty] | 234.15 | 4.68
A.2 | Labor
Sub - Total for A.2 - As Evaluated
B.1 | Name and Capacity |  |  | No. of Unit/s | No. of Hour/s | Hourly Rate | Amount (Php)
Equipment
| a. | Motorized Road Grader, G710A (140 hp) |  | 1 | 1 | 2664.75 | 2664.75
| b. | Vibratory Roller, SD100DC (10mt, 125 hp) |  | 1 | 1 | 2396.78 | 2396.78
| c. | Water Truck/Pump (16000 L, 360 hp) |  | 1 | 0.25 | 4217.31 | 1054.3275
| Sub - Total for B.1 - As Submitted | [5 empty] | 6115.8575 | 122.32
B.2 | Equipment
Sub - Total for B.2 - As Evaluated
C.1 | Total (A.1 + B.1) - As Submitted | [5 empty] | 6350.0075
C.2 | Total (A.2+ B.2) - As Evaluated
D.1 | Output per hour - As Submitted | [5 empty] | 50
D.2 | Output per hour - As Evaluated
E.1 | Direct Unit Cost (C.1 ÷ D.1) - As Submitted | [5 empty] | 127.0002
E.2 | Direct Unit Cost (C.1 ÷ D.1) - As Evaluated
F.1 | Name and Specification |  |  | Unit | Quantity | Unit Cost | Amount (PhP)
Materials
| a. Aggregate Subbase Course |  |  | cum | 1.15 | 470 | 540.5
(w/ 15% Shrinkage Factor)
| Sub - Total for F.1 - As Submitted | [5 empty] | 540.5 | 540.5
F.2 | Materials
Sub - Total for F.2 - As Evaluated
G.1 | Direct Unit Cost (E.1 + F.1) - As Submitted | [5 empty] | 667.5 | 667.5 | 0
G.2 | Direct Unit Cost (E.2 + F.2) - As Evaluated
H.1 | Overhead, Contingencies & Miscellaneous (OCM) - As Submitted |  |  |  |  | 12% | 80.1
H.2 | Overhead, Contingencies & Miscellaneous (OCM) - As Evaluated
I.1 | Contractor's Profit (CP) - As Submitted |  |  |  |  | 8% | 53.4
I.2 | Contractor's Profit (CP) - As Evaluated
J.1 | Value Added Tax (VAT) - As Submitted |  |  |  |  | 5% | 40.05
J.2 | Value Added Tax (VAT) - As Evaluated
K.1 | Total Unit Cost - As Submitted |  |  |  |  | (G.1+H.1+I.1+J.1) | 841.05
K.2 | Total Unit Cost - As Evaluated
Note: Prices/Rates were based on CMPD 4TH Quarter CY 2022 for Materials, Memorandum dated December 29, 2022 for Labor cost and Memorandum dated May 18, 2022 for Equipment rental including Fuel & Oil/Lubricant cost as of January 4, 2023 for DPWH Regional/District Engineering Offices
Prepared by: | [5 empty] | Checked by:
WINLOVE A. ESTEVES | [5 empty] | MARK ANGELO E. SURIL
Engineer II | [5 empty] | Engineer II
DPWH-ADEO | [5 empty] | DPWH-ADEO

## 311(1)b1
FORM-POW-2015-01D-00
Item No. / Description |  |  | : | 311(1)b1 | Portland Cement Concrete Pavement (Unreinforced, 0.20m thick, 14 days)
Unit of Measurement |  |  | : | sqm
Output per hour - As Submitted |  |  | : | 80.5
Output per hour - As Evaluated |  |  | :
A.1 | Designation |  |  | No. of Person/s | No. of Hour/s | Hourly Rate | Amount (PhP)
Labor
| a. | Construction Foreman |  | 1 | 1 | 110.65 | 110.65
| b. | Skilled Laborer |  | 4 | 1 | 80.05 | 320.2
| c. | Unskilled Laborer |  | 12 | 1 | 61.75 | 741
| Sub - Total for A.1 - As Submitted | [5 empty] | 1171.85 | 14.56 | 14.5571 | 0.0028571
A.2 | Labor
| Sub - Total for A.2 - As Evaluated | [5 empty] | 0
B.1 | Name and Capacity |  |  | No. of Unit/s | No. of Hour/s | Hourly Rate | Amount (Php)
Equipment
| a. | Transit Mixer (175 hp) |  | 4 | 1 | 2276.68 | 9106.72
| b. | Concrete Vibrator |  | 2 | 1 | 57.17 | 114.34
| c. | Concrete Batch Plant |  | 1 | 1 | 1759.5 | 1759.5
| d. | Payloader, LX80-2C (1.50m³, 110 hp) |  | 1 | 1 | 2114.8 | 2114.8
| e. | Concrete Screeder (5.50 hp) |  | 1 | 1 | 490.01 | 490.01
| f. | Water Truck/Pump (16000 L, 360 hp) |  | 1 | 1 | 4217.31 | 4217.31
| g. | Concrete Saw, 14" Blade ø (7.5 hp) |  | 1 | 1 | 77.63 | 77.63
| h. | Bar Cutter, Single Phase |  | 1 | 0.1 | 105.47 | 10.547
| i. | Joint Sealer |  | 1 | 0.1 | 84.55 | 8.455
| Minor Tools (5% of Labor Cost) | [5 empty] | 58.5925 | 5%
| Sub - Total for B.1 - As Submitted | [5 empty] | 17957.9045 | 223.07 | 223.0796 | -0.009559
B.2 | Equipment
| Sub - Total for B.2 - As Evaluated | [5 empty] | 0
C.1 | Total (A.1 + B.1) - As Submitted | [5 empty] | 19129.7545
C.2 | Total (A.2+ B.2) - As Evaluated
D.1 | Output per hour - As Submitted | [5 empty] | 80.5
D.2 | Output per hour - As Evaluated
E.1 | Direct Unit Cost (C.1 ÷ D.1) - As Submitted | [5 empty] | 237.6367
E.2 | Direct Unit Cost (C.1 ÷ D.1) - As Evaluated
F.1 | Name and Specification |  |  | Unit | Quantity | Unit Cost | Amount (PhP)
Materials
| a. Reinforcing Steel Bar (1.75 factor) |  |  | kg | 0.39 | 41 | 15.99
| b. Curing Compound |  |  | L | 0.29 | 76 | 22.04
| c. Asphalt Sealant (Asphalt Emulsified Cationic SS1) |  |  | L | 0.12 | 68.5 | 8.22
| d. Steel Forms (Rental) |  |  | m | 0.46 | 62 | 28.52
| e. Sand (Fine Aggregate) |  |  | cum | 0.11 | 400 | 44
| f. Gravel (2 1/2"), (Natural Gravel) |  |  | cum | 0.2 | 570 | 114
| g. Cement |  |  | bag | 1.9 | 260 | 494
| h. Concrete Saw (diamond blade 14") |  |  | pc | 0.00015 | 8000 | 1.2
| i. Pipe Sleeve, 1.50" dia. |  |  | m | 0.0086 | 210 | 1.806
| j. Grease / Tar |  |  | L | 0.0056 | 250 | 1.4
Hauling Cost
| a. Reinforcing Steel Bar (1.75 factor) |  |  | kg | 0.39 | 4.1 | 1.599
| Sub - Total for F.1 - As Submitted | [5 empty] | 732.775 | 732.78
F.2 | Materials
| Sub - Total for F.2 - As Evaluated | [5 empty] | 0
G.1 | Direct Unit Cost (E.1 + F.1) - As Submitted | [5 empty] | 970.41 | 970.41 | 0
G.2 | Direct Unit Cost (E.2 + F.2) - As Evaluated
H.1 | Overhead, Contingencies & Miscellaneous (OCM) - As Submitted |  |  |  |  | 12% | 116.4492
H.2 | Overhead, Contingencies & Miscellaneous (OCM) - As Evaluated
I.1 | Contractor's Profit (CP) - As Submitted |  |  |  |  | 8% | 77.6328
I.2 | Contractor's Profit (CP) - As Evaluated
J.1 | Value Added Tax (VAT) - As Submitted |  |  |  |  | 5% | 58.2246
J.2 | Value Added Tax (VAT) - As Evaluated
K.1 | Total Unit Cost - As Submitted |  |  |  |  | (G.1+H.1+I.1+J.1) | 1222.72
K.2 | Total Unit Cost - As Evaluated
Note: Prices/Rates were based on CMPD 4TH Quarter CY 2022 for Materials, Memorandum dated December 29, 2022 for Labor cost and Memorandum dated May 18, 2022 for Equipment rental including Fuel & Oil/Lubricant cost as of January 4, 2023 for DPWH Regional/District Engineering Offices
Prepared by: | [5 empty] | Checked by:
WINLOVE A. ESTEVES | [5 empty] | MARK ANGELO E. SURIL
Engineer II | [5 empty] | Engineer II
DPWH-ADEO | [5 empty] | DPWH-ADEO

## 404(1)a
FORM-POW-2015-01D-00
Item No. / Description |  |  | : | 404(1)a | Reinforcing Steel (Grade 40)
Unit of Measurement |  |  | : | kg
Output per hour - As Submitted |  |  | : | 180
Output per hour - As Evaluated |  |  | :
A.1 | Designation |  |  | No. of Person/s | No. of Hour/s | Hourly Rate | Amount (PhP)
Labor
| a. | Construction Foreman |  | 1 | 1 | 110.65 | 110.65
| b. | Skilled Laborer |  | 2 | 1 | 80.05 | 160.1
| c. | Unskilled Laborer |  | 8 | 1 | 61.75 | 494
| Sub - Total for A.1 - As Submitted | [5 empty] | 764.75 | 4.25 | 4.2486 | 0.0013889
A.2 | Labor
| Sub - Total for A.2 - As Evaluated | [5 empty] | 0
B.1 | Name and Capacity |  |  | No. of Unit/s | No. of Hour/s | Hourly Rate | Amount (Php)
Equipment
| a. | Bar Cutter, Single Phase |  | 1 | 0.5 | 105.47 | 52.735
| b. | Bar Bender, Three Phase |  | 1 | 0.5 | 168.75 | 84.375
| c. | Cargo/Service Truck (9-10mt, 270 hp) |  | 1 | 0.15 | 2544.47 | 381.6705
| Sub - Total for B.1 - As Submitted | [5 empty] | 518.7805 | 2.88 | 2.8821 | -0.0021139
B.2 | Equipment
| Sub - Total for B.2 - As Evaluated | [5 empty] | 0
C.1 | Total (A.1 + B.1) - As Submitted | [5 empty] | 1283.5305
C.2 | Total (A.2+ B.2) - As Evaluated
D.1 | Output per hour - As Submitted | [5 empty] | 180
D.2 | Output per hour - As Evaluated
E.1 | Direct Unit Cost (C.1 ÷ D.1) - As Submitted | [5 empty] | 7.1307
E.2 | Direct Unit Cost (C.1 ÷ D.1) - As Evaluated
F.1 | Name and Specification |  |  | Unit | Quantity | Unit Cost | Amount (PhP)
Materials
| a. Tie Wire (2% of RSB) |  |  | kg | 0.021 | 85 | 1.785
| b. Reinforcing Steel Bar, Grade 40 |  |  | kg | 1.05 | 41 | 43.05
(w/ 5% Wastage)
Hauling Cost
| b. Reinforcing Steel Bar, Grade 40 |  |  | kg | 1.05 | 4.1 | 4.305
| Sub - Total for F.1 - As Submitted | [5 empty] | 49.14 | 49.14
F.2 | Materials
| Sub - Total for F.2 - As Evaluated | [5 empty] | 0
G.1 | Direct Unit Cost (E.1 + F.1) - As Submitted | [5 empty] | 56.27 | 56.27 | 0
G.2 | Direct Unit Cost (E.2 + F.2) - As Evaluated
H.1 | Overhead, Contingencies & Miscellaneous (OCM) - As Submitted |  |  |  |  | 12% | 6.7524
H.2 | Overhead, Contingencies & Miscellaneous (OCM) - As Evaluated
I.1 | Contractor's Profit (CP) - As Submitted |  |  |  |  | 8% | 4.5016
I.2 | Contractor's Profit (CP) - As Evaluated
J.1 | Value Added Tax (VAT) - As Submitted |  |  |  |  | 5% | 3.3762
J.2 | Value Added Tax (VAT) - As Evaluated
K.1 | Total Unit Cost - As Submitted |  |  |  |  | (G.1+H.1+I.1+J.1) | 70.9
K.2 | Total Unit Cost - As Evaluated
Note: Prices/Rates were based on CMPD 4TH Quarter CY 2022 for Materials, Memorandum dated December 29, 2022 for Labor cost and Memorandum dated May 18, 2022 for Equipment rental including Fuel & Oil/Lubricant cost as of January 4, 2023 for DPWH Regional/District Engineering Offices
Prepared by: | [5 empty] | Checked by:
WINLOVE A. ESTEVES | [5 empty] | MARK ANGELO E. SURIL
Engineer II | [5 empty] | Engineer II
DPWH-ADEO | [5 empty] | DPWH-ADEO

## 405(1)a3
FORM-POW-2015-01D-00
Item No. / Description |  |  | : | 405(1)a3 | Structural Concrete, 20.68 Mpa, Class A, 28 days
Unit of Measurement |  |  | : | cum
Output per hour - As Submitted |  |  | : | 1.4
Output per hour - As Evaluated |  |  | :
A.1 | Designation |  |  | No. of Person/s | No. of Hour/s | Hourly Rate | Amount (PhP)
Labor
| a. | Construction Foreman |  | 1 | 1 | 110.65 | 110.65
| b. | Skilled Laborer |  | 4 | 1 | 80.05 | 320.2
| c. | Unskilled Laborer |  | 8 | 1 | 61.75 | 494
Installation & Removal of Formworks
| a. | Skilled Laborer |  | 4 | 1 | 80.05 | 320.2
| b. | Unskilled Laborer |  | 8 | 1 | 61.75 | 494
| Sub - Total for A.1 - As Submitted | [5 empty] | 1739.05 | 1242.18
A.2 | Labor
| Sub - Total for A.2 - As Evaluated | [5 empty] | 0
B.1 | Name and Capacity |  |  | No. of Unit/s | No. of Hour/s | Hourly Rate | Amount (Php)
Equipment
| a. | One Bagger Mixer (4-6 ft³/min) |  | 1 | 1 | 172 | 172
| b. | Concrete Vibrator |  | 1 | 1 | 57.17 | 57.17
| c. | Water Truck/Pump (16000 L, 360 hp) |  | 1 | 0.1 | 4217.31 | 421.731
| Minor Tools (5% of Labor Cost) | [5 empty] | 86.9525 | 5%
| Sub - Total for B.1 - As Submitted | [5 empty] | 737.8535 | 527.04
B.2 | Equipment
| Sub - Total for B.2 - As Evaluated | [5 empty] | 0
C.1 | Total (A.1 + B.1) - As Submitted | [5 empty] | 2476.9035
C.2 | Total (A.2+ B.2) - As Evaluated
D.1 | Output per hour - As Submitted | [5 empty] | 1.4
D.2 | Output per hour - As Evaluated
E.1 | Direct Unit Cost (C.1 ÷ D.1) - As Submitted | [5 empty] | 1769.2168
E.2 | Direct Unit Cost (C.1 ÷ D.1) - As Evaluated
F.1 | Name and Specification |  |  | Unit | Quantity | Unit Cost | Amount (PhP)
Materials
| a. Lumber, Good - 4 uses |  |  | bdft | *70.00 | 46 | 805
| b. Marine Plywood (1/2" x 4' x 8') - 4 uses |  |  | pc | *1.60 | 780 | 312
| c. Assorted CWN (1kg./100 bd.ft. of Lumber) |  |  | kg | *0.70 | 77.5 | 54.25
| d. Cement |  |  | bag | 9.5 | 260 | 2470
| e. Sand (Fine Aggregate) |  |  | cum | 0.5 | 400 | 200
| f. Gravel (Natural Gravel) |  |  | cum | 1 | 570 | 570
| Sub - Total for F.1 - As Submitted | [5 empty] | 4411.25 | 4411.25
F.2 | Materials
| Sub - Total for F.2 - As Evaluated | [5 empty] | 0
G.1 | Direct Unit Cost (E.1 + F.1) - As Submitted | [5 empty] | 6180.47 | 6180.47 | 0
G.2 | Direct Unit Cost (E.2 + F.2) - As Evaluated
H.1 | Overhead, Contingencies & Miscellaneous (OCM) - As Submitted |  |  |  |  | 12% | 741.6564
H.2 | Overhead, Contingencies & Miscellaneous (OCM) - As Evaluated
I.1 | Contractor's Profit (CP) - As Submitted |  |  |  |  | 8% | 494.4376
I.2 | Contractor's Profit (CP) - As Evaluated
J.1 | Value Added Tax (VAT) - As Submitted |  |  |  |  | 5% | 370.8282
J.2 | Value Added Tax (VAT) - As Evaluated
K.1 | Total Unit Cost - As Submitted |  |  |  |  | (G.1+H.1+I.1+J.1) | 7787.39
K.2 | Total Unit Cost - As Evaluated
Note: Prices/Rates were based on CMPD 4TH Quarter CY 2022 for Materials, Memorandum dated December 29, 2022 for Labor cost and Memorandum dated May 18, 2022 for Equipment rental including Fuel & Oil/Lubricant cost as of January 4, 2023 for DPWH Regional/District Engineering Offices
Prepared by: | [5 empty] | Checked by:
WINLOVE A. ESTEVES | [5 empty] | MARK ANGELO E. SURIL
Engineer II | [5 empty] | Engineer II
DPWH-ADEO | [5 empty] | DPWH-ADEO

## 506(1)
FORM-POW-2015-01D-00
Item No. / Description |  |  | : | 506(1) | Stone Masonry(Slope Protection)
Unit of Measurement |  |  | : | cum
Output per hour - As Submitted |  |  | : | 1.6
Output per hour - As Evaluated |  |  | :
A.1 | Designation |  |  | No. of Person/s | No. of Hour/s | Hourly Rate | Amount (PhP)
Labor
| a. | Construction Foreman |  | 1 | 1 | 110.65 | 110.65
| b. | Skilled Laborer |  | 2 | 1 | 80.05 | 160.1
| c. | Unskilled Laborer |  | 8 | 1 | 61.75 | 494
| Sub - Total for A.1 - As Submitted | [5 empty] | 764.75 | 477.9688 | 477.9688 | 0
A.2 | Labor
| Sub - Total for A.2 - As Evaluated | [5 empty] | 0
B.1 | Name and Capacity |  |  | No. of Units | No. of Hours | Hourly Rate | Amount (Php)
Equipment
| a. | One Bagger Mixer (4-6 ft³/min) |  | 1 | 1 | 172 | 172
| b. | Water Truck/Pump (16000 L, 360 hp) |  | 1 | 0.05 | 4217.31 | 210.8655
| c. | Backhoe, Wheel Mounted (0.28 m³, 50 hp) |  | 1 | 0.1 | 1073.91 | 107.391
| Minor Tools (10% of Labor Cost) | [5 empty] | 76.475 | 10%
| Sub - Total for B.1 - As Submitted | [5 empty] | 566.7315 | 354.2062 | 354.2072 | -0.0009375
B.2 | Equipment
| Sub - Total for B.2 - As Evaluated | [5 empty] | 0
C.1 | Total (A.1 + B.1) - As Submitted | [5 empty] | 1331.4815
C.2 | Total (A.2+ B.2) - As Evaluated
D.1 | Output per hour - As Submitted | [5 empty] | 1.6
D.2 | Output per hour - As Evaluated
E.1 | Direct Unit Cost (C.1 ÷ D.1) - As Submitted | [5 empty] | 832.1759
E.2 | Direct Unit Cost (C.1 ÷ D.1) - As Evaluated
F.1 | Name and Specification |  |  | Unit | Quantity | Unit Cost | Amount (PhP)
Materials
| a. Cement |  |  | bag | 5.5 | 260 | 1430
| b. Sand (Fine Aggregate) |  |  | cum | 0.3 | 400 | 120
| c. Gravel Fill (Natural Gravel) |  |  | cum | 0.02 | 570 | 11.4
| d. Weep Holes (PVC) 3" dia. |  |  | l.m. | 0.3 | 146.6667 | 44
| e. Filter Cloth |  |  | sqm | 0.015 | 177 | 2.655
| f. Boulders |  |  | cum | 1.05 | 700 | 735
| Sub - Total for F.1 - As Submitted | [5 empty] | 2343.055 | 2343.055 | 2343.055 | 0
F.2 | Materials
Sub - Total for F.2 - As Evaluated
G.1 | Direct Unit Cost (E.1 + F.1) - As Submitted | [5 empty] | 3175.23 | 3175.23 | 0
G.2 | Direct Unit Cost (E.2 + F.2) - As Evaluated
H.1 | Overhead, Contingencies & Miscellaneous (OCM) - As Submitted |  |  |  |  | 12% | 381.03
H.2 | Overhead, Contingencies & Miscellaneous (OCM) - As Evaluated
I.1 | Contractor's Profit (CP) - As Submitted |  |  |  |  | 8% | 254.02
I.2 | Contractor's Profit (CP) - As Evaluated
J.1 | Value Added Tax (VAT) - As Submitted |  |  |  |  | 5% | 190.51
J.2 | Value Added Tax (VAT) - As Evaluated
K.1 | Total Unit Cost - As Submitted |  |  |  |  | (G.1+H.1+I.1+J.1) | 4000.79
K.2 | Total Unit Cost - As Evaluated
Note: Prices/Rates were based on CMPD 4TH Quarter CY 2022 for Materials, Memorandum dated December 29, 2022 for Labor cost and Memorandum dated May 18, 2022 for Equipment rental including Fuel & Oil/Lubricant cost as of January 4, 2023 for DPWH Regional/District Engineering Offices | [10 empty] | 133.3333
Prepared by: | [5 empty] | Checked by:
WINLOVE A. ESTEVES | [5 empty] | MARK ANGELO E. SURIL
Engineer II | [5 empty] | Engineer II
Planning and Design Section | [5 empty] | Planning and Design Section
DPWH-ADEO | [5 empty] | DPWH-ADEO
Note: Prices of Material were based on CMPD 3rd Quarter 2019 and Labor based on 2019 rates for DPWH Regional/District Offices

## 611(1)
FORM-POW-2015-01D-00
Item No. / Description |  |  | : | 611(1) | Trees Furnishing and Transplanting (Seedling Only)
Unit of Measurement |  |  | : | ea
Output per hour - As Submitted |  |  | : | 1
Output per hour - As Evaluated |  |  | :
A.1 | Designation |  |  | No. of Person/s | No. of Hour/s | Hourly Rate | Amount (PhP)
Labor
| a. | Unskilled Laborer |  | 2 | 0.33 | 61.75 | 40.755
Note: Including 3 years Maintenance
Maintenance and Protection (Hectare)
1st year - 1000/ha.
2nd year - 5000/ha.
3rd year - 5000/ha.
(based on Computation of DENR-CENRO)
| Sub - Total for A.1 - As Submitted | [5 empty] | 40.755 | 40.76 | 40.755 | 0.005
A.2 | Labor
| Sub - Total for A.2 - As Evaluated | [5 empty] | 0
B.1 | Name and Capacity |  |  | No. of Units | No. of Hours | Hourly Rate | Amount (Php)
Equipment
| Minor Tools (5% of Labor Cost) | [5 empty] | 2.0378 | 5%
| Sub - Total for B.1 - As Submitted | [5 empty] | 2.0378 | 2.03 | 2.0378 | -0.00775
B.2 | Equipment
| Sub - Total for B.2 - As Evaluated | [5 empty] | 0
C.1 | Total (A.1 + B.1) - As Submitted | [5 empty] | 42.7928
C.2 | Total (A.2+ B.2) - As Evaluated
D.1 | Output per hour - As Submitted | [5 empty] | 1
D.2 | Output per hour - As Evaluated
E.1 | Direct Unit Cost (C.1 ÷ D.1) - As Submitted | [5 empty] | 42.7928
E.2 | Direct Unit Cost (C.1 ÷ D.1) - As Evaluated
F.1 | Name and Specification |  |  | Unit | Quantity | Unit Cost | Amount (PhP)
Materials
| a. Seedling (Delivered at Site) |  |  | pc | 1 | 12 | 12
Note: 1 tree (cut/removed = 50 seedlings to replace)
30 trees = 1500 seedlings
| Sub - Total for F.1 - As Submitted | [5 empty] | 12 | 12 | 12 | 0
F.2 | Materials
Sub - Total for F.2 - As Evaluated
G.1 | Direct Unit Cost (E.1 + F.1) - As Submitted | [5 empty] | 54.79 | 54.79 | 0
G.2 | Direct Unit Cost (E.2 + F.2) - As Evaluated
H.1 | Overhead, Contingencies & Miscellaneous (OCM) - As Submitted |  |  |  |  | 12% | 6.5748
H.2 | Overhead, Contingencies & Miscellaneous (OCM) - As Evaluated
I.1 | Contractor's Profit (CP) - As Submitted |  |  |  |  | 8% | 4.3832
I.2 | Contractor's Profit (CP) - As Evaluated
J.1 | Value Added Tax (VAT) - As Submitted |  |  |  |  | 5% | 3.29
J.2 | Value Added Tax (VAT) - As Evaluated
K.1 | Total Unit Cost - As Submitted |  |  |  |  | (G.1+H.1+I.1+J.1) | 69.04
K.2 | Total Unit Cost - As Evaluated
Note: Prices/Rates were based on CMPD 4TH Quarter CY 2022 for Materials, Memorandum dated December 29, 2022 for Labor cost and Memorandum dated May 18, 2022 for Equipment rental including Fuel & Oil/Lubricant cost as of January 4, 2023 for DPWH Regional/District Engineering Offices | [10 empty] | 133.3333
Prepared by: | [5 empty] | Checked by:
WINLOVE A. ESTEVES | [5 empty] | MARK ANGELO E. SURIL
Engineer II | [5 empty] | Engineer II
Planning and Design Section | [5 empty] | Planning and Design Section
DPWH-ADEO | [5 empty] | DPWH-ADEO
Note: Prices of Material were based on CMPD 3rd Quarter 2019 and Labor based on 2019 rates for DPWH Regional/District Offices

## PRICE_LIST
MATERIALS |  |  |  |  | EQUIPMENTS |  |  |  | LABOR |  |  |  |  | 7801031.85
CODE | DESCRIPTION | UNIT | PRICE | REMARKS | DESCRIPTION | UNIT | RENTAL RATE | REMARKS | DESCRIPTION | RATE | UNIT | Cement Hauling Cost | 2 | DIRECT COST | OCM | CP | VAT
| 8' x 8' Tarpaulin | sqm | 50 |  | Rental of Field Office w/ complete facilities | monthly | 5000 |  | Construction Foreman | 110.65 | hourly | RSB Hauling Cost | 4.1 | 0 < DC ≤ 5M | 15% | 10% | 5% | 25%
| Asphalt Sealant | L | 44 |  | Low Bed Trailer |  | 10815 |  | Skilled Laborer | 80.05 | hourly |  |  | 5M < DC ≤ 50M | 12% | 8% | 5% | 20%
| Concrete Saw (diamond blade 14") | pc | 8000 |  | Backhoe, Wheel Mounted (0.28 m³, 50 hp) |  | 1073.91 |  | Unskilled Laborer | 61.75 | hourly |  |  | 50M < DC ≤ 150M | 10% | 8% | 5% | 18%
M104.0000 | EMBANKMENT |  |  |  | Backhoe, SOLAR 220 LC-3 (0.80 m³,138 hp) |  | 2588.75 | [6 empty] | DC > 150M | 8% | 8% | 5% | 16%
M104.0001 | Common Borrow | cum | 340 |  | Backhoe with Breaker, SOLAR 220 LC-3 (0.80 m³, 138 hp) |  | 3117.05 |  | Safety Officer (Part Time) | 885.2 | daily
M104.0003 | Mixed Sand & Gravel | cum | 360 |  | Boom Truck, NXG1160D3ZAL1X (197 hp) |  | 2859.64 |  | Health Personnel (Full Time First Aider) | 640.4 | daily
M104.0004 | Rock | cum | 570 |  | Bulldozer, DX175 (167 hp) |  | 4060.69 |  | Sanitation Aide (Part Time) | 494 | daily
M200.0000 | AGGREGATE SUBBASE COURSE |  |  |  | Bulldozer with Ripper, DX175 (167 hp) |  | 4519.54 |  | Traffic Officer/ Flag Man | 494 | daily
M200.0001 | Aggregate Subbase Course Material | cum | 470 |  | Payloader, LX80-2C (1.50m³, 110 hp) |  | 2114.8
M201.0000 | AGGREGATE BASE COURSE |  |  |  | Payloader, LX80-2C (1.50m³, 110 hp) - at disposal area |  | 2114.8
M201.0001 | Crushed Grading A | cum | 550 |  | Dump Truck (12 yd³, 290 hp) |  | 2932.45
M201.0002 | Uncrushed Grading A | cum | 420 |  | Motorized Road Grader, G710A (140 hp) |  | 2664.75
M311.0000 | PORTLAND CEMENT CONCRETE PAVEMENT |  |  |  | Vibratory Roller, SD100DC (10mt, 125 hp) |  | 2396.78
M311.0001 | Ready Mix Concrete 3000psi @ 28 days | cum | 3500 |  | Water Truck/Pump (16000 L, 360 hp) |  | 4217.31
M311.0009 | Ready Mix Concrete 4000psi @ 28 days | cum | 3900 |  | Transit Mixer (175 hp) |  | 2276.68
M311.0012 | Ready Mix Concrete 5000psi @ 28 days | cum | 4400 |  | Concrete Vibrator |  | 57.17
M311.0013 | Curing Compound | L | 76 |  | Concrete Batch Plant |  | 1759.5
M311.0015 | Steel Forms 15 cm width | m | 50 |  | Concrete Screeder (5.50 hp) |  | 490.01
M311.0016 | Steel Forms 20 cm width | m | 62 |  | Concrete Saw, 14" Blade ø (7.5 hp) |  | 77.63
M311.0017 | Steel Forms 23 cm width | m | 75 |  | Bar Cutter, Single Phase |  | 105.47
M400.0000 | PILING |  |  |  | Bar Bender, Three Phase |  | 168.75
M400.0007 | Steel Sheet Piles Fy36 | kg | 53 |  | Cargo/Service Truck (2-5mt, 160 hp) |  | 1557.7
M400.0008 | Steel Sheet Piles Fy50 | kg | 54 |  | Cargo/Service Truck (9-10mt, 270 hp) |  | 2544.47
M400.0025 | Steel Casing 10mm thick @ 1000mm Dia. | m | 15605 |  | One Bagger Mixer (4-6 ft³/min) |  | 172
M400.0030 | Steel Casing 10mm thick @ 1500mm Dia. | m | 22790 |  | Plate Compactor (5 hp) |  | 153.01
M400.0031 | Steel Casing 10mm thick @ 1600mm Dia. | m | 24966 |  | Vibro Hammer, Hydraulic Pile Driver (60 ton, 201 hp) |  | 2989.63
M400.0033 | Steel Casing 10mm thick @ 1800mm Dia. | m | 28330 |  | Cutting Outfit |  | 45.45
M400.0038 | Steel Casing | kg | 65 |  | Chain Saw |  | 75.36
| Steel Casing 12mm thick @ 1600mm Dia. | m | 29959.2 |  | Drilling Rig (300 hp) |  | 12414.43
| Steel Casing 12mm thick @ 1800mm Dia. | m | 33996 | 34856 | Crawler Crane (36-40 mt, 190 hp) |  | 2837.64
M400.0039 | Acetylene | kg | 65 |  | Crawler Crane with Bucket (36-40 mt, 190 hp) |  | 3177.24
M400.0042 | Oxygen | kg | 57 |  | Crawler Crane (41-45 mt, 190 hp) |  | 3059.64
M400.0046 | Welding Rod | kg | 122.5 |  | Crawler Crane (21-25 mt, 145 hp) |  | 2228.72
M403.0000 | METAL STRUCTURES |  |  |  | Generator Set (300 kW) |  | 3284.98
M403.0001 | Milled Steel Plates Checkered FY36 | kg | 0 |  | Generator Set (900 kW) |  | 9895.75
M403.0007 | Structural Steel Angular Bar (A36) | kg | 0 |  | Bentonite Bin |  | 280
M403.0008 | Structural Steel Channel Bar (A36) | kg | 69 |  | Bentonite Mixer |  | 173
M403.0011 | Structural Steel Wide Flange (A36) | kg | 0 |  | Water Pump, 100mm suction Ø (7.5 hp) |  | 168.37
M404.0000 | REINFORCING STEEL |  |  |  | Welding Machine, Gas/Diesel Driven (300A, 48 hp) |  | 598.93
M404.0003 | Reinforcing Steel Bars Deformed Grade 40 | kg | 41 |  | Welding Machine, Gas/Diesel Driven (500A, 70 hp) |  | 872.86
M404.0004 | Reinforcing Steel Bars Deformed Grade 60 | kg | 42 |  | Welding Machine, Electric Driven (500A) |  | 391
M404.0006 | GI Tie Wire #16 | kg | 85 |  | Tremie Pipe Set |  | 320
M405.0000 | STRUCTURAL CONCRETE |  |  |  | SPT & Desanding Machine |  | 559
M405.0002 | Common Nails Assorted | kg | 77.5 |  | Portable Breaker, BHF30s (4 hp) |  | 147.19
M405.0010 | Gravel G3/4 | cum | 630 |  | Air Compressor (126-160 cfm, 51 hp) |  | 666.93
M405.0011 | Fine Aggregate | cum | 400 |  | Tower Lights |  | 260.86
M405.0012 | Natural Gravel | cum | 570 |  | Pile Integrity Testing (Sonic) and Accessories |  | 37000
M405.0013 | Lumber Coco | bdft | 21 |  | Dynamic Pile Testing |  | 103000
M405.0014 | Lumber Good | bdft | 46 |  | Truck Mounted Crane (31-35 mt, 238 hp) |  | 2968.57
M405.0018 | Plywood Marine (0.00625m x 1.2m x 2.44m) | pc | 420 | 1/4" x 4' x 8' | Truck Mounted Crane (41-45 mt, 246 hp) |  | 3233.53
M405.0019 | Plywood Marine (0.0125m x 1.2m x 2.44m) | pc | 780 | 1/2" x 4' x 8' | Truck Mounted Crane with Bucket (41-45 mt, 246 hp) |  | 3585.13
M406.0000 | PRESTRESSED CONCRETE STRUCTURES |  |  |  | Truck Mounted Crane (51-60 mt, 280 hp) |  | 4141.47
M406.0009 | Prestressed Concrete Anchorage Assembly | set | 1850 |  | Drop Hammer w/ accessories |  | 5000
M406.0010 | Prestressed Concrete Wire Strand 12.70mm | kg | 57 |  | 1 Air Compressor w/ 2 Jack Hammer |  | 1265
M406.0011 | Duct Tube Galvanized Metal 50mm | m | 275 |  | Stressing (Jack) Machine |  | 2500
M406.0012 | Rubber Hose 12.7mm | m | 40 |  | Grouting Machine, Air Driven |  | 866.25
M406.0013 | Packaging Tape 50mm (Industrial Type) | pc | 75 |  | Wood/Steel Ladder |  | 100
M412.0000 | ELASTOMERIC BEARING PAD |  |  |  | Applicator Machine |  | 93.75
M412.0001 | Elastomeric Plain Bearing Pad | pc | 6300 | 8' x 4' x 1" | Kneading Machine |  | 187.5
M412.0002 | Elastomeric Bearing Pad 1-pc 1-Metal | pc | 10500 |  | Dolly |  | 1249
M412.0003 | Elastomeric Bearing Pad 1-pc 2-Metal | pc | 16500 |  | Crawler Crane (51-60 mt, 275 hp) |  | 4129.47
M500.0000 | PIPE CULVERTS AND STORM DRAINS |  |  |  | Vibro Hammer w/ Hydraulic Power Pack |  | 4790.6
M500.0005 | Reinforced Concrete Pipe Class II Dia 36" (910mm) | pc | 2635 |  | Vibro Hammer (272.22 hp) |  | 4210.81
M502.0000 | MANHOLES, INLETS AND CATCH BASINS
M502. 0003 | CHB Ordinary (101mm x 203mm x 406mm) | pc | 18
M505.0000 | RIPRAP & GROUTED RIPRAP |  |  |  | Asphalt Distributor, ROSCO/5 ton (3000 USG, 100 hp) |  | 1385.82
M505.0001 | Riprap, Class A | cum | 650 |  | Power Broom (2.0m wide) |  | 130.54
M506.0000 | STONE MASONRY |  |  |  | Asphalt Paver (80 hp) |  | 2018.87
M506.0001 | Stone Masonry | cum | 700 |  | Pneumatic Tire Roller ( 10 mt, 107 hp) |  | 1171.8
M511.0000 | GABIONS AND MATTRESSES |  |  |  | Tandem Steel Roller, HD110 (11 mt, 134 hp) |  | 2642.76
M511.0003 | Gabions Metallic Coated, 1.0 x 1.0 x 2.0m | pc | 2480 |  | Jackhammer |  | 150
M511.0011 | Mattress Metallic Coated 0.30 x 2.0 x 6.0m | pc | 3800 |  | Air Compressor, (356-450 cfm, 130 hp) |  | 1551.78
M511.0013 | Filter Cloth | sqm | 177 |  | Joint Sealer |  | 84.55
M602.0000 | MONUMENTS, MARKERS AND GUIDE POSTS
M602.0005 | GI Pipe Schedule 40 Dia (25.4mm) | pc | 830 | 1"
M602.0006 | GI Pipe Schedule 40 Dia (38mm) | pc | 1350 | 1.5"
M602.0007 | GI Pipe Schedule 40 Dia (50.8mm) | pc | 1840 | 2"
M602.0008 | GI Pipe Schedule 40 Dia (76mm) | pc | 3140 | 3"
M603.0000 | GUARDRAIL
M603.0010 | Metal Beam End Piece | pc | 1575
M603.0011 | Guardrail Metal Beam (355mm) width | m | 2100
M603.0016 | Guardrail Bolt Nut & Washer (16mm dia x 25.40) | pc | 35 | 5/8" dia x 1"
M603.0017 | Guardrail Bolt Nut & Washer (16mm dia x 152) | pc | 85 | 5/8" dia x 6"
M603.0018 | Guardrail Bolt Nut & Washer (16mm dia x 229) | pc | 95 | 5/8" dia x 9"
M606.0000 | PAVEMENT MARKINGS
M606.0001 | Glass Beads (Pre-Mix) | bag | 680
M606.0002 | Primer White | L | 132
M606.0003 | Primer Yellow | L | 132
M606.0004 | LPG Cylinder | kg | 65
M606.0005 | Paint Rollers (152mm) | pc | 98
M606.0006 | Paint Thermoplastic White | bag | 1490
M606.0007 | Paint Thermoplastic Yellow | bag | 1540
M606.0008 | Reflectorized Traffic Paint White | L | 461
M606.0009 | Reflectorized Traffic Paint Yellow | L | 481
M700.0000 | HYDRAULIC CEMENT
M700.0002 | Portland Cement | bag | 260
M702.0000 | BITUMINOUS MATERIALS
M702.0017 | Asphalt Emulsified Cationic SS1 | mton | 68500
M708.0000 | CONCRETE CURING MATERIALS AND ADMIXTURES
M708.0001 | Concrete Admixture Accelerating | L | 137
M709.0000 | PAINTS
M709.0004 | Paint Latex Gloss | gal | 710
M900.0000 | CHEMICALS AND TERMITE CONTROL PESTICIDE
M900.0001 | Concrete Neutralizer | L | 53
M900.0010 | Greasing | L | 250
M1002.0000 | PLUMBING AND FIXTURES
M1002.0001 | Water Closet Including Fitting and Acc. (Elongated) American Std or Equivalent | set | 8980
M1002.0005 | Bronze Faucets (12.7mm D) | pc | 180
M1002.0008 | G.I. Pipes (25.4mm D) | pc | 840 | 1"
M1002.0009 | G.I. Pipes (38mm D) | pc | 1260 | 1.5"
M1002.0010 | G.I. Pipes (50mm D) | pc | 1680 | 2"
M1002.0012 | G.I. Pipes (76mm D) | pc | 3040 | 3" dia
M1002.0070 | PVC Pipes (76mm D) | pc | 440 | 3" dia
M1004.0000 | HARDWARE
M1004.0011 | Sand Paper | roll | 1830
M1013.0000 | METAL ROOFING
M1013.0001 | Corrugated Roofing, Gauge 26 (0.551mm x 2.44m) | sqm | 375
M1013.0009 | Ordinary Ridge Roll, GA 24 (0.701mm x 2.44) | m | 110
OTHERS
| Bituminous Concrete Surface Course (50mm thk) | mt | 11120
| Patching Compound | gal | 850
| Neutralizer | gal | 630
| Sand Paper | pc | 15
| GI Bolts w/ Nuts & washer, 5mm dia | pc | 59
| GI Bolts w/ Nuts & washer, 2mm dia | pc | 35
| Sign Face, 3mm thk Auminum Sheet | pc | 1700
| Rope 1" Ø | m | 120

## Equipments
LIST OF EQUIPMENT ADOPTED IN THE STANDARD DUPA FOR ROAD, BRIDGE AND BUILDING (LOW AND HIGH RISE) CONSTRUCTION COST ESTIMATION MANUALS WITH MAKE, MODEL, CAPACITY AND OPERATED RENTAL RATE PER HOUR BASED ON THE PREVAILING ACEL EQUIPMENT GUIDEBOOK, EDITION 26
1. EARTHMOVING EQUIPMENT | [8 empty] | FUEL CONSUMPTION (L/hr) | [6 empty] | OIL/LUBRICANTS (L/hr) | [6 empty] | RENTAL RATE/ OPERATED WITH FUEL & OIL/LUBRICANT
DESCRIPTION |  | MODEL | CAPACITY | FLYWHEEL HORSEPOWER | RENTAL RATE/ OPERATED |  | RENTAL RATE/ OPERATED DRY |  | LOW | AVERAGE | HIGH | *FUEL COST PER LITER |  | FUEL COST |  | LOW | AVERAGE | HIGH | *OIL/LUBRICANT COST PER LITER |  | OIL/LUBRICANT COST
1.1 | Bulldozer | DX175 |  | 167 | PhP | 3642 | PhP | 3059 | 11.2747 | 14.6571 | 18.0395 | PhP | 67.9 | PhP | 995.2171 | 0.0169 | 0.022 | 0.0271 | PhP | 294 | PhP | 6.468 | PhP | 4060.69 | 418.69 | BFClow | = | 0.0905 | L/kW-hr
1.2 | Bulldozer with Ripper | DX175 |  | 167 | PhP | 4188.3 | PhP | 3517.85 | 11.2747 | 14.6571 | 18.0395 | PhP | 67.9 | PhP | 995.2171 | 0.0169 | 0.022 | 0.0271 | PhP | 294 | PhP | 6.468 | PhP | 4519.54 | 331.24 | BFChigh | = | 0.1448 | L/kW-hr
1.3 | Payloader | LX80-2C | 1.50 m3/1.95 yd3 | 110 | PhP | 1733 | PhP | 1455 | 7.4264 | 9.6544 | 11.8823 | PhP | 67.9 | PhP | 655.5338 | 0.0111 | 0.0145 | 0.0178 | PhP | 294 | PhP | 4.263 | PhP | 2114.8 | 381.8 | HP factor | = | 0.746 | kW/hp
1.4 | Motorized Road Grader | G710A |  | 140 | PhP | 2173 | PhP | 1825 | 9.4518 | 12.2874 | 15.1229 | PhP | 67.9 | PhP | 834.3145 | 0.0142 | 0.0185 | 0.0227 | PhP | 294 | PhP | 5.439 | PhP | 2664.75 | 491.75
1.5 | Motorized Road Grader with Scarifier | G710A |  | 140 | PhP | 2824.9 | PhP | 2372.5 | 9.4518 | 12.2874 | 15.1229 | PhP | 67.9 | PhP | 834.3145 | 0.0142 | 0.0185 | 0.0227 | PhP | 294 | PhP | 5.439 | PhP | 3212.25 | 387.35 | Fuel Cost per Liter | = | 67.9
2. COMPACTION EQUIPMENT | [8 empty] | FUEL CONSUMPTION (L/hr) | [6 empty] | OIL/LUBRICANTS (L/hr) | [6 empty] | RENTAL RATE/ OPERATED WITH FUEL & OIL/LUBRICANT |  | 0 | Oil/Lubricant Cost per Liter | = | 294
DESCRIPTION |  | MODEL | CAPACITY | FLYWHEEL HORSEPOWER | RENTAL RATE/ OPERATED |  | RENTAL RATE/ OPERATED DRY |  | LOW | AVERAGE | HIGH | *FUEL COST PER LITER |  | FUEL COST |  | LOW | AVERAGE | HIGH | *OIL/LUBRICANT COST PER LITER |  | OIL/LUBRICANT COST |  |  |  | 0
2.1 | Pneumatic Tire Roller | 9-WHL, 9.00X20, 4PR | 10 mt | 107 | PhP | 561 | PhP | 530 | 7.2239 | 9.3911 | 11.5582 | PhP | 67.9 | PhP | 637.6557 | 0.0108 | 0.0141 | 0.0173 | PhP | 294 | PhP | 4.1454 | PhP | 1171.8 | 610.8
2.2 | Vibratory Roller | SD100DC | 10 mt | 125 | PhP | 1846 | PhP | 1647 | 8.4391 | 10.9709 | 13.5026 | PhP | 67.9 | PhP | 744.9241 | 0.0127 | 0.0165 | 0.0203 | PhP | 294 | PhP | 4.851 | PhP | 2396.78 | 550.78
2.3 | Tandem Steel Roller | HD110 | 11 mt | 134 | PhP | 2061 | PhP | 1839 | 9.0467 | 11.7608 | 14.4748 | PhP | 67.9 | PhP | 798.5583 | 0.0136 | 0.0177 | 0.0217 | PhP | 294 | PhP | 5.2038 | PhP | 2642.76 | 581.76
2.4 | Plate Compactor | 400-500 Gasoline Engine |  | 5 | PhP | 123 | PhP |  | 0.3376 | 0.4389 | 0.5401 | PhP | 67.9 | PhP | 29.8013 | 0.0005 | 0.0007 | 0.0008 | PhP | 294 | PhP | 0.2058 | PhP | 153.01 | 30.01
3. LIFTING EQUIPMENT | [8 empty] | FUEL CONSUMPTION (L/hr) | [6 empty] | OIL/LUBRICANTS (L/hr) | [6 empty] | RENTAL RATE/ OPERATED WITH FUEL & OIL/LUBRICANT |  | 0
DESCRIPTION |  | MODEL | CAPACITY | FLYWHEEL HORSEPOWER | RENTAL RATE/ OPERATED |  | RENTAL RATE/ OPERATED DRY |  | LOW | AVERAGE | HIGH | *FUEL COST PER LITER |  | FUEL COST |  | LOW | AVERAGE | HIGH | *OIL/LUBRICANT COST PER LITER |  | OIL/LUBRICANT COST |  |  |  | 0
3.1 | Crawler Crane | All Models | 21-25 mt | 145 | PhP | 1522 | PhP | 1359 | 9.7894 | 12.7262 | 15.663 | PhP | 67.9 | PhP | 864.109 | 0.0147 | 0.0191 | 0.0235 | PhP | 294 | PhP | 5.6154 | PhP | 2228.72 | 706.72
3.2 | Crawler Crane | All Models | 36-40 mt | 190 | PhP | 1902 | PhP | 1698 | 12.8275 | 16.6758 | 20.524 | PhP | 67.9 | PhP | 1132.2868 | 0.0192 | 0.025 | 0.0308 | PhP | 294 | PhP | 7.35 | PhP | 2837.64 | 935.64
3.3 | Crawler Crane with Bucket | All Models | 36-40 mt | 190 | PhP | 2282.4 | PhP | 2037.6 | 12.8275 | 16.6758 | 20.524 | PhP | 67.9 | PhP | 1132.2868 | 0.0192 | 0.025 | 0.0308 | PhP | 294 | PhP | 7.35 | PhP | 3177.24 | 894.84
3.4 | Crawler Crane | All Models | 41-45 mt | 190 | PhP | 2151 | PhP | 1920 | 12.8275 | 16.6758 | 20.524 | PhP | 67.9 | PhP | 1132.2868 | 0.0192 | 0.025 | 0.0308 | PhP | 294 | PhP | 7.35 | PhP | 3059.64 | 908.64
3.5 | Crawler Crane | All Models | 51-60 mt | 275 | PhP | 2778 | PhP | 2480 | 18.5661 | 24.1359 | 29.7057 | PhP | 67.9 | PhP | 1638.8276 | 0.0278 | 0.0362 | 0.0446 | PhP | 294 | PhP | 10.6428 | PhP | 4129.47 | 1351.47
3.6 | Crawler Crane | All Models | 61-70 mt | 275 | PhP | 3572 | PhP | 3188 | 18.5661 | 24.1359 | 29.7057 | PhP | 67.9 | PhP | 1638.8276 | 0.0278 | 0.0362 | 0.0446 | PhP | 294 | PhP | 10.6428 | PhP | 4837.47 | 1265.47
3.7 | Crawler Crane | All Models | 71-80 mt | 285 | PhP | 3595 | PhP | 3208 | 19.2412 | 25.0136 | 30.7859 | PhP | 67.9 | PhP | 1698.4234 | 0.0289 | 0.0376 | 0.0462 | PhP | 294 | PhP | 11.0544 | PhP | 4917.48 | 1322.48
3.8 | Truck Mounted Crane | All Models | 21-25 mt | 200 | PhP | 1631 | PhP | 1268 | 13.5026 | 17.5534 | 21.6042 | PhP | 67.9 | PhP | 1191.8759 | 0.0203 | 0.0264 | 0.0324 | PhP | 294 | PhP | 7.7616 | PhP | 2467.64 | 836.64
3.9 | Truck Mounted Crane | All Models | 31-35 mt | 238 | PhP | 1861 | PhP | 1541 | 16.0681 | 20.8886 | 25.709 | PhP | 67.9 | PhP | 1418.3359 | 0.0241 | 0.0314 | 0.0386 | PhP | 294 | PhP | 9.2316 | PhP | 2968.57 | 1107.57
3.1 | Truck Mounted Crane | All Models | 41-45 mt | 246 | PhP | 2606 | PhP | 1758 | 16.6082 | 21.5907 | 26.5731 | PhP | 67.9 | PhP | 1466.0085 | 0.0249 | 0.0324 | 0.0399 | PhP | 294 | PhP | 9.5256 | PhP | 3233.53 | 627.53
3.11 | Truck Mounted Crane with Bucket | All Models | 41-45 mt | 246 | PhP | 3127.2 | PhP | 2109.6 | 16.6082 | 21.5907 | 26.5731 | PhP | 67.9 | PhP | 1466.0085 | 0.0249 | 0.0324 | 0.0399 | PhP | 294 | PhP | 9.5256 | PhP | 3585.13 | 457.93
3.12 | Truck Mounted Crane | All Models | 51-60 mt | 280 | PhP | 3237 | PhP | 2462 | 18.9036 | 24.5747 | 30.2458 | PhP | 67.9 | PhP | 1668.6221 | 0.0284 | 0.0369 | 0.0454 | PhP | 294 | PhP | 10.8486 | PhP | 4141.47 | 904.47
3.13 | Topless Tower Crane | MDT 98-1.2M | 55M x 6T/1.2T |  | PhP | 4221 | PhP |  |  |  |  | PhP | 67.9 | PhP | 0 |  |  |  | PhP | 294 | PhP | 0 | PhP | 4221 | 0
3.14 | Topless Tower Crane | MDT 128 | 55M x 6T/1.6T |  | PhP | 5664 | PhP |  |  |  |  | PhP | 67.9 | PhP | 0 |  |  |  | PhP | 294 | PhP | 0 | PhP | 5664 | 0
3.15 | Topless Tower Crane | MDT 132 G8 | 55M x 8T/1.6T |  | PhP | 8605 | PhP |  |  |  |  | PhP | 67.9 | PhP | 0 |  |  |  | PhP | 294 | PhP | 0 | PhP | 8605 | 0
3.16 | Topless Tower Crane | MDT 162 H8 | 60M x 8T/1.8T |  | PhP | 8895 | PhP |  |  |  |  | PhP | 67.9 | PhP | 0 |  |  |  | PhP | 294 | PhP | 0 | PhP | 8895 | 0
3.17 | Topless Tower Crane | MDT 178 | 60M x 8T/1.5T |  | PhP | 6419 | PhP |  |  |  |  | PhP | 67.9 | PhP | 0 |  |  |  | PhP | 294 | PhP | 0 | PhP | 6419 | 0
3.18 | Topless Tower Crane | MDT 192-H12 | 60M x 12T/2.2T |  | PhP | 8390 | PhP |  |  |  |  | PhP | 67.9 | PhP | 0 |  |  |  | PhP | 294 | PhP | 0 | PhP | 8390 | 0
3.19 | Aerial Lift, Self Propelled, Scissor Lift | GS4080 Gas/Diesel Driven | 40 ft hts x 46 ft Range | 60 | PhP | 1386 | PhP | 1164 | 4.0508 | 5.266 | 6.4812 | PhP | 67.9 | PhP | 357.5614 | 0.0061 | 0.0079 | 0.0097 | PhP | 294 | PhP | 2.3226 | PhP | 1523.88 | 137.88
4. EXCAVATING EQUIPMENT | [8 empty] | FUEL CONSUMPTION (L/hr) | [6 empty] | OIL/LUBRICANTS (L/hr) | [6 empty] | RENTAL RATE/ OPERATED WITH FUEL & OIL/LUBRICANT |  | 0
DESCRIPTION |  | MODEL | CAPACITY | FLYWHEEL HORSEPOWER | RENTAL RATE/ OPERATED |  | RENTAL RATE/ OPERATED DRY |  | LOW | AVERAGE | HIGH | *FUEL COST PER LITER |  | FUEL COST |  | LOW | AVERAGE | HIGH | *OIL/LUBRICANT COST PER LITER |  | OIL/LUBRICANT COST |  |  |  | 0
4.1 | Backhoe | SOLAR 220 LC-3 | 0.80 m3/1.04 yd30.80 m3/1.04 yd30.80 m3/1.04 yd30.80 m3/1.04 yd30.80 m3/1.04 yd30.80 m3/1.04 yd3 | 138 | PhP | 2096 | PhP | 1761 | 9.3168 | 12.1119 | 14.9069 | PhP | 67.9 | PhP | 822.398 | 0.014 | 0.0182 | 0.0224 | PhP | 294 | PhP | 5.3508 | PhP | 2588.75 | 492.75
4.2 | Backhoe with Breaker | SOLAR 220 LC-3 | 0.80 m3/1.04 yd30.80 m3/1.04 yd30.80 m3/1.04 yd30.80 m3/1.04 yd30.80 m3/1.04 yd30.80 m3/1.04 yd3 | 138 | PhP | 2724.8 | PhP | 2289.3 | 9.3168 | 12.1119 | 14.9069 | PhP | 67.9 | PhP | 822.398 | 0.014 | 0.0182 | 0.0224 | PhP | 294 | PhP | 5.3508 | PhP | 3117.05 | 392.25
4.3 | Backhoe, Wheel Mounted | PW60N-1 | 0.28 m3/0.37 yd30.28 m3/0.37 yd30.28 m3/0.37 yd30.28 m3/0.37 yd30.28 m3/0.37 yd30.28 m3/0.37 yd3 | 50 | PhP | 922 | PhP | 774 | 3.3757 | 4.3884 | 5.401 | PhP | 67.9 | PhP | 297.9724 | 0.0051 | 0.0066 | 0.0081 | PhP | 294 | PhP | 1.9404 | PhP | 1073.91 | 151.91
5. FOUNDATION EQUIPMENT | [8 empty] | FUEL CONSUMPTION (L/hr) | [6 empty] | OIL/LUBRICANTS (L/hr) | [6 empty] | RENTAL RATE/ OPERATED WITH FUEL & OIL/LUBRICANT |  | 0
DESCRIPTION |  | MODEL | CAPACITY | FLYWHEEL HORSEPOWER | RENTAL RATE/ OPERATED |  | RENTAL RATE/ OPERATED DRY |  | LOW | AVERAGE | HIGH | *FUEL COST PER LITER |  | FUEL COST |  | LOW | AVERAGE | HIGH | *OIL/LUBRICANT COST PER LITER |  | OIL/LUBRICANT COST |  |  |  | 0
5.1 | Diesel Hammer | K25 - DSL | 7500 kg-m |  | PhP | 1286 | PhP | 1080 |  |  |  | PhP | 67.9 | PhP | 0 |  |  |  | PhP | 294 | PhP | 0 | PhP | 1286 | 0
5.2 | Vibro Hammer | VIBRO FONCEUR, PTC25H1A | 45000 kg-m | 272.22 | PhP | 3069 | PhP | 2578 | 18.3784 | 23.8919 | 29.4054 | PhP | 67.9 | PhP | 1622.26 | 0.0276 | 0.0359 | 0.0441 | PhP | 294 | PhP | 10.5546 | PhP | 4210.81 | 1141.81
5.3 | Vibro Hammer | MHF12 w/ Hyd. Power Pack | 120 kN-m | 222 | PhP | 4118 | PhP | 3459 | 14.9879 | 19.4843 | 23.9806 | PhP | 67.9 | PhP | 1322.984 | 0.0225 | 0.0293 | 0.036 | PhP | 294 | PhP | 8.6142 | PhP | 4790.6 | 672.6
5.4 | Vibro Hammer | DPD600T Hydraulic Pile Driver | 60 ton | 201 | PhP | 2123 | PhP | 1784 | 13.5701 | 17.6412 | 21.7122 | PhP | 67.9 | PhP | 1197.8375 | 0.0204 | 0.0265 | 0.0326 | PhP | 294 | PhP | 7.791 | PhP | 2989.63 | 866.63
5.5 | Drilling Rig | C.M.V. TH18/65, 2000mmØ 65m depth & 18000kg-m Drill TorqueC.M.V. TH18/65, 2000mmØ 65m depth & 18000kg-m Drill TorqueC.M.V. TH18/65, 2000mmØ 65m depth & 18000kg-m Drill TorqueC.M.V. TH18/65, 2000mmØ 65m depth & 18000kg-m Drill TorqueC.M.V. TH18/65, 2000mmØ 65m depth & 18000kg-m Drill TorqueC.M.V. TH18/65, 2000mmØ 65m depth & 18000kg-m Drill Torque |  | 300 | PhP | 12637 | PhP | 10615 | 20.2539 | 26.3301 | 32.4062 | PhP | 67.9 | PhP | 1787.8138 | 0.0304 | 0.0395 | 0.0486 | PhP | 294 | PhP | 11.613 | PhP | 12414.43 | -222.57
6. ASPHALTING EQUIPMENT | [8 empty] | FUEL CONSUMPTION (L/hr) | [6 empty] | OIL/LUBRICANTS (L/hr) | [6 empty] | RENTAL RATE/ OPERATED WITH FUEL & OIL/LUBRICANT |  | 0
DESCRIPTION |  | MODEL | CAPACITY | FLYWHEEL HORSEPOWER | RENTAL RATE/ OPERATED |  | RENTAL RATE/ OPERATED DRY |  | LOW | AVERAGE | HIGH | *FUEL COST PER LITER |  | FUEL COST |  | LOW | AVERAGE | HIGH | *OIL/LUBRICANT COST PER LITER |  | OIL/LUBRICANT COST |  |  |  | 0
6.1 | Asphalt Distributor | ROSCO/5 ton | 3000 USG | 100 | PhP | 936 | PhP | 786 | 6.7513 | 8.7767 | 10.8021 | PhP | 67.9 | PhP | 595.9379 | 0.0101 | 0.0132 | 0.0162 | PhP | 294 | PhP | 3.8808 | PhP | 1385.82 | 449.82
6.2 | Asphalt Paver | NF220BIIVDM |  | 80 | PhP | 1833 | PhP | 1539 | 5.401 | 7.0214 | 8.6417 | PhP | 67.9 | PhP | 476.7531 | 0.0081 | 0.0106 | 0.013 | PhP | 294 | PhP | 3.1164 | PhP | 2018.87 | 185.87
7. CONCRETING EQUIPMENT | [8 empty] | FUEL CONSUMPTION (L/hr) | [6 empty] | OIL/LUBRICANTS (L/hr) | [6 empty] | RENTAL RATE/ OPERATED WITH FUEL & OIL/LUBRICANT |  | 0
DESCRIPTION |  | MODEL | CAPACITY | FLYWHEEL HORSEPOWER | RENTAL RATE/ OPERATED |  | RENTAL RATE/ OPERATED DRY |  | LOW | AVERAGE | HIGH | *FUEL COST PER LITER |  | FUEL COST |  | LOW | AVERAGE | HIGH | *OIL/LUBRICANT COST PER LITER |  | OIL/LUBRICANT COST |  |  |  | 0
7.1 | Concrete Paver | COMMANDER III, FOUR-TRACK |  | 169 | PhP | 6765 | PhP | 5683 | 11.4097 | 14.8326 | 18.2555 | PhP | 67.9 | PhP | 1007.1335 | 0.0171 | 0.0223 | 0.0274 | PhP | 294 | PhP | 6.5562 | PhP | 6696.69 | -68.31
7.2 | Concrete Screeder | Wacker Truss Screed |  | 5.5 | PhP | 545 | PhP | 457 | 0.3713 | 0.4827 | 0.5941 | PhP | 67.9 | PhP | 32.7753 | 0.0006 | 0.0008 | 0.0009 | PhP | 294 | PhP | 0.2352 | PhP | 490.01 | -54.99
7.3 | One Bagger Mixer |  | 4-6 |  | PhP | 172 | PhP | 144 |  |  |  | PhP | 67.9 | PhP | 0 |  |  |  | PhP | 294 | PhP | 0 | PhP | 172 | 0
7.4 | Transit Mixer | All Models | 5 ft3/min5 ft3/min5 ft3/min5 ft3/min5 ft3/min | 175 | PhP | 1461 | PhP | 1227 | 11.8148 | 15.3592 | 18.9036 | PhP | 67.9 | PhP | 1042.8897 | 0.0177 | 0.0231 | 0.0284 | PhP | 294 | PhP | 6.7914 | PhP | 2276.68 | 815.68
7.5 | Concrete Pump | Diesel Driven, Trailer-Mounted Less Pipe | 100 ft3/min100 ft3/min100 ft3/min100 ft3/min100 ft3/min | 130 | PhP | 2076 | PhP | 1744 | 8.7767 | 11.4097 | 14.0427 | PhP | 67.9 | PhP | 774.7186 | 0.0132 | 0.0172 | 0.0211 | PhP | 294 | PhP | 5.0568 | PhP | 2523.78 | 447.78
7.6 | Grouting Machine | GARNER DENVER 6X3X6, Air Driven |  |  | PhP | 866.25 | PhP |  |  |  |  | PhP | 67.9 | PhP | 0 |  |  |  | PhP | 294 | PhP | 0 | PhP | 866.25 | 0
8. HAULING EQUIPMENT | [8 empty] | FUEL CONSUMPTION (L/hr) | [6 empty] | OIL/LUBRICANTS (L/hr) | [6 empty] | RENTAL RATE/ OPERATED WITH FUEL & OIL/LUBRICANT |  | 0
DESCRIPTION |  | MODEL | CAPACITY | FLYWHEEL HORSEPOWER | RENTAL RATE/ OPERATED |  | RENTAL RATE/ OPERATED DRY |  | LOW | AVERAGE | HIGH | *FUEL COST PER LITER |  | FUEL COST |  | LOW | AVERAGE | HIGH | *OIL/LUBRICANT COST PER LITER |  | OIL/LUBRICANT COST |  |  |  | 0
8.1 | Dump Truck | All Models | 12 yd312 yd312 yd312 yd312 yd3 | 290 | PhP | 1420 | PhP | 1193 | 19.5788 | 25.4524 | 31.326 | PhP | 67.9 | PhP | 1728.218 | 0.0294 | 0.0382 | 0.047 | PhP | 294 | PhP | 11.2308 | PhP | 2932.45 | 1512.45
8.2 | Cargo/Service Truck | All Models | 2-5 mt | 160 | PhP | 783 | PhP | 598 | 10.8021 | 14.0427 | 17.2833 | PhP | 67.9 | PhP | 953.4993 | 0.0162 | 0.0211 | 0.0259 | PhP | 294 | PhP | 6.2034 | PhP | 1557.7 | 774.7
8.3 | Boom Truck | NXG1160D3ZAL1X |  | 197 | PhP | 1930 | PhP | 1678 | 13.3001 | 17.2901 | 21.2801 | PhP | 67.9 | PhP | 1173.9978 | 0.02 | 0.026 | 0.0319 | PhP | 294 | PhP | 7.644 | PhP | 2859.64 | 929.64
8.4 | Cargo/Service Truck | All Models | 9-10 mt | 270 | PhP | 1212 | PhP | 925 | 18.2285 | 23.6971 | 29.1656 | PhP | 67.9 | PhP | 1609.0331 | 0.0273 | 0.0355 | 0.0437 | PhP | 294 | PhP | 10.437 | PhP | 2544.47 | 1332.47
8.5 | Water Truck/Pump | All Makes | 16000 L | 360 | PhP | 2450 | PhP | 2058 | 24.3047 | 31.5961 | 38.8875 | PhP | 67.9 | PhP | 2145.3752 | 0.0365 | 0.0474 | 0.0583 | PhP | 294 | PhP | 13.9356 | PhP | 4217.31 | 1767.31
9. AIR EQUIPMENT | [8 empty] | FUEL CONSUMPTION (L/hr) | [6 empty] | OIL/LUBRICANTS (L/hr) | [6 empty] | RENTAL RATE/ OPERATED WITH FUEL & OIL/LUBRICANT |  | 0
DESCRIPTION |  | MODEL | CAPACITY | FLYWHEEL HORSEPOWER | RENTAL RATE/ OPERATED |  | RENTAL RATE/ OPERATED DRY |  | LOW | AVERAGE | HIGH | *FUEL COST PER LITER |  | FUEL COST |  | LOW | AVERAGE | HIGH | *OIL/LUBRICANT COST PER LITER |  | OIL/LUBRICANT COST |  |  |  | 0
9.1 | Air Compressor | All Models | 15-35 cfm | 20 | PhP | 205 | PhP | 164 | 1.3503 | 1.7554 | 2.1604 | PhP | 67.9 | PhP | 119.1917 | 0.002 | 0.0026 | 0.0032 | PhP | 294 | PhP | 0.7644 | PhP | 283.96 | 78.96
9.2 | Air Compressor | All Models | 126-160 cfm | 51 | PhP | 450 | PhP | 361 | 3.4432 | 4.4762 | 5.5091 | PhP | 67.9 | PhP | 303.934 | 0.0052 | 0.0068 | 0.0083 | PhP | 294 | PhP | 1.9992 | PhP | 666.93 | 216.93
9.3 | Air Compressor | All Models | 161-185 cfm | 69 | PhP | 502 | PhP | 402 | 4.6584 | 6.0559 | 7.4534 | PhP | 67.9 | PhP | 411.1956 | 0.007 | 0.0091 | 0.0112 | PhP | 294 | PhP | 2.6754 | PhP | 815.87 | 313.87
9.4 | Air Compressor | All Models | 356-450 cfm | 130 | PhP | 965 | PhP | 772 | 8.7767 | 11.4097 | 14.0427 | PhP | 67.9 | PhP | 774.7186 | 0.0132 | 0.0172 | 0.0211 | PhP | 294 | PhP | 5.0568 | PhP | 1551.78 | 586.78
9.5 | Diamond Drill | CP-8 |  |  | PhP | 201.25 | PhP | 168.75 |  |  |  | PhP | 67.9 | PhP | 0 |  |  |  | PhP | 294 | PhP | 0 | PhP | 201.25 | 0
9.6 | Jackhammer |  |  |  | PhP | 150 | PhP |  |  |  |  | PhP | 67.9 | PhP | 0 |  |  |  | PhP | 294 | PhP | 0 | PhP | 150 | 0
9.7 | Pneumatic Drilling Machine |  |  |  | PhP | 170 | PhP |  |  |  |  | PhP | 67.9 | PhP | 0 |  |  |  | PhP | 294 | PhP | 0 | PhP | 170 | 0
10. PUMPING EQUIPMENT | [8 empty] | FUEL CONSUMPTION (L/hr) | [6 empty] | OIL/LUBRICANTS (L/hr) | [6 empty] | RENTAL RATE/ OPERATED WITH FUEL & OIL/LUBRICANT |  | 0
DESCRIPTION |  | MODEL | CAPACITY | FLYWHEEL HORSEPOWER | RENTAL RATE/ OPERATED |  | RENTAL RATE/ OPERATED DRY |  | LOW | AVERAGE | HIGH | *FUEL COST PER LITER |  | FUEL COST |  | LOW | AVERAGE | HIGH | *OIL/LUBRICANT COST PER LITER |  | OIL/LUBRICANT COST |  |  |  | 0
10.1 | Water Pump, 100 mm suction ØWater Pump, 100 mm suction ØWater Pump, 100 mm suction ØWater Pump, 100 mm suction Ø | 1800 |  | 7.5 | PhP | 123.38 | PhP |  | 0.5063 | 0.6583 | 0.8102 | PhP | 67.9 | PhP | 44.6986 | 0.0008 | 0.001 | 0.0012 | PhP | 294 | PhP | 0.294 | PhP | 168.37 | 44.99
10.2 | Water Pump, 100 mm suction ØWater Pump, 100 mm suction ØWater Pump, 100 mm suction ØWater Pump, 100 mm suction Ø | 2667 | 50 | 16 | PhP | 266.25 | PhP |  | 1.0802 | 1.4043 | 1.7283 | PhP | 67.9 | PhP | 95.352 | 0.0016 | 0.0021 | 0.0026 | PhP | 294 | PhP | 0.6174 | PhP | 362.22 | 95.97
11. POWER GENERATING EQUIPMENT | [8 empty] | FUEL CONSUMPTION (L/hr) | [6 empty] | OIL/LUBRICANTS (L/hr) | [6 empty] | RENTAL RATE/ OPERATED WITH FUEL & OIL/LUBRICANT |  | 0
DESCRIPTION |  | MODEL | CAPACITY |  | RENTAL RATE/ OPERATED |  | RENTAL RATE/ OPERATED DRY |  | LOW | AVERAGE | HIGH | *FUEL COST PER LITER |  | FUEL COST |  | LOW | AVERAGE | HIGH | *OIL/LUBRICANT COST PER LITER |  | OIL/LUBRICANT COST |  |  |  | 0
|  |  | kW | kVA | [20 empty] | 0
11.1 | Generator Set | All Makes | 300 | 375 | PhP | 872.87 | PhP |  | 27.15 | 35.295 | 43.44 | PhP | 67.9 | PhP | 2396.5305 | 0.0407 | 0.053 | 0.0652 | PhP | 294 | PhP | 15.582 | PhP | 3284.98 | 2412.11
11.2 | Generator Set | All Makes | 700 | 875 | PhP | 2147.27 | PhP |  | 63.35 | 82.355 | 101.36 | PhP | 67.9 | PhP | 5591.9045 | 0.095 | 0.1235 | 0.152 | PhP | 294 | PhP | 36.309 | PhP | 7775.48 | 5628.21
11.3 | Generator Set | All Makes | 900 | 1125 | PhP | 2659.44 | PhP |  | 81.45 | 105.885 | 130.32 | PhP | 67.9 | PhP | 7189.5915 | 0.1222 | 0.1589 | 0.1955 | PhP | 294 | PhP | 46.7166 | PhP | 9895.75 | 7236.31
12. SHOP EQUIPMENT | [8 empty] | FUEL CONSUMPTION (L/hr) | [6 empty] | OIL/LUBRICANTS (L/hr) | [6 empty] | RENTAL RATE/ OPERATED WITH FUEL & OIL/LUBRICANT |  | 0
DESCRIPTION |  | MODEL | AMPERE | FLYWHEEL HORSEPOWER | RENTAL RATE/ OPERATED |  | RENTAL RATE/ OPERATED DRY |  | LOW | AVERAGE | HIGH | *FUEL COST PER LITER |  | FUEL COST |  | LOW | AVERAGE | HIGH | *OIL/LUBRICANT COST PER LITER |  | OIL/LUBRICANT COST |  |  |  | 0
12.1 | Welding Machine | Gas/Diesel Driven | 300 | 48 | PhP | 371 | PhP | 311 | 3.2406 | 4.2128 | 5.185 | PhP | 67.9 | PhP | 286.0491 | 0.0049 | 0.0064 | 0.0078 | PhP | 294 | PhP | 1.8816 | PhP | 598.93 | 227.93
12.2 | Welding Machine | Gas/Diesel Driven | 500 | 70 | PhP | 539 | PhP | 453 | 4.7259 | 6.1437 | 7.5615 | PhP | 67.9 | PhP | 417.1572 | 0.0071 | 0.0092 | 0.0113 | PhP | 294 | PhP | 2.7048 | PhP | 872.86 | 333.86
12.3 | Welding Machine | Electric Driven/DC Output | 500 |  | PhP | 391 | PhP |  |  |  |  | PhP | 67.9 | PhP | 0 |  |  |  | PhP | 294 | PhP | 0 | PhP | 391 | 0
14. MISCELLANEOUS EQUIPMENT | [8 empty] | FUEL CONSUMPTION (L/hr) | [6 empty] | OIL/LUBRICANTS (L/hr) | [6 empty] | RENTAL RATE/ OPERATED WITH FUEL & OIL/LUBRICANT |  | 0
DESCRIPTION |  | MAKE/MODEL/CAPACITY |  | FLYWHEEL HORSEPOWER | RENTAL RATE/ OPERATED |  | RENTAL RATE/ OPERATED DRY |  | LOW | AVERAGE | HIGH | *FUEL COST PER LITER |  | FUEL COST |  | LOW | AVERAGE | HIGH | *OIL/LUBRICANT COST PER LITER |  | OIL/LUBRICANT COST |  |  |  | 0
14.1 | Portable Breaker | WACKER PORTABLE PETROL BREAKER, BHF30S |  | 4 | PhP | 123.2 | PhP |  | 0.2701 | 0.3511 | 0.4321 | PhP | 67.9 | PhP | 23.8397 | 0.0004 | 0.0005 | 0.0006 | PhP | 294 | PhP | 0.147 | PhP | 147.19 | 23.99
14.2 | Chainsaw | HUSQVARNA 2100 CD with CR22, 7 ft Reach, 9 in Standard Blade |  |  | PhP | 75.36 | PhP |  |  |  |  | PhP | 67.9 | PhP | 0 |  |  |  | PhP | 294 | PhP | 0 | PhP | 75.36 | 0
14.3 | Concrete Vibrator | Flexible Shaft Type 2" Head Ø with 5 Amperes Gasoline Drive UnitFlexible Shaft Type 2" Head Ø with 5 Amperes Gasoline Drive UnitFlexible Shaft Type 2" Head Ø with 5 Amperes Gasoline Drive Unit |  |  | PhP | 57.17 | PhP |  |  |  |  | PhP | 67.9 | PhP | 0 |  |  |  | PhP | 294 | PhP | 0 | PhP | 57.17 | 0
14.4 | Concrete Saw | 14" Blade Ø with 4 3/4" Cutting Depth14" Blade Ø with 4 3/4" Cutting Depth14" Blade Ø with 4 3/4" Cutting Depth |  | 7.5 | PhP | 32.64 | PhP |  | 0.5063 | 0.6583 | 0.8102 | PhP | 67.9 | PhP | 44.6986 | 0.0008 | 0.001 | 0.0012 | PhP | 294 | PhP | 0.294 | PhP | 77.63 | 44.99
14.5 | Bar Cutter | 25 mm Maximum Rebar Ø (Grade 40), Single Phase25 mm Maximum Rebar Ø (Grade 40), Single Phase |  |  | PhP | 105.47 | PhP |  |  |  |  | PhP | 67.9 | PhP | 0 |  |  |  | PhP | 294 | PhP | 0 | PhP | 105.47 | 0
14.6 | Bar Bender | 25 mm Maximum Rebar Ø, Three Phase |  |  | PhP | 168.75 | PhP |  |  |  |  | PhP | 67.9 | PhP | 0 |  |  |  | PhP | 294 | PhP | 0 | PhP | 168.75 | 0
14.7 | Tower Lights | Tower Height = 28 ft, No. of Lights = 4 x 1000 watts, hp = 10.50, Generator = 5 kW |  |  | PhP | 260.86 | PhP |  |  |  |  | PhP | 67.9 | PhP | 0 |  |  |  | PhP | 294 | PhP | 0 | PhP | 260.86 | 0
15. PLANTS | [8 empty] | FUEL CONSUMPTION (L/hr) | [6 empty] | OIL/LUBRICANTS (L/hr) | [6 empty] | RENTAL RATE/ OPERATED WITH FUEL & OIL/LUBRICANT |  | 0
DESCRIPTION |  | MAKE/MODEL/CAPACITY |  |  | RENTAL RATE/ OPERATED |  | RENTAL RATE/ OPERATED DRY |  | LOW | AVERAGE | HIGH | *FUEL COST PER LITER |  | FUEL COST |  | LOW | AVERAGE | HIGH | *OIL/LUBRICANT COST PER LITER |  | OIL/LUBRICANT COST |  |  |  | 0
15.1 | Asphalt Concrete Plant | Complete with: Cold Feed System, bins, feeder and collecting conveyors. Drying and Burner System, feed conveyors drum and fully modulating burner. Fuel feed system. Screening-Weighing-Mixing System, hot elevator, vibrating screen, hot bins, weighing scale and twinshaft pugmill mixer. Dust collection and filler feeding system, bag filter and exhaust fan. Thermal Hot Oil System, delivery pump and heater and Computerized Plant Control System. |  |  | PhP | 4286.63 | PhP | [15 empty] | PhP | 4286.63 | 0
15.2 | Concrete Batch Plant | Complete with: Cement silo and screw conveyor system. Water and supply system. Aggregate storage bins with vibrators and conveyors system. Weigh hopper with electronic loadcell for aggregates, cement, water and admixture. Central twinshaft mixer. Hydraulic System and Computerized Plant Control System. |  |  | PhP | 1759.5 | PhP | [15 empty] | PhP | 1759.5 | 0
18. OTHERS | [8 empty] | FUEL CONSUMPTION (L/hr) | [6 empty] | OIL/LUBRICANTS (L/hr) | [6 empty] | RENTAL RATE/ OPERATED WITH FUEL & OIL/LUBRICANT |  | 0
DESCRIPTION |  | MAKE/MODEL/CAPACITY |  |  | RENTAL RATE/ OPERATED |  | RENTAL RATE/ OPERATED DRY |  | LOW | AVERAGE | HIGH | *FUEL COST PER LITER |  | FUEL COST |  | LOW | AVERAGE | HIGH | *OIL/LUBRICANT COST PER LITER |  | OIL/LUBRICANT COST |  |  |  | 0
18.1 | Power Broom | Towed Type with Engine 2 m wide 6-30 km/h sweeping capacity |  |  | PhP | 130.54 | PhP | [15 empty] | PhP | 130.54 | 0
18.2 | Hydroseeding Machine |  |  |  | PhP | 952 | PhP | [15 empty] | PhP | 952 | 0
18.3 | Applicator Machine |  |  |  | PhP | 93.75 | PhP | [15 empty] | PhP | 93.75 | 0
18.4 | Kneading Machine |  |  |  | PhP | 187.5 | PhP | [15 empty] | PhP | 187.5 | 0
18.5 | Cutting Outfit |  |  |  | PhP | 45.45 | PhP | [15 empty] | PhP | 45.45 | 0
18.6 | Steel Wheel with Nylon Rope |  |  |  | PhP | 300 | PhP | [15 empty] | PhP | 300 | 0
18.7 | Improvised Bamboo with Bucket |  |  |  | PhP | 200 | PhP | [15 empty] | PhP | 200 | 0
18.8 | Asphalt Kettle/Drum |  |  |  | PhP | 10 | PhP | [15 empty] | PhP | 10 | 0
18.9 | SPT & Desanding Machine |  |  |  | PhP | 559 | PhP | [15 empty] | PhP | 559 | 0
18.1 | Drop Hammer |  |  |  | PhP | 200 | PhP | [15 empty] | PhP | 200 | 0
18.11 | Drop Hammer with accessories |  |  |  | PhP | 5000 | PhP | [15 empty] | PhP | 5000 | 0
18.12 | 1 Air Compressor with 2 Jack Hammer |  |  |  | PhP | 1265 | PhP | [15 empty] | PhP | 1265 | 0
18.13 | Bentonite Bin |  |  |  | PhP | 280 | PhP | [15 empty] | PhP | 280 | 0
18.14 | Bentonite Mixer |  |  |  | PhP | 173 | PhP | [15 empty] | PhP | 173 | 0
18.15 | Tremie Pipe Set |  |  |  | PhP | 320 | PhP | [15 empty] | PhP | 320 | 0
18.16 | Pile Integrity Testing (Sonic) & accessories (includes professional fee of Structural Engineer & reports) |  |  |  | PhP | 65000 | PhP | [15 empty] | PhP | 65000 | 0
18.17 | Dynamic Pile Testing (includes professional fee of Structural Engineer & reports) |  |  |  | PhP | 103000 | PhP | [15 empty] | PhP | 103000 | 0
18.18 | Pile Integrity Testing & accessories (includes professional fee of Structural Engineer & reports) |  |  |  | PhP | 37000 | PhP | [15 empty] | PhP | 37000 | 0
18.19 | Grinding Machine and accessories |  |  |  | PhP | 75.38 | PhP | [15 empty] | PhP | 75.38 | 0
18.2 | Stressing (Jack) Machine |  |  |  | PhP | 2500 | PhP | [15 empty] | PhP | 2500 | 0
18.21 | Dolly |  |  |  | PhP | 1249 | PhP | [15 empty] | PhP | 1249 | 0
18.22 | Wood/Steel Ladder |  |  |  | PhP | 100 | PhP | [15 empty] | PhP | 100 | 0
Note: Fuel & Oil/Lubricant cost as of October 26, 2022
| Prepared by: |  | Checked/Submitted by:
| WINLOVE A. ESTEVES |  | MARK ANGELO E. SURIL
| Engineer II |  | Engineer II
| Planning and Design Section |  | Planning and Design Section

## HAULING_COST_(cement)
Name of Project | : | CONSTRUCTION OF ROAD
Location | : | BRGY. L. PIMENTEL, SAN LUIS, AURORA
Material | : | Cement
Material Source | : | Baler
Material Cost | : | 260 | per bag | [10 empty] | Baler | 232000
Distance (from source to site) | : | 23.2 | km | [10 empty] | Project Site | 265000
Free Hauling Distance | : | 5 | km | [10 empty] | Distance | 33 | km
Hauling Distance | : | 18.2 | km
TERRAIN CONDITION | DISTANCE (km) |  | RATE (km/h) | LOADING TIME (min) | LOADING TIME (hr) | TRAVEL TIME (LOADED) (hr) | UNLOAD AND MANEUVER (min) | UNLOAD AND MANEUVER (hr) | RATE (km/h) | TRAVEL TIME (EMPTY) (hr) | CYCLE TIME | ALLOWANCE FOR DELAY (10% of Cycle Time) | TOTAL CYCLE TIME (hr)
FLAT
Paved | 18.2 |  | 35 | 3 | 0.05 | 0.57 | 2 | 0.033333 | 55 | 0.36424 | 0.93424 | 0.093424 | 1.0277
Unpaved |  |  | 30 |  | 0 | 0 |  | 0 | 45 | 0 | 0 | 0 | 0
ROLLING
Paved | 0 |  | 30 |  | 0 | 0 |  | 0 | 40 | 0 | 0 | 0 | 0
Unpaved |  |  | 25 |  | 0 | 0 |  | 0 | 35 | 0 | 0 | 0 | 0
MOUNTAINOUS
Paved | 0 |  | 20 |  | 0 | 0 |  | 0 | 30 | 0 | 0 | 0 | 0
Unpaved |  |  | 15 |  | 0 | 0 |  | 0 | 25 | 0 | 0 | 0 | 0
[13 empty] | 1.0277 | 18.2
LABOR | NO. OF PERSON/S |  | NO. OF HOUR/S |  | HOURLY RATE |  | AMOUNT
Helper | 2 |  | 1.0277 |  | 61.75 |  | 126.9168 |  |  | Prepared by:
Driver | 1 |  | 1.0277 |  | 80.05 |  | 82.2647
EQUIPMENT | NO. OF UNITS |  | NO. OF HOUR/S |  | HOURLY RATE |  | AMOUNT
Trailer Truck | 1 |  | 1.0277 |  | 2544.47 |  | 2614.867 |  |  | WINLOVE A. ESTEVES
TOTAL COST | [6 empty] | 2824.0486 |  |  | Engineer II
Planning and Design Section
HAULING COST per Kilogram | 1= | Total Cost |  | 1= | 2824.0486 | 1= | 0.058834 |  |  | Checked by:
|  | Total capacity of Truck (kg) |  |  | 48000
Hauling Cost per Bag of Cement = |  |  | 2 | Cost per Bag of Cement = |  |  | 260 |  |  | MARK ANGELO E. SURIL
Engineer II
|  | Note: 1 Bag of Cement = 40kg | [7 empty] | Planning and Design Section

## HAULING_COST_(RSB)
Name of Project | : | CONSTRUCTION OF ROAD
Location | : | BRGY. L. PIMENTEL, SAN LUIS, AURORA
Material | : | Reinforcing Steel Bars Deformed Grade 40
Material Source | : | NCR
Material Cost | : | 41
Distance (from source to site) | : | 250.4 | km
Free Hauling Distance | : | 5 | km
Hauling Distance | : | 245.4 | km
TERRAIN CONDITION | DISTANCE (km) |  | RATE (km/h) | LOADING TIME (min) | LOADING TIME (hr) | TRAVEL TIME (LOADED) (hr) | UNLOAD AND MANEUVER (min) | UNLOAD AND MANEUVER (hr) | RATE (km/h) | TRAVEL TIME (EMPTY) (hr) | CYCLE TIME | ALLOWANCE FOR DELAY (10% of Cycle Time) | TOTAL CYCLE TIME (hr) | Rizal Monument to Aurora Province Welcoming Arch (Villa) | Rizal Monument to Regional Boundary (Canili) | Boundary (Villa/Canili) to Project Site | Boundary (Villa) to DPWH
FLAT
Paved | 183.4 |  | 35 | 3 | 0.05 | 5.29 | 2 | 0.033333 | 55 | 3.3679 | 8.6579 | 0.86579 | 9.5237 | 151 | 156 | 37.4 | 19.2
Unpaved |  |  | 30 |  | 0 | 0 |  | 0 | 45 | 0 | 0 | 0 | 0
ROLLING
Paved | 14 |  | 30 |  | 0 | 0.46667 |  | 0 | 40 | 0.35 | 0.81667 | 0.081667 | 0.89833 | 6 | 13 | 8 | 8
Unpaved |  |  | 25 |  | 0 | 0 |  | 0 | 35 | 0 | 0 | 0 | 0
MOUNTAINOUS
Paved | 48 |  | 20 |  | 0 | 2.4 |  | 0 | 30 | 1.6 | 4 | 0.4 | 4.4 | 10 | 20 | 38 | 38
Unpaved |  |  | 15 |  | 0 | 0 |  | 0 | 25 | 0 | 0 | 0 | 0
T O T A L C Y C L E T I M E | [12 empty] | 14.822 | 167 | 189 | 83.4 | 65.2
LABOR | NO. OF PERSON/S |  | NO. OF HOUR/S |  | HOURLY RATE |  | AMOUNT | [6 empty] | 7.411
Helper | 2 |  | 14.822 |  | 61.75 |  | 1830.517 |  |  | Prepared by:
Driver | 1 |  | 14.822 |  | 80.05 |  | 1186.5011
EQUIPMENT | NO. OF UNITS |  | NO. OF HOUR/S |  | HOURLY RATE |  | AMOUNT
Cargo/Service Truck (9-10mt, 270 hp) | 1 |  | 14.822 |  | 2544.47 |  | 37714.1343 |  |  | WINLOVE A. ESTEVES
TOTAL COST | [6 empty] | 40731.1524 |  |  | Engineer II
Planning and Design Section
HAULING COST per Kilogram | 1= | Total Cost |  | 1= | 40731.1524 | 1= | 4.1 |  |  | Checked by:
|  | Total capacity of Truck (kg) |  |  | 10000
MARK ANGELO E. SURIL
Engineer II
Planning and Design Section

## Sheet1
Project | CONSTRUCTION OF ROAD
Location | BRGY. L. PIMENTEL, SAN LUIS, AURORA
Station Limits | LOCATION 1 | 0 | TO
Appropriation | 10000000
Net Length | 1.926 | Lane km
Total Project Duration | 65 | CD
DESCRIPTION OF WORKS TO BE DONE
[6 empty] | Road | CD | Test
PART A | FACILITIES FOR THE ENGINEER |  |  |  | % | 1 | 55 | 6
A.1.1 (3) | Construction of Field Office for the Engineer |  |  |  | 0.62746 | 2 | 52 | 6
|  |  |  | Subtotal | 0.62746 | 3 | 40 | 6
PART B | OTHER GENERAL REQUIREMENTS |  |  |  |  | 4 | 31 | 7
#NAME? | #NAME? |  |  |  | Err:509 | 5 | 39 | 7
B.5 | Project Billboard/ Signboard (DPWH) |  |  |  | 0.087579 | 6 | 14 | 6
B.5 | Project Billboard/ Signboard (COA) |  |  |  | 0.087579 | 7 | 26 | 7
B.7 (2) | Occupational Safety and Health Program |  |  |  | 1.4013 | 8 | 36 | 7
#NAME? | #NAME? |  |  |  | Err:509 | 9 | 10 | 3
B.9 | Mobilization/ Demobilization |  |  |  | 0.85886 | 10 | 84 | 5
|  |  |  | Subtotal | 2.4353 | 11 | 80 | 5
#NAME? | #NAME? |  |  |  |  | 12 | 28 | 7
#NAME? | #NAME? |  |  |  | Err:509
#NAME? | #NAME? |  |  |  | Err:509
#NAME? | #NAME? |  |  |  | Err:509
#NAME? | #NAME? |  |  |  | Err:509
#NAME? | #NAME? |  |  |  | Err:509
#NAME? | #NAME? |  |  |  | Err:509
|  |  |  | Subtotal | 0
#NAME? | #NAME?
#NAME? | #NAME? |  |  |  | Err:509
|  |  |  | Subtotal | Err:509
#NAME? | #NAME?
#NAME? | #NAME? |  |  |  | Err:509
|  |  |  | Subtotal | Err:509
#REF! | #REF!
#NAME? | #NAME? |  |  |  | Err:509
#NAME? | #NAME? |  |  |  | Err:509
|  |  |  | Subtotal | #VALUE!
#NAME? | #NAME?
#NAME? | #NAME? |  |  |  | Err:509
|  |  |  | Subtotal | Err:509
|  |  |  | TOTAL | #VALUE!

## INDEX
INDEX OF DRAWING
SHEET NO. | SHEET CONTENTS
1 | TITLE PAGE
2 | MAPS
3 | GENERAL NOTES, SYMBOLS AND ABBREVIATIONS
4 | GENERAL PLAN, GENERAL ELEVATION, TYPICAL @ PIER SECTION,TYPICAL ABUTMENT SECTION, HYDRAULIC DESIGN DATA & NOTES
5 | FRAMING PLAN, LONGITUDINAL SECTION
6 | SUPERSTRUCTURE CROSS SECTIONS, REINFORCEMENT OVER PIER
7 | GIRDER ELEVATION, DETAILS & SECTION (TYPE-IV) L = 25M
8 | CONCRETE POURING SEQUENCE AND SECTION, GIRDER DESIGN GUIDE AND CAMBER DIAGRAM
9 | END AND INTERMEDIATE DIAPHRAGM DETAILS, SECTION AND FIX CONNECTION
10 | PIER PLAN, ELEVATION, SECTION, SPIRAL SPLICE DETAILS AND RISER REINFORCEMENT DETAILS
11 | DETAILS OF BORED PILE AT ABUTMENT
12 | DETAILS OF BORED PILE AT PIER
13
14
15